## README
My TSPi Workbook - TMA3084 Software Engineering Laboratory
Faculty of Computer Science & Information Technology, UNIMAS ¦ Semester 1, Session 2026/2027 ¦ Member workbook v3.0
| What this is | Your own copy of the TSPi workbook. You record your work here - your time, your defects, your tests, your AI-assisted changes - and nobody else types in this file.
| How it fits together | Your team also keeps one master workbook. Once a week, at the team meeting, you open the EXPORT sheet here and paste its numbers into your row on the master's TEAM sheet, then paste your log rows into the master's shared logs. That is the whole handover.
| Fill in SETUP first | Your name and matric number on SETUP are what the EXPORT sheet stamps onto your numbers, so the team can tell whose row is whose.
| Colour convention | AMBER cells are yours to fill in. GREY cells are calculated - typing over one breaks the summary that depends on it.
| The honest bit | This file is the evidence behind your individual mark. Logging work you did not do is academic dishonesty, and because the master cross-checks your reported hours against the rows you paste in, a workbook that disagrees with itself is visible immediately.
The weekly routine
Every working session: start a LOGT row when you sit down, close it when you get up.
Every defect you fix: a LOGD row, with the phase the mistake was made in.
Every test you run: a LOGTEST row.
Every AI-assisted change: a LOGAI row, with a teammate named as reviewer.
Every week at the meeting: open EXPORT, paste into the master, done.

## SETUP
My Details
Fill this once. Everything else in this workbook reads from here.
Member
Full name
Matric number
Team
Project
| Course | TMA3084 Software Engineering Laboratory
| Semester | Semester 1, Session 2026/2027
| Instructor | Ts. Nurfauza Jali
My commitment
| Hours per week I am committing to | 10
My main role this cycle
My second role, if I have one

## MYTASK
My Task Plan
Only the tasks you own. Actual hours arrive from LOGT by themselves.
Member |  |  |  | My tasks |  | Plan hrs |  | Actual hrs |  | Complete
Task ID | M/stone | Phase | Component | Task | Plan hrs | Plan wk | Actual hrs | Act. wk | Status | Plan value | Earned value
Note on A7: Use the same Task IDs as the team master, so your hours line up with the team plan when you consolidate.

## MYSCHEDULE
My Weekly Schedule
What you planned to put in each week, against what you actually did.
Member |  |  |  | Task plan hrs |  | Schedule hrs |  | Difference
Week | Week starting | Plan hrs | Cum plan | Actual hrs | Cum actual | Plan value | Earned value | Cum EV | Comment
3 | 2026-10-05
4 | 2026-10-12
5 | 2026-10-19
6 | 2026-10-26
7 | 2026-11-02
8 | 2026-11-09 | [7 empty] | Mid-semester break
9 | 2026-11-16
10 | 2026-11-23
11 | 2026-11-30
12 | 2026-12-07
13 | 2026-12-14
14 | 2026-12-21
15 | 2026-12-28

## LOGT
Form LOGT - My Time Recording Log
One row per working session. Delta is calculated; never type over it.
Member |  |  |  | Total hours |  | Sessions
Date | M/stone | Week | Phase | Task ID | What you worked on | Start | Stop | Interrupt (min) | Delta (min) | Comments

## LOGD
Form LOGD - My Defect Recording Log
Every defect you found and fixed. Injected in is the phase the mistake was MADE.
Member |  |  |  | Defects |  | Fix time (hrs)
Date | Defect ID | M/stone | Type | Component | Injected in | Removed in | Fix time (min) | Fix reference | Severity | From AI? | Description & root cause

## LOGTEST
Form LOGTEST - My Test Case Log
Automated tests get a row too.
Member |  |  |  | Cases |  | Pass rate
Date run | Test ID | Module / screen | What is being tested | Type | Expected | Actual | Status | M/stone | Defect ref | Automated?

## LOGAI
Form LOGAI - My AI-Assisted Development Log
Every change where a generator wrote code that reached the repository. The reviewer must not be you.
Member |  |  |  | Entries |  | Lines kept |  |  | Keep rate
Date | M/stone | File / module | Feature | AI tool | Prompt (summarised) | Lines gen. | Lines kept | Keep % | Reviewer | Verdict | Tests? | Test status | Commit / PR ref
Note on J6: A teammate's name. Your own name here is self-review, which does not satisfy the rule - the cell turns red.

## MYSUMP
My Plan Summary
Plan column is yours; actual reads itself out of your logs.
Member
Time in Phase (hours)
Phase | Plan | Actual | Actual % | Description
MGMT |  |  |  | Management & Miscellaneous
STRAT |  |  |  | Launch & Strategy
PLAN |  |  |  | Planning
REQ |  |  |  | Requirements / SRS
STP |  |  |  | System Test Plan
REQINSP |  |  |  | Requirements Inspection
HLD |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  | Integration Test Plan
HLDINSP |  |  |  | HLD Inspection
DLD |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  | Detailed Design Review
TD |  |  |  | Test Development
DLDINSP |  |  |  | Detailed Design Inspection
CODE |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  | Code Inspection
UT |  |  |  | Unit Test
WT |  |  |  | Widget Test
IT |  |  |  | Build & Integration Test
CICD |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  | System Test
UAT |  |  |  | Client Acceptance Test
DOC |  |  |  | Documentation & User Manual
PM |  |  |  | Postmortem
TOTAL
Defects Injected
Phase | Plan | Actual | Actual % | Description
PLAN |  |  |  | Planning
REQ |  |  |  | Requirements / SRS
STP |  |  |  | System Test Plan
REQINSP |  |  |  | Requirements Inspection
HLD |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  | Integration Test Plan
HLDINSP |  |  |  | HLD Inspection
DLD |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  | Detailed Design Review
TD |  |  |  | Test Development
DLDINSP |  |  |  | Detailed Design Inspection
CODE |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  | Code Inspection
UT |  |  |  | Unit Test
WT |  |  |  | Widget Test
IT |  |  |  | Build & Integration Test
CICD |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  | System Test
TOTAL INJECTED
Defects Removed
Phase | Plan | Actual | Actual % | Description
PLAN |  |  |  | Planning
REQ |  |  |  | Requirements / SRS
STP |  |  |  | System Test Plan
REQINSP |  |  |  | Requirements Inspection
HLD |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  | Integration Test Plan
HLDINSP |  |  |  | HLD Inspection
DLD |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  | Detailed Design Review
TD |  |  |  | Test Development
DLDINSP |  |  |  | Detailed Design Inspection
CODE |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  | Code Inspection
UT |  |  |  | Unit Test
WT |  |  |  | Widget Test
IT |  |  |  | Build & Integration Test
CICD |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  | System Test
TOTAL REMOVED
My Size Contribution
| Plan | Actual |  | What to count
New & changed Dart LOC I wrote |  |  |  | Lines of Dart you added or changed, from your merged PRs
SRS / SDD pages I wrote |  |  |  | Pages you personally drafted
Screens I built |  |  |  | Screens you were the main author of
Test cases I wrote |  |  |  | From LOGTEST

## MYSUMQ
My Quality Summary
Your own review discipline. These are the numbers the Quality & Test Manager will ask you about.
Member
My Measures
Measure | Actual | Guideline | Verdict | Reading
Hours logged |  |  |  | Everything you have recorded this semester.
Defects I found |  |  |  | A higher number is better engineering, not worse work.
Defects / KLOC in my code |  |  |  | Needs your LOC on MYSUMP to compute.
Design review / design time |  | 0.5 |  | Time reviewing your own design against time producing it.
Code review / code time |  | 0.5 |  | Review time against time writing and generating code.
My code review rate (LOC/hr) |  | 200 |  | Above 200 and you are reading too fast to find anything.
A/FR (appraisal / failure) |  | 2 |  | Time reviewing against time fixing in test. Below 2 predicts a painful system test.
% of my defects found before test |  | 70% |  | Caught in review rather than by the machine.
My test pass rate |  | 95%
My AI keep rate |  |  |  | Lines that survived review. Low is informative, not shameful.
My AI entries with no reviewer |  | 0 |  | Any row here breaks the review rule.
My AI entries I reviewed myself |  | 0 |  | Self-review does not count as review.

## EXPORT
EXPORT - what to give the team each week
Copy the amber row, Paste Special > Values into your row on the master's TEAM sheet, columns F to K.
| Member |  |  | Matric
Paste this row into the team master (TEAM sheet, columns F to K)
| Plan tasks | Plan hours | Plan weeks | Actual hrs | Defects | Consolidated on | What the team does with it
| Plan tasks | How many tasks you own this cycle.
| Plan hours | The hours you committed to in MYTASK.
| Plan weeks | Weeks you planned to work in.
| Actual hrs | Hours you have actually logged. The master checks this against the rows you paste into its LOGT.
| Defects | Defects you have recorded.
| Consolidated on | Stamps the date so the team can see which rows are stale.
Also paste your log rows
The six numbers above tell the team where you stand. They do not carry your actual rows, and the team's summaries and charts are built from rows, not totals. So in the same sitting, copy your new LOGT, LOGD, LOGTEST and LOGAI rows into the bottom of the matching sheets on the master, and put your name in the Member column there. If the Agrees? cell on the master's TEAM sheet goes green afterwards, you are done.
My standing, at a glance
| Measure | Value |  |  |  |  | Reading
Hours logged
Tasks complete
Earned value
Defects found
Tests written
AI entries

## PHASES
Process Phase Standard
The phase codes you may use in LOGT, LOGD and MYTASK.
Code | Phase | Scope | Size basis
MGMT | Management & Miscellaneous | S | -
STRAT | Launch & Strategy | S | -
PLAN | Planning | S | -
REQ | Requirements / SRS | S | Pages
STP | System Test Plan | S | -
REQINSP | Requirements Inspection | S | Pages
HLD | High-Level Design / Architecture (SDD) | S | Pages
ITP | Integration Test Plan | S | -
HLDINSP | HLD Inspection | S | Pages
DLD | Detailed Design (screens, widgets, models) | P | LOC
DLDR | Detailed Design Review | P | LOC
TD | Test Development | P | -
DLDINSP | Detailed Design Inspection | P | LOC
CODE | Code - hand-written Dart/Flutter | P | LOC
AIGEN | Code - AI-assisted generation (Vibe) | P | LOC
CR | Code Review / Pull-Request Review | P | LOC
BUILD | Build & Static Analysis (flutter analyze) | P | LOC
CODEINSP | Code Inspection | P | LOC
UT | Unit Test | P | LOC
WT | Widget Test | P | LOC
IT | Build & Integration Test | S | LOC
CICD | CI/CD Pipeline (GitHub Actions) | S | -
ST | System Test | S | LOC
UAT | Client Acceptance Test | S | LOC
DOC | Documentation & User Manual | S | Pages
PM | Postmortem | S | -
PL | Product Life (post-release) | N | LOC

## DEFECTTYPES
Defect Type Standard
The types you may choose in LOGD.
Type | Name | What it covers
10 | Documentation | Comments, README, API docs, user manual
20 | Syntax | Dart syntax, spelling, punctuation, typos
30 | Build / Package | pubspec, dependency conflict, Gradle, signing, build config
40 | Assignment | Declaration, duplicate names, scope, null-safety misuse
50 | Interface | Procedure calls, REST/API contract, parameters, serialization
60 | Checking | Error messages, input validation, inadequate checks
70 | Data | Structure, content, persistence, local DB / Firestore schema
80 | Function | Logic, pointers, loops, recursion, computation, business rules
90 | System | Configuration, timing, memory, platform (iOS/Android) differences
100 | Environment | Design, compile, test or other support system problems
110 | UI / Layout | Overflow, responsiveness, theming, accessibility, Material 3 misuse
120 | State Management | Provider/Riverpod/GetX misuse, rebuild storms, stale or lost state
130 | Performance | Jank, frame drops, oversized images, unbounded list builds
140 | Security | Hard-coded API key, missing auth check, unsafe storage, leaked PII
150 | AI-Generated | Defect traced to AI-generated code that passed review unverified

## LISTS
Validation Lists
Source lists for the drop-downs in this workbook.
Phase | Phase description | Defect type | Milestone | Size measure | AI tool | Yes/No | Status | Test type | Severity
MGMT | Management & Miscellaneous | 10 - Documentation | M1 | Dart LOC | GitHub Copilot | Yes | Planned | Unit | Critical
STRAT | Launch & Strategy | 20 - Syntax | M2 | Screens | Claude | No | In progress | Widget | Major
PLAN | Planning | 30 - Build / Package | M3 | Widgets | ChatGPT / GPT-4 |  | Complete | Integration | Minor
REQ | Requirements / SRS | 40 - Assignment | M4 | API Endpoints | Google Gemini |  | Carried over | Manual | Cosmetic
STP | System Test Plan | 50 - Interface |  | Test Cases | Cursor |  | Cancelled | Acceptance
REQINSP | Requirements Inspection | 60 - Checking |  | SRS Pages | Other |  |  | Regression
HLD | High-Level Design / Architecture (SDD) | 70 - Data |  | SDD Pages | None |  |  | Performance
ITP | Integration Test Plan | 80 - Function |  | Documents |  |  |  | Security
HLDINSP | HLD Inspection | 90 - System
DLD | Detailed Design (screens, widgets, models) | 100 - Environment
DLDR | Detailed Design Review | 110 - UI / Layout
TD | Test Development | 120 - State Management
DLDINSP | Detailed Design Inspection | 130 - Performance
CODE | Code - hand-written Dart/Flutter | 140 - Security
AIGEN | Code - AI-assisted generation (Vibe) | 150 - AI-Generated
CR | Code Review / Pull-Request Review
BUILD | Build & Static Analysis (flutter analyze)
CODEINSP | Code Inspection
UT | Unit Test
WT | Widget Test
IT | Build & Integration Test
CICD | CI/CD Pipeline (GitHub Actions)
ST | System Test
UAT | Client Acceptance Test
DOC | Documentation & User Manual
PM | Postmortem
PL | Product Life (post-release)