## README
TSPi Team Workbook - TMA3084 Software Engineering Laboratory
Faculty of Computer Science & Information Technology, UNIMAS ¦ Semester 1, Session 2026/2027 ¦ Workbook v3.0 (2026-10-29)
WORKED SAMPLE - all names, matric numbers, emails, phone numbers and the client are fictional. The time, task and defect data is migrated from a real past team's workbooks with identities removed; the test, AI, client, GitHub and evaluation forms are illustrative, written to show what a complete workbook looks like. Do not copy the numbers - copy the habit.
| What this is | A Team Software Process (TSP) team workbook rebuilt for TMA3084. It keeps the TSP measurement discipline - time, defects, size, earned value - and adds the forms this course actually assesses: AI-assisted coding, automated testing, GitHub workflow, client engagement and peer evaluation.
| Lineage | The process model follows the Team Software Process introduced by Watts S. Humphrey. The original TSPi support workbook (2002, Addison-Wesley) is the ancestor of this file; every sheet here has been rewritten for this course. Forms, phases, defect types and all guidance text are original to TMA3084.
| What changed from the 2002 workbook | NEW forms: LOGAI (AI-assisted development), LOGTEST (test cases), LOGCLIENT (client meetings), LOGGIT (GitHub activity), CCR (change requests), PEER, TEAMEVAL, ASSESS, DASHBOARD, FORM-SI. MODERNISED: phase set now covers AI generation, pull-request review, static analysis, widget test and CI/CD; defect types extended with UI/Layout, State Management, Performance, Security and AI-Generated; size measures cover screens, widgets and API endpoints alongside LOC. REMOVED: the single-week WEEK form is now a 13-week tracking table, and the PSP-style prediction intervals are dropped as the team has no historical data base.
| Colour convention | AMBER cells are yours to fill in. GREY cells are calculated - typing over one destroys the rollup. Every drop-down is fed by the LISTS sheet.
| How to run it | 1. Fill SETUP once, then FORM-SI with every member. 2. Agree roles in ROLES and goals in GOALS. 3. Plan each cycle in TASK and SCHEDULE. 4. Record daily in LOGT, LOGD, LOGTEST and LOGAI. 5. Hold the weekly meeting against WEEK and IRTL. 6. SUMP, SUMQ, SUMS and DASHBOARD fill themselves.
| One workbook per team | The team keeps one shared copy in the repository (docs/tspi/). Each member records their own rows in the logs and tags them with their name, so individual contribution is traceable without separate files.
| Honesty clause | These numbers are the evidence behind Peer/Individual and Team Evaluation. Logging work you did not do, or back-filling a term's worth of hours the night before a milestone, is academic dishonesty and the pattern is visible in DASHBOARD.
Milestones
| Milestone | Week / Due | Deliverables
| M1 Proposal & Planning (10%) | Week 5 - due 25 Oct 2026 ¦ Proposal, SRS draft, GitHub repo, Team Charter, client approval, >=2 client meetings
| M2 Requirements & Design (15%) | Week 9 - due 20 Nov 2026 ¦ Revised SRS, SDD, Flutter prototype (4-5 screens), >=10 LOGAI entries, test plan (>=20 cases), >=4 client meetings
| M3 Implementation & Testing (35%) | Week 13 - due 20 Dec 2026 ¦ Final SDD, >=50 tests at >=60% coverage, GitHub Actions green, APK/IPA build, >=6 client meetings
| M4 Release & Oral Commitment (40%) | Week 15 - due 02 Jan 2027 ¦ Final report, user manual, demo video 5-10 min, presentation, client sign-off, v1.0.0 release

## MANUAL
How to Use This Workbook
TMA3084 Software Engineering Laboratory - a step-by-step manual for the team. Read this once, together, at the launch meeting.
1. What this workbook is
| The short version | This is a Team Software Process (TSP) workbook. TSP is a way of running a software project where the team plans its own work, measures what actually happens, and uses those measurements to plan better next time. The workbook is where the measuring happens.
| Why bother | Three questions decide most student projects: are we going to finish on time, is the thing we are building any good, and is everyone actually contributing. Opinions on all three are usually wrong. This workbook answers them with data the team collected itself.
| The four things you record | TIME - how long work actually took, not how long it felt. SIZE - how much you built. DEFECTS - every mistake found, and the phase where it was made. STATUS - which tasks are finished. Everything else on the summary sheets is arithmetic on those four.
| What it is not | It is not a surveillance tool and it is not graded on neatness. Nobody is marked down for a high defect count - a team recording 40 defects is doing better engineering than an identical team recording 3, because the second team is not looking. What does get noticed is a log that is empty, or one filled in all at once the night before a milestone.
2. Before you start - conventions
| Convention | What it means
| Amber cells | You type here. Everything the team knows goes into an amber cell.
| Grey cells | Calculated. Typing over one breaks the rollups that depend on it - if a grey number looks wrong, the log feeding it is wrong, so fix the log.
| Drop-downs | Fed by the LISTS sheet. Member names come from FORM-SI, so fill FORM-SI first or every name drop-down in the workbook will be empty.
| Red / amber / green | Applied automatically. Red is not a punishment, it is a prompt to talk about something at the next meeting.
| Hover for help | Cells with a small red corner marker carry a note explaining what goes in them.
| Reference sheets | PHASES and DEFECTTYPES are the standards you code against - read them in Week 1. PLANGUIDE and QUALGUIDE tell you what to aim for. None of the four should ever be edited.
| Charts | PROJECT and CHARTS draw themselves from the logs. There is no Draw button and nothing to refresh - if a chart is empty, the log behind it is empty.
3. Stage one - the launch (do this in Week 1, and again at the start of every cycle)
# | Step | What to do | Form | Who / when
1 | Fill in SETUP | Course details, team name, project title, client, repository URL and team size. Then check the milestone dates against the course outline and set the thresholds. Every other sheet reads its header from here, so this is the one place you type the team name. | SETUP | Team Leader, Week 1
2 | Enter every member | One row per member in FORM-SI: matric number, full name, UNIMAS email, GitHub handle. The name you type here is the name that appears in every drop-down, so agree on a spelling and do not change it later. | FORM-SI | All members, Week 1
3 | Write the team charter | The lower half of FORM-SI. Six short answers: vision, communication norms, definition of done, conflict resolution, quality standards, expected hours. Write these before you disagree about them, not after. | FORM-SI | Team, Week 1
4 | Assign roles | There are six roles and five of you, so one member holds two this cycle and nobody holds more than two. The double rotates, and nobody keeps the same role for more than two milestones running. The Role Load Check at the bottom of the sheet adds this up for you. A role is real work, not a title. | ROLES | Team Leader, each launch
5 | Set measurable goals | A goal needs a number and an owner or it is a wish. Seven starter goals are listed at the bottom of the sheet; replace them with your own. | GOALS | Team, each launch
6 | Agree the strategy | What each cycle actually delivers, what you build versus reuse, the main technical risk and who owns it. Then record the stack decisions and why - the Design rubric asks you to justify alternatives considered. | STRAT | Dev Manager, each launch
7 | Size what you are building | List the screens, modules and documents in SUMS with a planned size. Estimates will be wrong early on. Record them anyway - a wrong estimate you measured against is worth more than no estimate. | SUMS | Planning Manager
8 | Break the work into tasks | Tasks of roughly 2 to 10 hours, each with one owner, a phase, planned hours and a planned week. A task bigger than 10 hours is hiding something. | TASK | Planning Manager
9 | Spread it across the weeks | Put the hours each week in SCHEDULE. Check the Difference cell at the top: schedule hours must match task hours. If they do not, one of the two plans is fiction. | SCHEDULE | Planning Manager
4. Stage two - daily discipline (the habit that makes everything else work)
# | Step | What to do | Form | Who / when
10 | Log time as you work | Start a LOGT row when you sit down, fill in the stop time when you get up. Subtract interruptions honestly. Reconstructing a week of hours from memory produces numbers that are worse than useless, because they look real. | LOGT | Every member, daily
11 | Tag the task | Put the Task ID from TASK in the Task ID column. That is what makes hours roll up against the plan. Unplanned work with no ID is fine - add the task to TASK afterwards so the plan stays honest. | LOGT | Every member, daily
12 | Log every defect | Anything wrong that you had to fix, including the ones you found yourself within a minute. The hard column is Injected in: the phase where the mistake was MADE, not where you noticed it. Getting that right is the whole point. | LOGD | Every member, daily
13 | Log every test | One row per test case with its type and status. Automated tests get a row too - LOGTEST is the evidence behind the Testing and Release rubric, not a duplicate of your test files. | LOGTEST | Quality & Test Manager, daily
14 | Log every AI-assisted change | Any time Copilot, Claude or another generator wrote code that reached the repository: what you asked for, how many lines it gave you, how many survived review, who reviewed it, and whether tests were written. The reviewer must not be you - the sheet turns that row red. | LOGAI | Every member, each change
15 | Record client meetings | Date, mode, who attended, what was decided, what actions came out and who owns them. Keep the minutes or a photo as evidence. The milestones require 2, 4 and 6 cumulative meetings - this is how you prove it. | LOGCLIENT | Product Owner
5. Stage three - the weekly meeting (about 30 minutes, same time every week)
# | Step | What to do | Form | Who / when
16 | Pull the GitHub numbers | Commits, pull requests, reviews and issues closed per member, read from the repository Insights tab. These are facts - do not estimate them. | LOGGIT | Support Manager, weekly
17 | Update task status | Mark finished tasks Complete. Earned value is only credited for completed tasks; a task that is 90% done earns nothing. That is deliberate - it is what stops a plan from slipping quietly. | TASK | Planning Manager, weekly
18 | Read the week's numbers | WEEK fills itself from SCHEDULE. Look at EV variance: negative means the team has delivered less than it planned by this week, however many hours it has burned. Hours are effort; earned value is progress. | WEEK | Team Leader, weekly
19 | Raise risks and issues | A risk might happen, an issue already has. Both need a likelihood, an impact, an owner and a follow-up date. Priority is calculated; anything scoring 6 or more goes red and gets discussed. | IRTL | Team Leader, weekly
20 | Handle change requests | Once the client has agreed a baseline, changes go through CCR with an estimate and a decision - not through a quiet commit. This is also how scope creep becomes visible instead of mysterious. | CCR | Support Manager, as needed
21 | Check the dashboard | Milestone readiness, effort, quality and contribution on one screen. Anything red is the agenda for the next ten minutes. | DASHBOARD | Team, weekly
22 | Talk about contribution | The contribution panel compares each member's hours, commits, reviews and AI entries against an even share. A flag is a prompt for a conversation, not an accusation - someone may be carrying work the logs do not capture, and if so, that is worth knowing too. | DASHBOARD | Team, weekly
23 | Write next week's commitment | One line in WEEK saying what the team will have finished by the next meeting. Then check it at that meeting. This single habit does more for delivery than any tool. | WEEK | Team Leader, weekly
6. Stage four - closing a milestone (the postmortem)
# | Step | What to do | Form | Who / when
24 | Record actual sizes | Go back to SUMS and fill the actual columns, plus actual SRS and SDD pages. Without actual size there is no defect density and no productivity figure. | SUMS | Planning Manager
25 | Check the plan summary | SUMP now shows where the time went, where defects were injected and where they were removed. Compare the Actual % column against your plan. The gap between them is the lesson. | SUMP | Planning Manager
26 | Read the quality summary | SUMQ is where the uncomfortable truths live: review rates that were too fast, A/FR below 2.0, process yield under 70%. Each one predicts a specific kind of pain in the next cycle. | SUMQ | Quality & Test Manager
27 | Enter the coverage figure | One manual cell on SUMQ, read from the coverage job in GitHub Actions. Do not estimate it. | SUMQ | Quality & Test Manager
28 | Run the peer evaluation | Each member rates every member including themselves, 1 to 5, across the 10 rubric categories. Self-ratings are reported separately so they cannot inflate anyone's score. Rate what people did, not whether you like them. | PEER | All members, each milestone
29 | Run the team evaluation | Ten statements about how the team works, rated 1 to 5. Then look at the spread, not just the mean - where members disagree sharply is the thing worth discussing. Agree actions at the bottom of the sheet. | TEAMEVAL | All members, each milestone
30 | Update the assessment tracker | ASSESS maps every rubric to the forms that produce its evidence. Peer and Team Evaluation fill themselves; the rest are entered by the instructor. | ASSESS | Team Leader
31 | Look at the charts together | Open CHARTS and read them as a team. The four that matter most are Cumulative Earned Value (did we deliver what we planned), Defects Removed by Phase (are we catching them early), Review Rates (did we read fast enough to miss things) and Process Yield (what reached test). A number on a sheet is arguable; a line going the wrong way for six weeks is not. | CHARTS | Team, each milestone
32 | Agree three changes | Not twenty. Pick three things the team will do differently next cycle, write them into GOALS with an owner, and check them at the next postmortem. A postmortem that changes nothing was just a meeting. | GOALS | Team, each milestone
7. Every form, and what it is for
| Form | What it holds | Who owns it | Feeds into
| SETUP | Course, team, client, repository, milestone plan and the thresholds that drive the dashboard traffic lights. | Team Leader | Every sheet header, DASHBOARD
| FORM-SI | Member details, the team charter, and each member's planned versus actual hours with a contribution flag. | All members | Every name drop-down, DASHBOARD
| ROLES | Which of the six TSP roles each member holds in each milestone, what that role owns, and a check that nobody is carrying more than two. | Team Leader | -
| GOALS | Measurable team goals with a target, an owner and a review date. | Team | -
| STRAT | What each cycle delivers, build-versus-reuse decisions, technical risks, and the technology stack with justification. | Dev Manager | Design rubric evidence
| TASK | Every task with owner, phase, estimate, planned week, status and earned value. Actual hours arrive automatically from LOGT. | Planning Manager | SCHEDULE, WEEK, FORM-SI, DASHBOARD
| SCHEDULE | Planned hours per week from Week 3 to Week 15, against actual hours and earned value. | Planning Manager | WEEK, DASHBOARD
| LOGT | One row per working session: date, member, phase, task, start, stop and interruptions. The single most important sheet in the workbook. | Every member | TASK, SCHEDULE, SUMP, SUMQ, FORM-SI, DASHBOARD
| LOGD | Every defect found: type, component, the phase it was injected in, the phase it was removed in, fix time, severity, and whether it came from AI-generated code. | Every member | SUMP, SUMQ, DASHBOARD
| LOGTEST | Every test case with type, expected and actual result, status, tester and whether it is automated. | Quality & Test Manager | SUMQ, DASHBOARD
| LOGAI | Every AI-assisted change: tool, prompt, lines generated, lines kept, reviewer, verdict and test status. Self-review is flagged red. | Every member | SUMP, DASHBOARD
| LOGCLIENT | Client meetings with mode, attendees, decisions, actions and sign-off evidence. | Product Owner | DASHBOARD milestone readiness
| LOGGIT | Weekly commits, pull requests, reviews and issues per member, read from GitHub Insights. | Support Manager | DASHBOARD contribution panel
| WEEK | The weekly status record: hours, earned value, variance, risk and next week's commitment. | Team Leader | -
| IRTL | Risks and issues with likelihood, impact, calculated priority, owner and follow-up date. | Team Leader | DASHBOARD
| CCR | Change requests against an agreed baseline, with estimated impact and a recorded decision. | Support Manager | -
| SUMS | Planned and actual size of every component and document - LOC, screens, widgets, pages. | Planning Manager | SUMP, SUMQ
| SUMP | Size, time in each phase, and defects injected and removed by phase. Plan columns are typed; actual columns read themselves out of the logs. | Planning Manager | SUMQ, DASHBOARD
| SUMQ | Defect density, defect ratios, development time ratios, review rates, A/FR, phase yield, process yield and test quality - each against a guideline with a verdict. | Quality & Test Manager | DASHBOARD
| PEER | Peer and individual evaluation: every member rates every member on 10 categories out of 50, with self-ratings reported separately. | All members | ASSESS, DASHBOARD
| TEAMEVAL | Team dynamics across 10 variables rated 1 to 5, with the spread highlighted and agreed actions recorded. | All members | ASSESS
| ASSESS | The official assessment weighting mapped to the rubrics and to the forms that supply the evidence. | Team Leader | -
| DASHBOARD | Milestone readiness, effort and schedule, quality, and the contribution check - all read from the logs. | Automatic | -
| PROJECT | The one-page project summary: headline numbers, the earned-value and effort charts, and a plain sentence saying whether the team is on track. | Automatic | -
| CHARTS | Fourteen charts drawn from your logs - earned value, hours, defects by phase, review rates, yields, the quality profile and contribution. | Automatic | -
| IRWEEK | How the risk picture moved each week: raised, closed, still open, and how many are high priority. | Team Leader | -
| RISK | The top open risks and issues from IRTL, ranked by priority. Completed items drop off by themselves. | Automatic | -
| PHASES | The process phase standard: every phase code, what belongs in it, and whether it counts towards development defects. | Reference | LOGT, LOGD, TASK
| DEFECTTYPES | The defect type standard, each with a Flutter example. Types 110 to 150 were added for this course. | Reference | LOGD
| PLANGUIDE | Planning guidelines: how to split effort across phases and what rates to plan against before you have your own data. | Reference | TASK, SCHEDULE
| QUALGUIDE | Quality guidelines: what to aim for on each SUMQ measure, what it means when you are below it, and the order to fix things in. | Reference | SUMQ
| QPROFPARAM | The five targets behind the Quality Profile chart. | Quality & Test Mgr | CHARTS
| CHARTDATA | The calculated series every chart reads from. Look here only to find out why a chart is empty. | - | PROJECT, CHARTS
| LISTS | The source lists behind every drop-down. Leave it alone unless you are adding a role or a size measure. | - | -
8. Worked examples
| Situation | What you record
| You spend the morning writing the SRS, with a 15-minute phone call in the middle | LOGT: date 20-Oct-26, member your name, milestone M1, phase REQ, task ID T01, start 09:00, stop 12:00, interrupt 15. Delta calculates as 165 minutes. Week fills in by itself.
| During the code review of a login screen, you find a null check that was never written | LOGD: type 60 - Checking, component auth_module, injected in CODE (the mistake was made while coding), removed in CR (you found it in review), fix time 8 minutes, severity Major, from AI code No.
| Copilot generates a form validator; you keep about three quarters of it after review | LOGAI: tool GitHub Copilot, lines generated 60, lines kept 45, reviewer a teammate's name - not yours - verdict Approved with changes, tests written Yes, commit reference PR#7, approved Yes.
| A test that passed last week now fails after a refactor | LOGTEST: update that test's row to Fail with today's date. Then raise the defect in LOGD with injected phase CODE and removed phase UT, and link the two with the defect reference.
| The client asks for an extra screen three weeks before release | CCR: change type Requirement, what changes and why, estimated hours, affected milestone, reviewer and decision. If approved, add the tasks to TASK so the plan reflects reality.
9. Things that go wrong
| Symptom | Cause and fix
| The name drop-downs are empty | FORM-SI has no names in it yet. Every member drop-down in the workbook reads column C of FORM-SI rows 9 to 14. Fill those first.
| A summary number has not changed after I logged work | Press F9, or close and reopen the file. If it still looks wrong, check the phase or task ID you typed in the log - a typo means the row matches nothing and is silently excluded.
| Hours are logged but TASK shows zero actual hours | The Task ID column in LOGT is blank or does not match an ID in TASK. The match is exact, so T1 and T01 are different tasks.
| Defect density and review rates are blank | SUMS has no actual size recorded, so there is nothing to divide by. Fill the actual columns in SUMS at the end of each milestone.
| Someone's peer score looks far too low | Check that every member filled in their own rating block. An empty block is ignored rather than counted as zero, but a block filled in for only some members will skew the average.
| A grey cell shows a wrong number and I want to correct it | Do not type over it. Find the log row that is wrong and fix that. Overwriting a calculated cell breaks the formula permanently and every number downstream of it.
| We forgot to log for two weeks | Reconstruct what you honestly can, mark those rows in the comments column, and say so at the weekly meeting. Inventing plausible numbers is worse than admitting a gap - the gap is recoverable, fabricated data quietly corrupts every conclusion the team draws for the rest of the project.
10. One last thing
The workbook cannot make the team work well. What it can do is make it obvious, early and to everyone, when the team is not - while there is still time to do something about it. A team that logs honestly and looks at the numbers every week will finish; a team that fills this in the weekend before submission will have a very tidy record of a project that went wrong.

## INDEX
Index of Forms
Click a form name to jump to it.
Start here
| Form | What it is for | Owner | When
| MANUAL | Step-by-step manual: what to do, when, and on which form | Read at launch | Week 1
| PROJECT | Project summary: headline numbers and the two charts that matter most | Automatic | Always
Launch - do these once, at the start of each cycle
| Form | What it is for | Owner | When
| SETUP | Course, team, client, repository and the milestone plan | Team Leader | Week 1
| FORM-SI | Member details, contribution rollup and the team charter | All members | Week 1
| ROLES | Who holds which of the six TSP roles in each milestone | Team Leader | Each launch
| GOALS | Measurable team goals with owners and review dates | Team | Each launch
| STRAT | What each cycle delivers, and the stack decisions behind it | Dev Manager | Each launch
Plan - the commitment the team makes
| Form | What it is for | Owner | When
| TASK | Task plan, estimates, ownership and earned value | Planning Manager | Each launch
| SCHEDULE | Hours per week, planned against earned value | Planning Manager | Each launch
Record - fill these as the work happens, not afterwards
| Form | What it is for | Owner | When
| LOGT | Time recording log - one row per working session | All members | Daily
| LOGD | Defect recording log - every defect, wherever found | All members | Daily
| LOGTEST | Test case log with status, type and coverage evidence | Quality & Test Mgr | Daily
| LOGAI | AI-assisted development log with reviewer and verdict | All members | Every AI change
| LOGCLIENT | Client meetings, decisions, actions and sign-off | Product Owner | Each meeting
| LOGGIT | Weekly GitHub activity read from repository Insights | Support Manager | Weekly
Track - the weekly rhythm
| Form | What it is for | Owner | When
| WEEK | Weekly status: hours, earned value, risk and commitment | Team Leader | Weekly
| IRTL | Issue and risk tracking with likelihood, impact and owner | Team Leader | Weekly
| IRWEEK | How the risk picture moved week by week - raised, closed, still open | Team Leader | Weekly
| RISK | The top open risks from IRTL, ranked by priority | Automatic | Weekly
| CCR | Change requests against an agreed baseline | Support Manager | As needed
Summarise - these calculate themselves
| Form | What it is for | Owner | When
| SUMS | Size summary for components and documents | Planning Manager | Each milestone
| SUMP | Plan summary: size, time in phase, defects injected and removed | Planning Manager | Each milestone
| SUMQ | Quality summary: density, yield, review rates, test quality | Quality & Test Mgr | Each milestone
| CHARTS | The fourteen TSP charts, drawn from your own logs | Automatic | Always
Evaluate - the assessed forms
| Form | What it is for | Owner | When
| PEER | Peer and individual evaluation, 10 categories out of 50 | All members | Each milestone
| TEAMEVAL | Team dynamics evaluation, 10 variables out of 50 | All members | Each milestone
| ASSESS | Assessment tracker mapped to the published rubrics | Team Leader | Each milestone
| DASHBOARD | Readiness, effort, quality and contribution at a glance | Automatic | Always
Standards and guidance - read these, do not edit them
| Form | What it is for | Owner | When
| PHASES | Process phase standard: every phase code, what belongs in it | - | Read in Week 1
| DEFECTTYPES | Defect type standard with a Flutter example of each | - | Read in Week 1
| PLANGUIDE | Planning guidelines: effort split and the rates to plan against | - | Each launch
| QUALGUIDE | Quality guidelines: what good looks like on each SUMQ measure | - | Each milestone
| QPROFPARAM | The five targets behind the Quality Profile chart | Quality & Test Mgr | Set once
Machinery - calculated, leave alone
| Form | What it is for | Owner | When
| CHARTDATA | The series every chart reads from | - | -
| LISTS | Source lists behind every drop-down in the workbook | - | -

## PROJECT
Project Summary
The one page to open first. Everything here is calculated from the logs.
| Project |  |  | Report date
| Team |  |  | Current week
| Client |  |  | Team size
| Instructor |  |  | Repository
Headline Measures
| Planned hours | Actual hours | Planned value to date | Earned value to date | New & changed LOC | Defects removed | Defects / KLOC | Test cases | Test pass rate
Earned Value and Effort
Where the team stands

## SETUP
Project Setup
Fill this sheet once at team launch. Every other form reads from here.
Team & Project Identification
| Course | TMA3084 Software Engineering Laboratory
| Semester | Semester 1, Session 2026/2027
| Instructor | Ts. Nurfauza Jali
| Lab Demonstrator | Mr. MD. Aminul Islam Rakib
| Lab Group (1 or 2) | 1
| Team Name / Number | AUV
| Project Title | SeaFresh Supplier Mobile App
| Client Organisation | SeaFresh Seafood Trading (sample client)
| Client Contact & Email | Encik Faizal (sample) - faizal@seafresh.example
| GitHub Repository URL | https://github.com/tma3084-sample/auv-seafresh
| Project Board URL | https://github.com/orgs/tma3084-sample/projects/1
| Team Size | 5
Milestone Plan
ID | Milestone | Week | Start | Due | Weight | Status | Key Deliverables
M1 | Proposal & Planning | 5 | 2026-10-19 | 2026-10-25 | 10% | Complete | Proposal, SRS draft, GitHub repo, Team Charter, client approval, >=2 client meetings
M2 | Requirements & Design | 9 | 2026-11-16 | 2026-11-20 | 15% | Complete | Revised SRS, SDD, Flutter prototype (4-5 screens), >=10 LOGAI entries, test plan (>=20 cases), >=4 client meetings
M3 | Implementation & Testing | 13 | 2026-12-14 | 2026-12-20 | 35% | Complete | Final SDD, >=50 tests at >=60% coverage, GitHub Actions green, APK/IPA build, >=6 client meetings
M4 | Release & Oral Commitment | 15 | 2026-12-28 | 2027-01-02 | 40% | In progress | Final report, user manual, demo video 5-10 min, presentation, client sign-off, v1.0.0 release
Course Thresholds (used by DASHBOARD to flag a team that is behind)
Threshold | M1 | M2 | M3 | M4 |  |  | Notes
Minimum commits (cumulative) | 15 | 30 | 50 | 70 |  |  | Git history, all branches merged to develop
Minimum pull requests merged | 3 | 8 | 15 | 20 |  |  | Every PR needs at least one reviewer approval
Minimum client meetings (cumulative) | 2 | 4 | 6 | 7 |  |  | Logged in LOGCLIENT with client sign-off
Minimum LOGAI entries (cumulative) | 2 | 10 | 15 | 18 |  |  | Every AI-assisted change reviewed and logged
Minimum test cases (cumulative) | 0 | 20 | 50 | 60 |  |  | LOGTEST; unit + widget + integration
Minimum code coverage | 0% | 30% | 60% | 60% |  |  | Critical business logic; from coverage report
Minimum hours per member (cumulative) | 15 | 40 | 80 | 100 |  |  | LOGT; flags under-contribution

## FORM-SI
Form SI - Student & Team Information
One row per member. Names entered here feed every drop-down in the workbook.
| Team |  |  | Project
| Repository |  |  | Client
Team Members
# | Matric No. | Full Name | UNIMAS Email | Phone | GitHub Handle | Primary Role | Secondary Role | Plan Hrs | Actual Hrs | Share of Team Hrs | Flag
1 | 90001 | Aisyah Binti Rahman | 90001@siswa.unimas.my | 011-2000 0001 | aisyah-r | Team Leader | Support Manager
2 | 90002 | Daniel Wong Jun Hao | 90002@siswa.unimas.my | 011-2000 0002 | danielwjh | Development Manager
3 | 90003 | Mei Ling Chong | 90003@siswa.unimas.my | 011-2000 0003 | meiling-c | Planning Manager
4 | 90004 | Harith Bin Ismail | 90004@siswa.unimas.my | 011-2000 0004 | harith-i | Product Owner
5 | 90005 | Priya Nair | 90005@siswa.unimas.my | 011-2000 0005 | priyanair | Quality & Test Manager
6
TEAM TOTAL
Team Charter (agree in Week 1, revisit at every launch)
| Team vision | Give SeaFresh's counter staff a phone app that replaces the paper order book, so an order reaches the kitchen without being re-typed.
| Communication norms | WhatsApp group for day-to-day, GitHub Issues for anything that needs a record. Replies within 12 hours on weekdays. Stand-up every Wednesday 4pm in the lab; client meeting every second Saturday.
| Definition of done | Merged to develop, reviewed and approved by someone other than the author, tests written and passing, CI green, and the LOGAI row filled in if a generator touched it.
| Conflict resolution | Raise it in the Wednesday meeting first. If the team cannot settle it, the Team Leader decides and records the reason in IRTL. Nobody re-opens a settled decision without new information.
| Quality standards | 60% coverage on business logic, zero analyzer warnings on develop, code review within 24 hours, and no AI-generated code merged without a second pair of eyes.
| Commitment | About 10 hours per person per week. Tell the team in advance if you will be away; an unexplained silent week gets raised at the next meeting.
Note on H8: Only the member who doubles up this cycle has a secondary role - leave it blank for everyone else. ROLES is where the full rotation lives.
Note on L8: LOW = this member has logged well under an even share of team hours. HIGH = carrying a disproportionate load. Both are conversations to have at the weekly meeting, not automatic verdicts.
Note on B18: What this product is for, in one sentence the client would recognise.
Note on B19: Channel, response time, meeting cadence, language.
Note on B20: Code reviewed, tests written and passing, CI green, documented.
Note on B21: How disagreements are escalated and settled.
Note on B22: Coverage floor, lint rules, review turnaround, AI-code review rule.
Note on B23: Expected hours per member per week and how absence is handled.

## ROLES
Role Assignment Matrix
Six roles, five of you. One member doubles up each cycle and the double rotates, so everyone leads something.
Team
Roles by Milestone
Role | What this role owns in TMA3084 | M1 | M2 | M3 | M4
Team Leader | Runs the launch and the weekly meeting, keeps the team to its plan, owns the relationship with the instructor and demonstrator, reports status. | Aisyah Binti Rahman | Aisyah Binti Rahman | Daniel Wong Jun Hao | Mei Ling Chong
Product Owner | Owns the client relationship and the backlog. Books and chairs client meetings, turns client needs into prioritised user stories, obtains sign-off. | Harith Bin Ismail | Harith Bin Ismail | Priya Nair | Aisyah Binti Rahman
Development Manager | Owns the Flutter codebase and the architecture. Allocates implementation work, enforces the branching model and the pull-request review rule. | Daniel Wong Jun Hao | Daniel Wong Jun Hao | Harith Bin Ismail | Priya Nair
Planning Manager | Owns TASK and SCHEDULE. Produces the plan, tracks earned value weekly, raises the alarm when the team drifts off plan. | Mei Ling Chong | Mei Ling Chong | Aisyah Binti Rahman | Harith Bin Ismail
Quality & Test Manager | Owns SUMQ, LOGD and LOGTEST - the review, inspection and test discipline. Tracks defect density, yield and coverage, chairs inspections, owns the AI-code review rule, and reports release readiness. | Priya Nair | Priya Nair | Mei Ling Chong | Daniel Wong Jun Hao
Support Manager | Owns the repository, CI/CD, environments, builds and configuration control. Maintains LOGGIT and the CCR log. | Aisyah Binti Rahman | Mei Ling Chong | Daniel Wong Jun Hao | Priya Nair
Role Load Check - calculated from the matrix above, do not type here
Member | Reading | M1 | M2 | M3 | M4
Members holding two roles
Roles filled
Role Rotation Rule
There are six roles and five of you, so in every cycle exactly one member holds two roles and nobody holds more than two. The double role rotates - the same member does not carry it twice in a row - and every member holds a role in every cycle. No member may hold the same role for more than two consecutive milestones. Agree the rotation at the launch meeting and record it above; a change mid-cycle goes through the CCR log with the reason stated. If your team has four members, two of you will double up; the check above works that out from the team size.
Note on C7: Six roles, and nobody may hold more than two of them in one cycle. With five members that means exactly one member doubles up; with four it means two do. The check below works this out from the team size on SETUP.

## GOALS
Team & Role Goals
A goal that cannot be measured is a wish. Every goal needs a number and an owner.
Team
Goals
# | Stakeholder | Goal | Measure | Target | Actual | Owner | Review By
1 | Client | SeaFresh accepts the app and uses it for real orders | Client sign-off form signed | Yes by M4 | Yes | Harith Bin Ismail | 2027-01-02
2 | Client | Counter staff can place an order without training | Time to first successful order, new user | < 3 minutes | 2 min 40 s | Harith Bin Ismail | 2026-12-18
3 | Team | Finish inside the planned effort | Actual hours / planned hours | 0.9 - 1.1 | 0.75 | Mei Ling Chong | 2026-12-18
4 | Team | Work is shared evenly across the five of us | Each member's share of logged hours | within +/-40% of even | not met - see DASHBOARD | Aisyah Binti Rahman | 2026-11-18
5 | Quality | Catch defects before they reach test | % of defects removed before unit test | >= 70% | 73% | Priya Nair | 2026-12-18
6 | Quality | Nothing critical reaches the client | Critical defects found in acceptance test | 0 | 0 | Priya Nair | 2027-01-02
7 | Process | Every AI-generated change is reviewed by someone else | LOGAI rows approved / total rows | 100% | 100% | Priya Nair | 2026-12-18
8 | Process | develop stays releasable | GitHub Actions pass rate on develop | >= 95% | 96% | Aisyah Binti Rahman | 2026-12-18
9
10
11
12
13
14
Suggested starting goals (replace with your own)
| Stakeholder | Goal | Measure | Target
| Client | Client accepts the delivered app | Client sign-off obtained | Yes by M4
| Team | Finish within the planned effort | Actual hours / planned hours | 0.9 - 1.1
| Quality | Catch defects before test | % defects removed before unit test | >= 70%
| Quality | Keep the released build clean | Defects found in acceptance test | 0 critical
| Process | Every AI-generated change is reviewed | LOGAI entries approved / total | 100%
| Process | Keep the main branch releasable | GitHub Actions pass rate on develop | >= 95%
| Individual | Contribution is evenly shared | Each member's share of team hours | within +/-40% of even

## STRAT
Development Strategy
What gets built in each cycle, what is reused, and what could go wrong.
Cycle Strategy
# | Milestone | Scope delivered this cycle | Build / buy / reuse decision | Main technical risk | Mitigation | Owner
1 | M1 | Requirements and a clickable prototype of the order screen. No real data yet. | Build the app; reuse Firebase Auth rather than writing sign-in. | The client has never used a tracking app and may not recognise what we design. | Show paper mock-ups at the second client meeting before writing any code. | Harith Bin Ismail
2 | M2 | Order entry, catalogue browsing and the local database. Prototype against seeded data. | Build order entry; reuse an off-the-shelf PDF package for invoices. | Supplier price list changes weekly and we had assumed it was static. | Model prices as dated records from the start; agreed with client at meeting 3. | Daniel Wong Jun Hao
3 | M3 | Live catalogue sync, invoice generation, full test suite and CI. | Build sync; reuse Firestore offline persistence rather than our own cache. | The shop's connection drops; orders could be lost mid-entry. | Offline-first write queue plus an integration test that simulates loss of connection. | Harith Bin Ismail
4 | M4 | Release build, user manual, demo video and handover to the client. | No new build; packaging and documentation only. | Counter staff may not adopt it after handover. | Train two staff in person at handover and leave a one-page card at the till. | Aisyah Binti Rahman
Technology Stack Decisions
# | Area | Decision | Why | Alternative considered | Decided | Owner
1 | Mobile framework | Flutter 3.x / Dart 3 | One codebase for Android and iOS; the course requires it. | Native Kotlin - rejected, no iOS and no time for two codebases. | 2026-10-08 | Daniel Wong Jun Hao
2 | State management | Riverpod | Compile-safe, testable, and easier to reason about than InheritedWidget. | Provider - simpler but we wanted the compile-time safety. | 2026-10-08 | Daniel Wong Jun Hao
3 | Backend / data | Firebase Firestore + offline persistence | The shop's connection is unreliable; offline-first is the whole point. | Supabase - good, but we already had Firebase Auth. | 2026-10-15 | Harith Bin Ismail
4 | AI capability & API | Gemini API for the order-note parser | Lets staff type 'two boxes tiger prawn' instead of browsing the catalogue. | Rule-based parser - brittle against the way staff actually write. | 2026-10-22 | Priya Nair
5 | Authentication | Firebase Auth (email + phone) | Staff share a counter device; phone sign-in is the simplest for them. | Custom JWT - more work, no benefit here. | 2026-10-15 | Aisyah Binti Rahman
6 | Testing framework | flutter_test + mockito + integration_test | Standard toolchain, works in CI without extra setup. | None seriously considered. | 2026-10-29 | Mei Ling Chong
7 | CI/CD | GitHub Actions | Free for the repo, runs analyze + test + coverage on every PR. | Codemagic - nicer mobile builds, but needed a paid tier for our frequency. | 2026-10-29 | Aisyah Binti Rahman
8 | Release channel | Internal APK via GitHub Releases | The client has two Android devices; no store listing needed for the pilot. | Play Store internal testing - rejected, review delay would hit M4. | 2026-12-10 | Aisyah Binti Rahman

## TASK
Form TASK - Task Plan & Earned Value
Break the cycle into tasks of roughly 2-10 hours. A task is done or it is not - no part marks.
Team |  |  |  | Tasks |  | Plan hrs |  | Actual hrs |  |  | Complete |  |  | Earned value
Task ID | M/stone | Phase | Component | Task | Owner | Est. size | Size measure | Rate /hr | Est. hrs | Plan hrs | Plan wk | Actual hrs | Act. wk | Status | Plan value | Earned value | Cum PV | Cum EV
T01 | M1 | MGMT | SYSTEM | Team admin, lab attendance, instructor check-ins | Aisyah Binti Rahman |  |  |  |  | 7 | 3 |  |  | Complete
T02 | M1 | STRAT | SYSTEM | Launch meeting, cycle strategy and stack decisions | Aisyah Binti Rahman |  |  |  |  | 11 | 3 |  |  | Complete
T03 | M1 | PLAN | SYSTEM | Task and schedule plan for the cycle | Mei Ling Chong |  |  |  |  | 10.5 | 3 |  |  | Complete
T04 | M1 | REQ | SYSTEM | Elicit requirements from SeaFresh and write the SRS | Harith Bin Ismail |  |  |  |  | 7 | 4 |  |  | Complete
T05 | M1 | STP | SYSTEM | System test plan | Mei Ling Chong |  |  |  |  | 6 | 4 |  |  | Complete
T06 | M1 | REQINSP | SYSTEM | Team inspection of the SRS | Harith Bin Ismail |  |  |  |  | 11 | 4 |  |  | Complete
T07 | M1 | HLD | SYSTEM | Architecture and SDD | Daniel Wong Jun Hao |  |  |  |  | 9.5 | 4 |  |  | Complete
T08 | M1 | ITP | SYSTEM | Integration test plan | Mei Ling Chong |  |  |  |  | 6 | 4 |  |  | Complete
T09 | M1 | HLDINSP | SYSTEM | Team inspection of the SDD | Daniel Wong Jun Hao |  |  |  |  | 6 | 4 |  |  | Complete
T10 | M1 | DLD | UI / screens | Detailed design of screens, widgets and models | Priya Nair |  |  |  |  | 10.5 | 5 |  |  | Complete
T11 | M1 | DLDR | UI / screens | Personal review of the detailed design | Priya Nair |  |  |  |  | 12.5 | 5 |  |  | Complete
T12 | M1 | TD | UI / screens | Write the test cases for this component | Priya Nair |  |  |  |  | 17 | 5 |  |  | Complete
T13 | M1 | DLDINSP | UI / screens | Team inspection of the detailed design | Priya Nair |  |  |  |  | 11.5 | 5 |  |  | Complete
T14 | M2 | CODE | UI / screens | Implement in Dart / Flutter | Priya Nair |  |  |  |  | 24 | 6 |  |  | Complete
T15 | M2 | CR | UI / screens | Pull-request review by a teammate | Priya Nair |  |  |  |  | 14 | 6 |  |  | Complete
T16 | M2 | BUILD | UI / screens | flutter analyze and build, fix what it reports | Priya Nair |  |  |  |  | 10 | 6 |  |  | Complete
T17 | M2 | CODEINSP | UI / screens | Team code inspection | Priya Nair |  |  |  |  | 12 | 6 |  |  | Complete
T18 | M2 | UT | UI / screens | Unit tests for this component | Priya Nair |  |  |  |  | 15 | 7 |  |  | Complete
T19 | M2 | DLD | Order & catalogue service | Detailed design of screens, widgets and models | Daniel Wong Jun Hao |  |  |  |  | 8 | 7 |  |  | Complete
T20 | M2 | DLDR | Order & catalogue service | Personal review of the detailed design | Daniel Wong Jun Hao |  |  |  |  | 14 | 7 |  |  | Complete
T21 | M2 | TD | Order & catalogue service | Write the test cases for this component | Daniel Wong Jun Hao |  |  |  |  | 10 | 7 |  |  | Complete
T22 | M2 | DLDINSP | Order & catalogue service | Team inspection of the detailed design | Daniel Wong Jun Hao |  |  |  |  | 14 | 7 |  |  | Complete
T23 | M2 | CODE | Order & catalogue service | Implement in Dart / Flutter | Daniel Wong Jun Hao |  |  |  |  | 18 | 7 |  |  | Complete
T24 | M2 | CR | Order & catalogue service | Pull-request review by a teammate | Daniel Wong Jun Hao |  |  |  |  | 15 | 9 |  |  | Complete
T25 | M2 | BUILD | Order & catalogue service | flutter analyze and build, fix what it reports | Daniel Wong Jun Hao |  |  |  |  | 12 | 9 |  |  | Complete
T26 | M2 | CODEINSP | Order & catalogue service | Team code inspection | Daniel Wong Jun Hao |  |  |  |  | 14 | 9 |  |  | Complete
T27 | M2 | UT | Order & catalogue service | Unit tests for this component | Daniel Wong Jun Hao |  |  |  |  | 9 | 9 |  |  | Complete
T28 | M2 | DLD | Local store & sync | Detailed design of screens, widgets and models | Mei Ling Chong |  |  |  |  | 9 | 9 |  |  | Complete
T29 | M2 | DLDR | Local store & sync | Personal review of the detailed design | Mei Ling Chong |  |  |  |  | 14 | 9 |  |  | Complete
T30 | M3 | TD | Local store & sync | Write the test cases for this component | Mei Ling Chong |  |  |  |  | 10 | 10 |  |  | Complete
T31 | M3 | DLDINSP | Local store & sync | Team inspection of the detailed design | Mei Ling Chong |  |  |  |  | 0 | 10 |  |  | Complete
T32 | M3 | CODE | Local store & sync | Implement in Dart / Flutter | Mei Ling Chong |  |  |  |  | 24 | 10 |  |  | Complete
T33 | M3 | CR | Local store & sync | Pull-request review by a teammate | Mei Ling Chong |  |  |  |  | 8 | 10 |  |  | Complete
T34 | M3 | BUILD | Local store & sync | flutter analyze and build, fix what it reports | Mei Ling Chong |  |  |  |  | 12.5 | 10 |  |  | Complete
T35 | M3 | CODEINSP | Local store & sync | Team code inspection | Mei Ling Chong |  |  |  |  | 10 | 11 |  |  | Complete
T36 | M3 | UT | Local store & sync | Unit tests for this component | Mei Ling Chong |  |  |  |  | 11 | 11 |  |  | Complete
T37 | M3 | IT | SYSTEM | Build and integration test across components | Daniel Wong Jun Hao |  |  |  |  | 17 | 11 |  |  | Complete
T38 | M3 | ST | SYSTEM | System test against the SRS | Mei Ling Chong |  |  |  |  | 20 | 12 |  |  | In progress
T39 | M3 | DOC | SYSTEM | User manual and final report | Harith Bin Ismail |  |  |  |  | 16 | 12 |  |  | Complete
T40 | M3 | PM | SYSTEM | Postmortem: review the data and agree three changes | Aisyah Binti Rahman |  |  |  |  | 12 | 12 |  |  | Complete
T41 | M2 | AIGEN | UI / screens | Generate form validation and list builders with Copilot | Priya Nair |  |  |  |  | 12 | 7 |  |  | Complete
T42 | M2 | AIGEN | Order & catalogue service | Generate the Gemini order-note parser wrapper | Daniel Wong Jun Hao |  |  |  |  | 10 | 9 |  |  | Complete
T43 | M3 | WT | UI / screens | Widget tests for order entry and catalogue screens | Mei Ling Chong |  |  |  |  | 14 | 10 |  |  | Complete
T44 | M2 | CICD | SYSTEM | GitHub Actions: analyze, test, coverage on every PR | Aisyah Binti Rahman |  |  |  |  | 10 | 9 |  |  | Complete
T45 | M3 | UAT | SYSTEM | Acceptance test with counter staff at the shop | Harith Bin Ismail |  |  |  |  | 8 | 12 |  |  | Complete
T46 | M3 | AIGEN | Local store & sync | Generate the offline write-queue scaffolding | Mei Ling Chong |  |  |  |  | 8 | 10 |  |  | Complete
Note on J7: Estimated hours from size and rate. If you have no rate data yet, leave size and rate blank and put your judgement straight into Plan hrs.
Note on Q7: Earned value is only credited when the task is marked Complete. Half-finished work earns nothing - that is what stops a plan from quietly slipping.

## SCHEDULE
Form SCHEDULE - Weekly Schedule & Earned Value
Planned hours are what the team commits to. Earned value is what it actually delivered.
Team |  |  |  | Task plan hrs |  | Schedule plan hrs |  | Difference
Week | Week starting | Plan hrs | Cum plan | Actual hrs | Cum actual | Plan value | Cum PV | Earned value | Cum EV | EV vs PV | Comment
3 | 2026-10-05 | 28.5 | [8 empty] | Launch week - plan built here
4 | 2026-10-12 | 45.5
5 | 2026-10-19 | 51.5 | [8 empty] | M1 submitted
6 | 2026-10-26 | 60
7 | 2026-11-02 | 91
8 | 2026-11-09 | 0 | [8 empty] | Mid-semester break, no work planned
9 | 2026-11-16 | 93 | [8 empty] | M2 submitted
10 | 2026-11-23 | 76.5
11 | 2026-11-30 | 38
12 | 2026-12-07 | 56 | [8 empty] | System test and acceptance
13 | 2026-12-14 | 0 | [8 empty] | M3 submitted
14 | 2026-12-21 | 0
15 | 2026-12-28 | 0 | [8 empty] | M4 - presentation and handover
TOTAL
Note on K7: Negative means the team has earned less value than it planned to by this week - it is behind, regardless of how many hours it has burned.

## LOGT
Form LOGT - Time Recording Log
One row per working session. Delta is calculated; never type over it.
Team |  |  |  | Total hours logged |  |  | Sessions
Date | Member | Milestone | Week | Phase | Task ID | Component / what you worked on | Start | Stop | Interrupt (min) | Delta (min) | AI used? | Comments
2026-10-05 | Aisyah Binti Rahman | M1 |  | MGMT | T01 | SYSTEM - Team admin, lab attendance, instructor check-ins | 10:00 | 11:56 | 0 |  | No
2026-10-06 | Aisyah Binti Rahman | M1 |  | STRAT | T02 | SYSTEM - Launch meeting, cycle strategy and stack decisions | 13:23 | 15:23 | 0 |  | No
2026-10-07 | Aisyah Binti Rahman | M1 |  | PLAN | T03 | SYSTEM - Task and schedule plan for the cycle | 12:15 | 14:22 | 0 |  | No
2026-10-15 | Aisyah Binti Rahman | M1 |  | REQ | T04 | SYSTEM - Elicit requirements from SeaFresh and write the SRS | 8:00 | 8:51 | 0 |  | No
2026-10-16 | Aisyah Binti Rahman | M1 |  | REQINSP | T06 | SYSTEM - Team inspection of the SRS | 11:10 | 12:50 | 0 |  | No
2026-10-17 | Aisyah Binti Rahman | M1 |  | HLD | T07 | SYSTEM - Architecture and SDD | 10:00 | 10:55 | 0 |  | No
2026-10-12 | Aisyah Binti Rahman | M1 |  | HLDINSP | T09 | SYSTEM - Team inspection of the SDD | 9:00 | 9:48 | 0 |  | No
2026-10-20 | Aisyah Binti Rahman | M1 |  | DLDR | T11 | UI / screens - Personal review of the detailed design | 14:10 | 16:10 | 0 |  | No
2026-10-21 | Aisyah Binti Rahman | M1 |  | TD | T12 | UI / screens - Write the test cases for this component | 15:00 | 16:57 | 0 |  | No
2026-10-22 | Aisyah Binti Rahman | M1 |  | DLDINSP | T13 | UI / screens - Team inspection of the detailed design | 9:45 | 10:35 | 0 |  | No
2026-10-30 | Aisyah Binti Rahman | M2 |  | CR | T15 | UI / screens - Pull-request review by a teammate | 14:00 | 15:56 | 0 |  | No
2026-10-31 | Aisyah Binti Rahman | M2 |  | CODEINSP | T17 | UI / screens - Team code inspection | 9:00 | 10:47 | 0 |  | No
2026-12-07 | Aisyah Binti Rahman | M3 |  | DLDR | T20 | Order & catalogue service - Personal review of the detailed design | 9:00 | 11:00 | 0 |  | No
2026-12-08 | Aisyah Binti Rahman | M3 |  | DLDINSP | T22 | Order & catalogue service - Team inspection of the detailed design | 14:00 | 16:00 | 0 |  | No
2026-12-09 | Aisyah Binti Rahman | M3 |  | CR | T24 | Order & catalogue service - Pull-request review by a teammate | 9:30 | 12:15 | 0 |  | No
2026-12-10 | Aisyah Binti Rahman | M3 |  | CODEINSP | T26 | Order & catalogue service - Team code inspection | 15:05 | 16:40 | 0 |  | No
2026-12-11 | Aisyah Binti Rahman | M3 |  | DLDR | T29 | Local store & sync - Personal review of the detailed design | 14:00 | 15:30 | 0 |  | No
2026-12-12 | Aisyah Binti Rahman | M3 |  | DLDINSP | T31 | Local store & sync - Team inspection of the detailed design | 9:00 | 10:30 | 0 |  | No
2026-12-07 | Aisyah Binti Rahman | M3 |  | BUILD | T34 | Local store & sync - flutter analyze and build, fix what it reports | 11:00 | 12:00 | 0 |  | No
2026-12-01 | Aisyah Binti Rahman | M3 |  | UT | T36 | Local store & sync - Unit tests for this component | 15:00 | 16:00 | 0 |  | No
2026-12-02 | Aisyah Binti Rahman | M3 |  | IT | T37 | SYSTEM - Build and integration test across components | 9:00 | 11:00 | 0 |  | No
2026-12-10 | Aisyah Binti Rahman | M3 |  | ST | T38 | SYSTEM - System test against the SRS | 14:00 | 17:00 | 0 |  | No
2026-12-11 | Aisyah Binti Rahman | M3 |  | DOC | T39 | SYSTEM - User manual and final report | 10:00 | 12:00 | 0 |  | No
2026-12-12 | Aisyah Binti Rahman | M3 |  | PM | T40 | SYSTEM - Postmortem: review the data and agree three changes | 8:30 | 11:15 | 0 |  | No
2026-10-05 | Daniel Wong Jun Hao | M1 |  | STRAT | T02 | SYSTEM - Launch meeting, cycle strategy and stack decisions | 10:05 | 11:05 | 0 |  | No
2026-10-06 | Daniel Wong Jun Hao | M1 |  | PLAN | T03 | SYSTEM - Task and schedule plan for the cycle | 9:35 | 11:20 | 15 |  | No | eat breakfast
2026-10-14 | Daniel Wong Jun Hao | M1 |  | REQ | T04 | SYSTEM - Elicit requirements from SeaFresh and write the SRS | 11:40 | 13:40 | 0 |  | No
2026-10-15 | Daniel Wong Jun Hao | M1 |  | STP | T05 | SYSTEM - System test plan | 15:10 | 17:58 | 0 |  | No
2026-10-16 | Daniel Wong Jun Hao | M1 |  | REQINSP | T06 | SYSTEM - Team inspection of the SRS | 14:20 | 15:56 | 0 |  | No
2026-10-17 | Daniel Wong Jun Hao | M1 |  | HLD | T07 | SYSTEM - Architecture and SDD | 15:56 | 17:56 | 0 |  | No
2026-10-12 | Daniel Wong Jun Hao | M1 |  | ITP | T08 | SYSTEM - Integration test plan | 17:05 | 19:30 | 25 |  | No | friend call
2026-10-13 | Daniel Wong Jun Hao | M1 |  | HLDINSP | T09 | SYSTEM - Team inspection of the SDD | 19:30 | 20:30 | 0 |  | No
2026-10-21 | Daniel Wong Jun Hao | M1 |  | DLD | T10 | UI / screens - Detailed design of screens, widgets and models | 18:40 | 21:16 | 0 |  | No
2026-10-22 | Daniel Wong Jun Hao | M1 |  | DLDR | T11 | UI / screens - Personal review of the detailed design | 21:16 | 23:16 | 0 |  | No
2026-10-23 | Daniel Wong Jun Hao | M1 |  | TD | T12 | UI / screens - Write the test cases for this component | 11:30 | 13:00 | 0 |  | No
2026-10-24 | Daniel Wong Jun Hao | M1 |  | DLDINSP | T13 | UI / screens - Team inspection of the detailed design | 15:55 | 16:55 | 0 |  | No
2026-10-26 | Daniel Wong Jun Hao | M2 |  | CODE | T14 | UI / screens - Implement in Dart / Flutter | 19:40 | 21:46 | 0 |  | No
2026-10-27 | Daniel Wong Jun Hao | M2 |  | CR | T15 | UI / screens - Pull-request review by a teammate | 14:40 | 15:40 | 0 |  | No
2026-10-28 | Daniel Wong Jun Hao | M2 |  | BUILD | T16 | UI / screens - flutter analyze and build, fix what it reports | 17:10 | 18:46 | 0 |  | No
2026-10-29 | Daniel Wong Jun Hao | M2 |  | CODEINSP | T17 | UI / screens - Team code inspection | 12:15 | 14:15 | 0 |  | No
2026-10-05 | Mei Ling Chong | M1 |  | MGMT | T01 | SYSTEM - Team admin, lab attendance, instructor check-ins | 15:30 | 17:30 | 0 |  | No
2026-10-06 | Mei Ling Chong | M1 |  | STRAT | T02 | SYSTEM - Launch meeting, cycle strategy and stack decisions | 14:10 | 16:09 | 0 |  | No
2026-10-07 | Mei Ling Chong | M1 |  | PLAN | T03 | SYSTEM - Task and schedule plan for the cycle | 10:00 | 12:13 | 0 |  | No
2026-10-15 | Mei Ling Chong | M1 |  | STP | T05 | SYSTEM - System test plan | 14:15 | 16:00 | 0 |  | No
2026-10-16 | Mei Ling Chong | M1 |  | REQINSP | T06 | SYSTEM - Team inspection of the SRS | 7:30 | 9:53 | 30 |  | No | breakfast
2026-10-17 | Mei Ling Chong | M1 |  | HLD | T07 | SYSTEM - Architecture and SDD | 20:30 | 21:26 | 0 |  | No
2026-10-12 | Mei Ling Chong | M1 |  | ITP | T08 | SYSTEM - Integration test plan | 15:00 | 17:23 | 20 |  | No | solve other matters
2026-10-20 | Mei Ling Chong | M1 |  | DLDR | T11 | UI / screens - Personal review of the detailed design | 16:00 | 17:00 | 0 |  | No
2026-10-21 | Mei Ling Chong | M1 |  | TD | T12 | UI / screens - Write the test cases for this component | 16:00 | 20:00 | 60 |  | No | dinner
2026-10-22 | Mei Ling Chong | M1 |  | DLDINSP | T13 | UI / screens - Team inspection of the detailed design | 14:00 | 15:51 | 0 |  | No
2026-10-30 | Mei Ling Chong | M2 |  | CODE | T14 | UI / screens - Implement in Dart / Flutter | 10:45 | 14:00 | 30 |  | No | lunch
2026-10-31 | Mei Ling Chong | M2 |  | CR | T15 | UI / screens - Pull-request review by a teammate | 19:00 | 22:00 | 0 |  | No
2026-10-26 | Mei Ling Chong | M2 |  | CODEINSP | T17 | UI / screens - Team code inspection | 18:30 | 20:25 | 0 |  | No
2026-11-03 | Mei Ling Chong | M2 |  | UT | T18 | UI / screens - Unit tests for this component | 16:00 | 21:53 | 120 |  | No | rest, dinner
2026-11-04 | Mei Ling Chong | M2 |  | DLDR | T20 | Order & catalogue service - Personal review of the detailed design | 19:20 | 22:55 | 0 |  | No
2026-11-05 | Mei Ling Chong | M2 |  | TD | T21 | Order & catalogue service - Write the test cases for this component | 10:00 | 13:55 | 0 |  | No
2026-11-06 | Mei Ling Chong | M2 |  | DLDINSP | T22 | Order & catalogue service - Team inspection of the detailed design | 15:00 | 17:30 | 0 |  | No
2026-11-21 | Mei Ling Chong | M2 |  | CR | T24 | Order & catalogue service - Pull-request review by a teammate | 11:00 | 14:50 | 60 |  | No | lunch
2026-11-16 | Mei Ling Chong | M2 |  | BUILD | T25 | Order & catalogue service - flutter analyze and build, fix what it rep | 17:00 | 19:45 | 0 |  | No
2026-11-17 | Mei Ling Chong | M2 |  | CODEINSP | T26 | Order & catalogue service - Team code inspection | 20:00 | 23:30 | 0 |  | No
2026-11-18 | Mei Ling Chong | M2 |  | UT | T27 | Order & catalogue service - Unit tests for this component | 10:30 | 14:30 | 0 |  | No
2026-11-19 | Mei Ling Chong | M2 |  | DLD | T28 | Local store & sync - Detailed design of screens, widgets and models | 10:00 | 12:00 | 0 |  | No
2026-11-20 | Mei Ling Chong | M2 |  | DLDR | T29 | Local store & sync - Personal review of the detailed design | 14:30 | 18:00 | 30 |  | No | break
2026-11-28 | Mei Ling Chong | M3 |  | TD | T30 | Local store & sync - Write the test cases for this component | 19:05 | 22:00 | 0 |  | No
2026-11-23 | Mei Ling Chong | M3 |  | DLDINSP | T31 | Local store & sync - Team inspection of the detailed design | 11:00 | 13:05 | 0 |  | No
2026-11-24 | Mei Ling Chong | M3 |  | CODE | T32 | Local store & sync - Implement in Dart / Flutter | 19:00 | 22:00 | 0 |  | No
2026-11-25 | Mei Ling Chong | M3 |  | CR | T33 | Local store & sync - Pull-request review by a teammate | 15:00 | 17:10 | 0 |  | No
2026-11-26 | Mei Ling Chong | M3 |  | BUILD | T34 | Local store & sync - flutter analyze and build, fix what it reports | 21:00 | 22:55 | 0 |  | No
2026-12-04 | Mei Ling Chong | M3 |  | CODEINSP | T35 | Local store & sync - Team code inspection | 16:10 | 18:10 | 0 |  | No
2026-12-05 | Mei Ling Chong | M3 |  | UT | T36 | Local store & sync - Unit tests for this component | 16:00 | 22:00 | 120 |  | No | rest, dinner
2026-11-30 | Mei Ling Chong | M3 |  | IT | T37 | SYSTEM - Build and integration test across components | 18:00 | 20:00 | 0 |  | No
2026-12-08 | Mei Ling Chong | M3 |  | ST | T38 | SYSTEM - System test against the SRS | 15:00 | 22:00 | 120 |  | No | dinner, family meeting
2026-12-09 | Mei Ling Chong | M3 |  | DOC | T39 | SYSTEM - User manual and final report | 10:00 | 15:00 | 60 |  | No | lunch
2026-12-10 | Mei Ling Chong | M3 |  | PM | T40 | SYSTEM - Postmortem: review the data and agree three changes | 14:00 | 16:00 | 0 |  | No
2026-10-05 | Harith Bin Ismail | M1 |  | MGMT | T01 | SYSTEM - Team admin, lab attendance, instructor check-ins | 18:00 | 19:00 | 0 |  | No
2026-10-06 | Harith Bin Ismail | M1 |  | STRAT | T02 | SYSTEM - Launch meeting, cycle strategy and stack decisions | 19:00 | 21:00 | 0 |  | No
2026-10-07 | Harith Bin Ismail | M1 |  | PLAN | T03 | SYSTEM - Task and schedule plan for the cycle | 19:00 | 21:00 | 0 |  | No
2026-10-15 | Harith Bin Ismail | M1 |  | REQ | T04 | SYSTEM - Elicit requirements from SeaFresh and write the SRS | 15:00 | 18:00 | 0 |  | No
2026-10-16 | Harith Bin Ismail | M1 |  | STP | T05 | SYSTEM - System test plan | 19:00 | 20:00 | 0 |  | No
2026-10-17 | Harith Bin Ismail | M1 |  | REQINSP | T06 | SYSTEM - Team inspection of the SRS | 17:00 | 19:30 | 0 |  | No
2026-10-12 | Harith Bin Ismail | M1 |  | HLD | T07 | SYSTEM - Architecture and SDD | 13:00 | 16:30 | 0 |  | No
2026-10-13 | Harith Bin Ismail | M1 |  | ITP | T08 | SYSTEM - Integration test plan | 10:00 | 12:00 | 0 |  | No
2026-10-14 | Harith Bin Ismail | M1 |  | HLDINSP | T09 | SYSTEM - Team inspection of the SDD | 11:00 | 13:00 | 0 |  | No
2026-10-22 | Harith Bin Ismail | M1 |  | DLD | T10 | UI / screens - Detailed design of screens, widgets and models | 14:00 | 21:00 | 0 |  | No
2026-10-23 | Harith Bin Ismail | M1 |  | DLDR | T11 | UI / screens - Personal review of the detailed design | 9:00 | 14:00 | 0 |  | No
2026-10-24 | Harith Bin Ismail | M1 |  | TD | T12 | UI / screens - Write the test cases for this component | 10:00 | 17:00 | 0 |  | No
2026-10-19 | Harith Bin Ismail | M1 |  | DLDINSP | T13 | UI / screens - Team inspection of the detailed design | 11:00 | 16:00 | 0 |  | No
2026-10-27 | Harith Bin Ismail | M2 |  | CODE | T14 | UI / screens - Implement in Dart / Flutter | 14:00 | 0:00 | 80 |  | No | dinner
2026-10-28 | Harith Bin Ismail | M2 |  | CODE | T14 | UI / screens - Implement in Dart / Flutter | 15:30 | 23:30 | 80 |  | No | dinner and rest
2026-10-29 | Harith Bin Ismail | M2 |  | CR | T15 | UI / screens - Pull-request review by a teammate | 17:00 | 22:00 | 0 |  | No
2026-10-30 | Harith Bin Ismail | M2 |  | BUILD | T16 | UI / screens - flutter analyze and build, fix what it reports | 14:30 | 17:00 | 0 |  | No
2026-10-31 | Harith Bin Ismail | M2 |  | CODEINSP | T17 | UI / screens - Team code inspection | 13:00 | 20:00 | 40 |  | No | lunch
2026-10-26 | Harith Bin Ismail | M2 |  | UT | T18 | UI / screens - Unit tests for this component | 11:00 | 16:00 | 0 |  | No
2026-11-03 | Harith Bin Ismail | M2 |  | DLD | T19 | Order & catalogue service - Detailed design of screens, widgets and mo | 17:00 | 21:00 | 0 |  | No
2026-11-04 | Harith Bin Ismail | M2 |  | DLDR | T20 | Order & catalogue service - Personal review of the detailed design | 19:00 | 22:00 | 0 |  | No
2026-11-05 | Harith Bin Ismail | M2 |  | TD | T21 | Order & catalogue service - Write the test cases for this component | 13:00 | 16:00 | 0 |  | No
2026-11-06 | Harith Bin Ismail | M2 |  | DLDINSP | T22 | Order & catalogue service - Team inspection of the detailed design | 10:00 | 15:00 | 0 |  | No
2026-11-07 | Harith Bin Ismail | M2 |  | CODE | T23 | Order & catalogue service - Implement in Dart / Flutter | 10:00 | 14:00 | 0 |  | No
2026-11-16 | Harith Bin Ismail | M2 |  | CR | T24 | Order & catalogue service - Pull-request review by a teammate | 15:00 | 20:00 | 60 |  | No | dinner
2026-11-17 | Harith Bin Ismail | M2 |  | BUILD | T25 | Order & catalogue service - flutter analyze and build, fix what it rep | 10:00 | 16:00 | 60 |  | No | lunch
2026-11-18 | Harith Bin Ismail | M2 |  | CODEINSP | T26 | Order & catalogue service - Team code inspection | 19:00 | 22:00 | 0 |  | No
2026-11-19 | Harith Bin Ismail | M2 |  | UT | T27 | Order & catalogue service - Unit tests for this component | 14:00 | 16:30 | 0 |  | No
2026-11-20 | Harith Bin Ismail | M2 |  | DLD | T28 | Local store & sync - Detailed design of screens, widgets and models | 17:00 | 20:00 | 0 |  | No
2026-11-21 | Harith Bin Ismail | M2 |  | DLDR | T29 | Local store & sync - Personal review of the detailed design | 13:00 | 18:00 | 0 |  | No
2026-11-23 | Harith Bin Ismail | M3 |  | TD | T30 | Local store & sync - Write the test cases for this component | 9:00 | 14:00 | 60 |  | No | lunch
2026-11-24 | Harith Bin Ismail | M3 |  | DLDINSP | T31 | Local store & sync - Team inspection of the detailed design | 10:00 | 13:00 | 0 |  | No
2026-11-25 | Harith Bin Ismail | M3 |  | CODE | T32 | Local store & sync - Implement in Dart / Flutter | 17:00 | 22:00 | 80 |  | No | dinner and rest
2026-11-26 | Harith Bin Ismail | M3 |  | CR | T33 | Local store & sync - Pull-request review by a teammate | 13:00 | 16:00 | 0 |  | No
2026-11-27 | Harith Bin Ismail | M3 |  | BUILD | T34 | Local store & sync - flutter analyze and build, fix what it reports | 10:00 | 12:00 | 0 |  | No
2026-12-12 | Harith Bin Ismail | M3 |  | CODEINSP | T35 | Local store & sync - Team code inspection | 9:00 | 13:00 | 0 |  | No
2026-12-07 | Harith Bin Ismail | M3 |  | UT | T36 | Local store & sync - Unit tests for this component | 10:00 | 13:00 | 0 |  | No
2026-12-08 | Harith Bin Ismail | M3 |  | IT | T37 | SYSTEM - Build and integration test across components | 13:00 | 20:00 | 80 |  | No | rest
2026-12-09 | Harith Bin Ismail | M3 |  | ST | T38 | SYSTEM - System test against the SRS | 10:00 | 16:00 | 50 |  | No | lunch
2026-12-10 | Harith Bin Ismail | M3 |  | DOC | T39 | SYSTEM - User manual and final report | 10:00 | 14:00 | 0 |  | No
2026-12-11 | Harith Bin Ismail | M3 |  | PM | T40 | SYSTEM - Postmortem: review the data and agree three changes | 12:00 | 15:00 | 0 |  | No
2026-10-05 | Priya Nair | M1 |  | MGMT | T01 | SYSTEM - Team admin, lab attendance, instructor check-ins | 10:45 | 12:45 | 0 |  | No
2026-10-06 | Priya Nair | M1 |  | STRAT | T02 | SYSTEM - Launch meeting, cycle strategy and stack decisions | 12:45 | 15:15 | 0 |  | No
2026-10-07 | Priya Nair | M1 |  | PLAN | T03 | SYSTEM - Task and schedule plan for the cycle | 15:45 | 18:15 | 0 |  | No
2026-10-15 | Priya Nair | M1 |  | STP | T05 | SYSTEM - System test plan | 10:00 | 10:12 | 0 |  | No
2026-10-16 | Priya Nair | M1 |  | REQINSP | T06 | SYSTEM - Team inspection of the SRS | 11:00 | 12:00 | 0 |  | No
2026-10-17 | Priya Nair | M1 |  | HLD | T07 | SYSTEM - Architecture and SDD | 13:00 | 14:00 | 0 |  | No
2026-10-12 | Priya Nair | M1 |  | HLDINSP | T09 | SYSTEM - Team inspection of the SDD | 15:45 | 16:45 | 0 |  | No
2026-10-20 | Priya Nair | M1 |  | DLD | T10 | UI / screens - Detailed design of screens, widgets and models | 10:00 | 10:48 | 0 |  | No
2026-10-21 | Priya Nair | M1 |  | DLDR | T11 | UI / screens - Personal review of the detailed design | 11:00 | 12:30 | 0 |  | No
2026-10-22 | Priya Nair | M1 |  | TD | T12 | UI / screens - Write the test cases for this component | 15:00 | 17:30 | 0 |  | No
2026-10-23 | Priya Nair | M1 |  | DLDINSP | T13 | UI / screens - Team inspection of the detailed design | 18:00 | 19:30 | 0 |  | No
2026-10-31 | Priya Nair | M2 |  | CODE | T14 | UI / screens - Implement in Dart / Flutter | 10:00 | 10:48 | 0 |  | No
2026-10-26 | Priya Nair | M2 |  | CR | T15 | UI / screens - Pull-request review by a teammate | 11:00 | 13:00 | 0 |  | No
2026-10-27 | Priya Nair | M2 |  | BUILD | T16 | UI / screens - flutter analyze and build, fix what it reports | 10:00 | 11:00 | 0 |  | No
2026-10-28 | Priya Nair | M2 |  | CODEINSP | T17 | UI / screens - Team code inspection | 16:00 | 17:00 | 0 |  | No
2026-11-05 | Priya Nair | M2 |  | DLDINSP | T22 | Order & catalogue service - Team inspection of the detailed design | 10:00 | 12:00 | 0 |  | No
2026-11-06 | Priya Nair | M2 |  | CODE | T23 | Order & catalogue service - Implement in Dart / Flutter | 14:00 | 18:00 | 0 |  | No
2026-11-07 | Priya Nair | M2 |  | CR | T24 | Order & catalogue service - Pull-request review by a teammate | 19:00 | 21:00 | 0 |  | No
2026-11-16 | Priya Nair | M2 |  | CODEINSP | T26 | Order & catalogue service - Team code inspection | 10:00 | 11:00 | 0 |  | No
2026-11-17 | Priya Nair | M2 |  | DLDR | T29 | Local store & sync - Personal review of the detailed design | 14:00 | 15:00 | 0 |  | No
2026-11-25 | Priya Nair | M3 |  | DLDINSP | T31 | Local store & sync - Team inspection of the detailed design | 12:00 | 13:00 | 0 |  | No
2026-11-26 | Priya Nair | M3 |  | CODE | T32 | Local store & sync - Implement in Dart / Flutter | 10:00 | 12:00 | 0 |  | No
2026-11-27 | Priya Nair | M3 |  | BUILD | T34 | Local store & sync - flutter analyze and build, fix what it reports | 13:00 | 14:00 | 0 |  | No
2026-12-05 | Priya Nair | M3 |  | IT | T37 | SYSTEM - Build and integration test across components | 12:00 | 13:00 | 0 |  | No
2026-12-07 | Priya Nair | M3 |  | ST | T38 | SYSTEM - System test against the SRS | 14:00 | 15:00 | 0 |  | No
2026-12-08 | Priya Nair | M3 |  | DOC | T39 | SYSTEM - User manual and final report | 10:00 | 12:00 | 0 |  | No
2026-12-09 | Priya Nair | M3 |  | PM | T40 | SYSTEM - Postmortem: review the data and agree three changes | 14:00 | 16:00 | 0 |  | No
2026-11-02 | Priya Nair | M2 |  | AIGEN | T41 | UI / screens - Generate with Copilot, review, keep what survives | 9:00 | 11:30 | 0 |  | Yes
2026-11-03 | Priya Nair | M2 |  | AIGEN | T41 | UI / screens - Generate with Copilot, review, keep what survives | 20:00 | 22:00 | 0 |  | Yes
2026-11-05 | Priya Nair | M2 |  | AIGEN | T41 | UI / screens - Generate with Copilot, review, keep what survives | 9:30 | 12:00 | 20 |  | Yes
2026-11-16 | Daniel Wong Jun Hao | M2 |  | AIGEN | T42 | Order & catalogue service - Generate with Copilot, review, keep what s | 14:00 | 16:30 | 0 |  | Yes
2026-11-18 | Daniel Wong Jun Hao | M2 |  | AIGEN | T42 | Order & catalogue service - Generate with Copilot, review, keep what s | 20:30 | 22:30 | 15 |  | Yes
2026-11-24 | Mei Ling Chong | M3 |  | WT | T43 | UI / screens - Widget tests for the screens | 9:00 | 12:00 | 0 |  | No
2026-11-26 | Mei Ling Chong | M3 |  | WT | T43 | UI / screens - Widget tests for the screens | 14:00 | 17:00 | 30 |  | No
2026-11-27 | Mei Ling Chong | M3 |  | WT | T43 | UI / screens - Widget tests for the screens | 9:00 | 11:30 | 0 |  | No
2026-11-18 | Aisyah Binti Rahman | M2 |  | CICD | T44 | SYSTEM - GitHub Actions workflow and coverage job | 15:00 | 17:30 | 0 |  | No
2026-11-20 | Aisyah Binti Rahman | M2 |  | CICD | T44 | SYSTEM - GitHub Actions workflow and coverage job | 10:00 | 12:00 | 0 |  | No
2026-11-23 | Mei Ling Chong | M3 |  | AIGEN | T46 | Local store & sync - Generate with Copilot, review, keep what survives | 20:00 | 21:30 | 0 |  | Yes
2026-11-25 | Mei Ling Chong | M3 |  | AIGEN | T46 | Local store & sync - Generate with Copilot, review, keep what survives | 9:00 | 11:00 | 0 |  | Yes
2026-12-12 | Harith Bin Ismail | M3 |  | UAT | T45 | SYSTEM - Client acceptance test session at the shop | 9:00 | 12:30 | 30 |  | No
2026-12-12 | Harith Bin Ismail | M3 |  | UAT | T45 | SYSTEM - Client acceptance test session at the shop | 14:00 | 16:00 | 0 |  | No
2026-12-12 | Aisyah Binti Rahman | M3 |  | UAT | T45 | SYSTEM - Client acceptance test session at the shop | 9:00 | 12:30 | 30 |  | No
Note on F6: Must match an ID on the TASK sheet so the hours roll up against the plan. Leave blank only for unplanned work, and then add the task to TASK afterwards.
Note on J6: Minutes of interruption to subtract: a phone call, a break, switching to something else. Be honest - interrupt time is what makes the rate data usable.

## LOGD
Form LOGD - Defect Recording Log
Every defect found, wherever it was found. A defect caught in review still counts.
Team |  |  |  | Defects recorded |  |  | Total fix time (hrs)
Date | Defect ID | Found by | Milestone | Type | Component | Injected in | Removed in | Fix time (min) | Fix reference | Severity | From AI code? | Description & root cause
2026-12-08 | D001 | Daniel Wong Jun Hao | M3 | 10 - Documentation | HLD | HLD | HLDINSP | 30 | PR | Minor | No | Proposal correction on system artefacts
2026-10-21 | D002 | Mei Ling Chong | M1 | 10 - Documentation | SRS | HLDINSP | HLDINSP | 30 | PR | Minor | No | fix the error found in diagram
2026-11-05 | D003 | Mei Ling Chong | M2 | 50 - Interface | UI / screens | CODEINSP | UT | 60 | PR | Major | No | fix the bug in shopping cart page
2026-10-30 | D004 | Harith Bin Ismail | M2 | 50 - Interface | UI / screens | CODE | CODE | 120 | PR | Major | No | Fix the front-end code for better layout
2026-11-02 | D005 | Harith Bin Ismail | M2 | 80 - Function | Order & catalogue service | CODE | CODE | 80 | PR | Major | No | Fix shopping cart and invoice part
2026-10-20 | D006 | Priya Nair | M1 | 10 - Documentation | SRS | PLAN | REQINSP | 14 | PR | Minor | No | Misunderstanding on the phrase "Joy buyers" in non-functional requirements
2026-11-18 | D007 | Priya Nair | M2 | 80 - Function | Order & catalogue service | CODE | CODEINSP | 30 | PR | Minor | No | Fixed back-end code for user profile for "Edit" function, and any other functions that need fixing
2026-11-19 | D008 | Priya Nair | M2 | 80 - Function | Order & catalogue service | CODE | CODEINSP | 30 | PR | Minor | No | Fixed back-end code for password hashing in "Add Admin" function and "Edit Profile" at Admin side
2026-10-19 | D009 | Harith Bin Ismail | M1 | 10 - Documentation | SYSTEM | REQ | REQINSP | 20 | PR#20 | Minor | No | Order cancellation rule stated twice, in two different ways
2026-10-20 | D010 | Harith Bin Ismail | M1 | 60 - Checking | SYSTEM | REQ | REQINSP | 35 | PR#21 | Major | No | No requirement for what happens when a price changes mid-order
2026-10-21 | D011 | Aisyah Binti Rahman | M1 | 10 - Documentation | SYSTEM | REQ | REQINSP | 15 | PR#22 | Minor | No | Glossary missing 'catch of the day', used throughout section 3
2026-10-22 | D012 | Mei Ling Chong | M1 | 80 - Function | SYSTEM | REQ | REQINSP | 45 | PR#23 | Major | No | Quantity units unspecified - kg or box? Client meant box
2026-10-23 | D013 | Priya Nair | M1 | 10 - Documentation | SYSTEM | REQ | REQINSP | 10 | PR#24 | Cosmetic | No | Use-case diagram numbering out of order
2026-10-31 | D014 | Daniel Wong Jun Hao | M2 | 50 - Interface | SYSTEM | HLD | HLDINSP | 40 | PR#25 | Major | No | Sync service and order service both own the price cache
2026-10-26 | D015 | Daniel Wong Jun Hao | M2 | 90 - System | SYSTEM | HLD | HLDINSP | 30 | PR#26 | Major | No | No offline behaviour described for the catalogue screen
2026-10-27 | D016 | Harith Bin Ismail | M2 | 80 - Function | SYSTEM | HLD | HLDINSP | 25 | PR#27 | Minor | No | Invoice numbering scheme would repeat across devices
2026-10-28 | D017 | Priya Nair | M2 | 10 - Documentation | SYSTEM | HLD | HLDINSP | 10 | PR#28 | Cosmetic | No | Component diagram label does not match the SRS name
2026-10-29 | D018 | Priya Nair | M2 | 80 - Function | UI / screens | DLD | DLDR | 20 | PR#29 | Minor | No | Order line edit had no way to remove a line once added
2026-10-30 | D019 | Priya Nair | M2 | 110 - UI / Layout | UI / screens | DLD | DLDR | 15 | PR#30 | Minor | No | Quantity field design assumed a hardware keyboard
2026-11-07 | D020 | Daniel Wong Jun Hao | M2 | 120 - State Management | Order & catalogue service | DLD | DLDR | 30 | PR#31 | Major | No | Cart state held in the widget, lost on rotation
2026-11-02 | D021 | Mei Ling Chong | M2 | 70 - Data | Local store & sync | DLD | DLDR | 25 | PR#32 | Major | No | Local schema had no column for sync status
2026-11-03 | D022 | Priya Nair | M2 | 40 - Assignment | UI / screens | DLD | DLDR | 10 | PR#33 | Minor | No | Two widgets named OrderTile in different files
2026-11-04 | D023 | Daniel Wong Jun Hao | M2 | 50 - Interface | Order & catalogue service | DLD | DLDINSP | 35 | PR#34 | Major | No | Repository method signature did not match the design
2026-11-05 | D024 | Mei Ling Chong | M2 | 80 - Function | Local store & sync | DLDR | DLDINSP | 20 | PR#35 | Minor | No | Review missed the empty-queue case in the write queue
2026-11-06 | D025 | Harith Bin Ismail | M2 | 60 - Checking | UI / screens | DLD | DLDINSP | 15 | PR#36 | Minor | No | No validation described for an order with zero lines
2026-11-21 | D026 | Priya Nair | M2 | 80 - Function | UI / screens | CODE | CR | 25 | PR#37 | Major | No | Total recalculated only on add, not on quantity change
2026-11-16 | D027 | Mei Ling Chong | M2 | 110 - UI / Layout | UI / screens | CODE | CR | 15 | PR#38 | Minor | No | Column overflow on a 5-inch screen in the catalogue list
2026-11-17 | D028 | Daniel Wong Jun Hao | M2 | 120 - State Management | UI / screens | CODE | CR | 30 | PR#39 | Major | No | setState called after dispose when leaving the screen quickly
2026-11-18 | D029 | Aisyah Binti Rahman | M2 | 140 - Security | Order & catalogue service | CODE | CR | 45 | PR#40 | Critical | No | Gemini API key read from a const in source, not .env
2026-11-19 | D030 | Daniel Wong Jun Hao | M2 | 150 - AI-Generated | UI / screens | AIGEN | CR | 35 | PR#41 | Major | Yes | Generated validator accepted negative quantities
2026-11-27 | D031 | Priya Nair | M3 | 150 - AI-Generated | Order & catalogue service | AIGEN | CR | 40 | PR#42 | Major | Yes | Generated parser assumed English-only input; staff write Malay
2026-11-28 | D032 | Harith Bin Ismail | M3 | 50 - Interface | Local store & sync | CODE | CR | 20 | PR#43 | Minor | No | Repository returned a list where the caller expected a stream
2026-11-23 | D033 | Mei Ling Chong | M3 | 80 - Function | Order & catalogue service | CODE | CR | 25 | PR#44 | Minor | No | Rounding applied per line instead of on the invoice total
2026-11-17 | D034 | Priya Nair | M2 | 20 - Syntax | UI / screens | CODE | BUILD | 5 | PR#45 | Cosmetic | No | Missing const, analyzer warning on develop
2026-11-18 | D035 | Aisyah Binti Rahman | M2 | 30 - Build / Package | SYSTEM | CODE | BUILD | 40 | PR#46 | Major | No | intl version conflict broke the Android build
2026-11-26 | D036 | Daniel Wong Jun Hao | M3 | 20 - Syntax | Order & catalogue service | CODE | BUILD | 5 | PR#47 | Cosmetic | No | Unused import flagged by flutter analyze
2026-11-27 | D037 | Mei Ling Chong | M3 | 40 - Assignment | Local store & sync | CODE | BUILD | 15 | PR#48 | Minor | No | Nullable field used without a null check
2026-11-28 | D038 | Aisyah Binti Rahman | M3 | 30 - Build / Package | SYSTEM | CODE | BUILD | 30 | PR#49 | Major | No | Release build failed - signing config missing from CI
2026-11-23 | D039 | Harith Bin Ismail | M3 | 80 - Function | Order & catalogue service | CODE | CODEINSP | 30 | PR#50 | Major | No | Discount applied before tax instead of after
2026-12-01 | D040 | Mei Ling Chong | M3 | 70 - Data | Local store & sync | CODE | CODEINSP | 25 | PR#51 | Minor | No | Date stored as local time, compared as UTC
2026-12-02 | D041 | Priya Nair | M3 | 60 - Checking | UI / screens | CODE | CODEINSP | 15 | PR#52 | Minor | No | No guard against a double tap on Submit
2026-11-26 | D042 | Daniel Wong Jun Hao | M3 | 80 - Function | Order & catalogue service | CODE | UT | 35 | PR#53 | Major | No | Order total wrong when a line quantity was zero
2026-11-27 | D043 | Mei Ling Chong | M3 | 150 - AI-Generated | UI / screens | AIGEN | UT | 30 | PR#54 | Major | Yes | Generated date formatter failed on the first of the month
2026-12-05 | D044 | Mei Ling Chong | M3 | 70 - Data | Local store & sync | CODE | UT | 25 | PR#55 | Minor | No | Sync marked records done before the write confirmed
2026-11-30 | D045 | Daniel Wong Jun Hao | M3 | 80 - Function | Order & catalogue service | DLD | UT | 40 | PR#56 | Major | No | Price lookup returned the newest price, not the one at order time
2026-12-01 | D046 | Priya Nair | M3 | 60 - Checking | UI / screens | CODE | UT | 15 | PR#57 | Minor | No | Empty catalogue showed a spinner forever
2026-12-02 | D047 | Mei Ling Chong | M3 | 110 - UI / Layout | UI / screens | CODE | WT | 20 | PR#58 | Minor | No | Submit button stayed enabled while the order was saving
2026-12-03 | D048 | Mei Ling Chong | M3 | 120 - State Management | UI / screens | CODE | WT | 25 | PR#59 | Major | No | Catalogue filter did not clear when the screen was reopened
2026-12-04 | D049 | Daniel Wong Jun Hao | M3 | 50 - Interface | SYSTEM | HLD | IT | 50 | PR#60 | Major | No | Order service and sync service disagreed on the id format
2026-12-05 | D050 | Aisyah Binti Rahman | M3 | 90 - System | SYSTEM | CODE | IT | 45 | PR#61 | Major | No | Offline queue drained twice when connection flapped
2026-12-07 | D051 | Priya Nair | M3 | 130 - Performance | UI / screens | CODE | ST | 40 | PR#62 | Major | No | Catalogue list janked badly past about 300 items
2026-12-08 | D052 | Harith Bin Ismail | M3 | 90 - System | SYSTEM | HLD | ST | 35 | PR#63 | Major | No | Invoice PDF rendered blank on one of the client's devices
2026-12-09 | D053 | Harith Bin Ismail | M3 | 110 - UI / Layout | UI / screens | CODE | UAT | 15 | PR#64 | Cosmetic | No | Counter staff found the font too small at the till
Note on G6: The phase where the mistake was MADE, not where you noticed it. Being honest here is the whole point - it is what tells you which review to strengthen.
Note on L6: Mark Yes if the faulty line came from Copilot, Claude or any other generator. This is how the team learns where unreviewed AI output costs it time.

## LOGTEST
Form LOGTEST - Test Case Log
The evidence behind the Testing & Release rubric. Automated tests still get a row.
Team |  |  |  | Cases |  | Passed |  | Pass rate |  | Automated
Date run | Test ID | Module / Screen | What is being tested | Type | Expected result | Actual result | Status | Milestone | Tester | Defect ref (LOGD) | Automated?
2026-11-16 | TC001 | Order entry screen | Order total sums line amounts correctly | Unit | Total equals sum of line amounts | As expected | Pass | M2 | Aisyah Binti Rahman |  | Yes
2026-11-17 | TC002 | Catalogue screen | Order total recalculates when a quantity changes | Unit | Total updates immediately | As expected | Pass | M2 | Daniel Wong Jun Hao |  | Yes
2026-11-18 | TC003 | Invoice & history | Zero-quantity line is rejected | Unit | Validation error shown, line not added | As expected | Pass | M2 | Mei Ling Chong |  | Yes
2026-11-19 | TC004 | Order & catalogue service | Negative quantity is rejected | Unit | Validation error shown | As expected | Pass | M2 | Harith Bin Ismail |  | Yes
2026-11-20 | TC005 | Local store & sync | Discount applied after tax | Unit | Invoice total matches the worked example | As expected | Pass | M2 | Priya Nair |  | Yes
2026-11-21 | TC006 | Shared widgets & theme | Price at order time is used, not latest price | Unit | Historic price returned | As expected | Pass | M2 | Aisyah Binti Rahman |  | Yes
2026-11-16 | TC007 | Order entry screen | Rounding applied once, on the invoice total | Unit | Total matches to two decimals | As expected | Pass | M2 | Daniel Wong Jun Hao |  | Yes
2026-11-17 | TC008 | Catalogue screen | Invoice number unique across devices | Unit | No duplicate for 1000 generated ids | As expected | Pass | M2 | Mei Ling Chong |  | Yes
2026-11-18 | TC009 | Invoice & history | Empty order cannot be submitted | Unit | Submit rejected with a message | As expected | Pass | M2 | Harith Bin Ismail |  | Yes
2026-11-19 | TC010 | Order & catalogue service | Catalogue filter returns matching items only | Unit | Filtered list matches the query | As expected | Pass | M2 | Priya Nair |  | Yes
2026-11-20 | TC011 | Local store & sync | Catalogue sorts by name | Unit | Alphabetical order | As expected | Pass | M2 | Aisyah Binti Rahman |  | Yes
2026-11-21 | TC012 | Shared widgets & theme | Order note parser reads a Malay quantity phrase | Unit | Two lines parsed correctly | As expected | Pass | M2 | Daniel Wong Jun Hao |  | Yes
2026-11-16 | TC013 | Order entry screen | Order note parser handles an unknown item | Unit | Item flagged, not silently dropped | As expected | Pass | M2 | Mei Ling Chong |  | Yes
2026-11-17 | TC014 | Catalogue screen | Write queue stores an order when offline | Unit | Record written with status pending | As expected | Pass | M2 | Harith Bin Ismail |  | Yes
2026-11-18 | TC015 | Invoice & history | Write queue drains once when connection returns | Unit | Record sent exactly once | As expected | Pass | M2 | Priya Nair |  | Yes
2026-11-19 | TC016 | Order & catalogue service | Write queue survives app restart | Unit | Pending record still present | As expected | Pass | M2 | Aisyah Binti Rahman |  | Yes
2026-11-20 | TC017 | Local store & sync | Sync marks a record done only after confirmation | Unit | Status stays pending until ack | As expected | Pass | M2 | Daniel Wong Jun Hao |  | Yes
2026-11-21 | TC018 | Shared widgets & theme | Dates stored and compared in UTC | Unit | Same instant across time zones | As expected | Pass | M2 | Mei Ling Chong |  | Yes
2026-11-16 | TC019 | Order entry screen | Repository returns a stream of catalogue updates | Unit | Listener receives the update | As expected | Pass | M2 | Harith Bin Ismail |  | Yes
2026-11-17 | TC020 | Catalogue screen | Auth rejects an unknown phone number | Unit | Sign-in fails with a clear message | As expected | Pass | M2 | Priya Nair |  | Yes
2026-11-18 | TC021 | Invoice & history | API key read from environment, not source | Unit | Key absent from the compiled bundle | As expected | Pass | M2 | Aisyah Binti Rahman |  | Yes
2026-11-19 | TC022 | Order & catalogue service | Session expires after the configured period | Unit | User returned to sign-in | As expected | Pass | M2 | Daniel Wong Jun Hao |  | Yes
2026-11-27 | TC023 | Local store & sync | Cart survives a screen rotation | Unit | Cart contents unchanged | As expected | Pass | M3 | Mei Ling Chong |  | Yes
2026-11-28 | TC024 | Shared widgets & theme | Price change mid-order prompts the user | Unit | Prompt shown once | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-11-23 | TC025 | Order entry screen | Stock below threshold is flagged | Unit | Item marked low stock | As expected | Pass | M3 | Priya Nair |  | Yes
2026-11-24 | TC026 | Catalogue screen | Order history pages in batches of twenty | Unit | Second page loads on scroll | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-11-25 | TC027 | Invoice & history | Invoice PDF renders all order lines | Unit | Line count matches the order | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-11-26 | TC028 | Order & catalogue service | Currency formatted as RM with two decimals | Unit | Formatted string matches | As expected | Pass | M3 | Mei Ling Chong |  | Yes
2026-11-27 | TC029 | Local store & sync | Unknown item in a note does not crash the parser | Unit | Error returned, app alive | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-11-28 | TC030 | Shared widgets & theme | Duplicate submit within one second is ignored | Unit | Only one order created | As expected | Pass | M3 | Priya Nair |  | Yes
2026-11-30 | TC031 | Order entry screen | Order entry screen renders an empty cart state | Widget | Empty-state message shown | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-12-01 | TC032 | Catalogue screen | Submit button disabled while saving | Widget | Button shows a spinner and is disabled | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-12-02 | TC033 | Invoice & history | Quantity field accepts digits only | Widget | Letters rejected by the field | As expected | Pass | M3 | Mei Ling Chong |  | Yes
2026-12-03 | TC034 | Order & catalogue service | Removing a line updates the displayed total | Widget | Total decreases correctly | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-12-04 | TC035 | Local store & sync | Catalogue list scrolls past three hundred items | Widget | No frame drops reported | Still failing - defect raised, fix in progress | Fail | M3 | Priya Nair | PR#64 | Yes
2026-12-05 | TC036 | Shared widgets & theme | Catalogue filter clears when the screen reopens | Widget | Filter field empty | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-11-30 | TC037 | Order entry screen | Long item names do not overflow on a small screen | Widget | No overflow warning | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-12-01 | TC038 | Catalogue screen | Invoice screen shows the order lines | Widget | All lines visible | As expected | Pass | M3 | Mei Ling Chong |  | Yes
2026-12-02 | TC039 | Invoice & history | History screen shows the most recent order first | Widget | Order matches expectation | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-12-03 | TC040 | Order & catalogue service | Offline banner appears when connection is lost | Widget | Banner visible | As expected | Pass | M3 | Priya Nair |  | Yes
2026-12-04 | TC041 | Local store & sync | Offline banner disappears on reconnect | Widget | Banner removed | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-12-05 | TC042 | Shared widgets & theme | Error dialog is dismissable | Widget | Dialog closes on tap | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-11-30 | TC043 | Order entry screen | Theme applies the brand colour to the app bar | Widget | Colour matches the design system | As expected | Pass | M3 | Mei Ling Chong |  | Yes
2026-12-01 | TC044 | Catalogue screen | Font size is readable at the counter device setting | Widget | Text scales as configured | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-12-02 | TC045 | Invoice & history | Sign-in screen validates the phone format | Widget | Inline error shown | As expected | Pass | M3 | Priya Nair |  | Yes
2026-12-03 | TC046 | Order & catalogue service | Low-stock badge renders on the catalogue tile | Widget | Badge visible | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-12-11 | TC047 | Local store & sync | Place an order end to end while online | Integration | Order appears in history | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-12-12 | TC048 | Shared widgets & theme | Place an order offline, then reconnect | Integration | Order syncs once, no duplicate | Still failing - defect raised, fix in progress | Fail | M3 | Mei Ling Chong | PR#77 | Yes
2026-12-07 | TC049 | Order entry screen | Generate and open an invoice PDF | Integration | PDF opens with correct totals | As expected | Pass | M3 | Harith Bin Ismail |  | Yes
2026-12-08 | TC050 | Catalogue screen | Sign in, place an order, sign out | Integration | Session cleared, order retained | As expected | Pass | M3 | Priya Nair |  | Yes
2026-12-09 | TC051 | Invoice & history | Catalogue updates propagate to an open screen | Integration | List refreshes without restart | As expected | Pass | M3 | Aisyah Binti Rahman |  | Yes
2026-12-10 | TC052 | Order & catalogue service | Connection flaps repeatedly during a sync | Integration | Queue drains exactly once | As expected | Pass | M3 | Daniel Wong Jun Hao |  | Yes
2026-12-11 | TC053 | Local store & sync | Counter staff place a real order unaided | Acceptance | Order completed in under 3 minutes | As expected | Pass | M3 | Mei Ling Chong |  | No
2026-12-12 | TC054 | Shared widgets & theme | Counter staff find yesterday's order | Acceptance | Order located without help | As expected | Pass | M3 | Harith Bin Ismail |  | No

## LOGAI
Form LOGAI - AI-Assisted Development Log
Every change where a generator wrote code that reached the repository. No entry, no merge.
Team |  |  | Entries |  | Approved |  | Lines generated |  |  | Lines kept after review |  |  | Keep rate
Date | Member | Milestone | File / module | Feature or behaviour | AI tool | Prompt (summarised) | Lines gen. | Lines kept | Keep % | Reviewer | Review verdict | Tests written? | Test status | Commit / PR ref | Approved?
2026-10-27 | Priya Nair | M2 | order_form.dart | Form validation for quantity and item fields | GitHub Copilot | Validate quantity is a positive integer and item is selected; return a message per field | 60 | 45 |  | Daniel Wong Jun Hao | Approved with changes | Yes | Pass | PR#21 | Yes
2026-10-28 | Priya Nair | M2 | catalogue_list.dart | ListView.builder with lazy loading | GitHub Copilot | Build a lazy list of catalogue items with a low-stock badge | 40 | 34 |  | Mei Ling Chong | Approved | Yes | Pass | PR#22 | Yes
2026-11-05 | Aisyah Binti Rahman | M2 | .github/workflows/ci.yml | GitHub Actions workflow | Claude | Workflow that runs flutter analyze, flutter test and uploads a coverage report | 55 | 50 |  | Mei Ling Chong | Approved with changes | No | Not run | PR#23 | Yes
2026-11-06 | Daniel Wong Jun Hao | M2 | price_repository.dart | Dated price lookup | GitHub Copilot | Return the price effective on a given date from a list of dated price records | 45 | 28 |  | Harith Bin Ismail | Changes requested | Yes | Pass | PR#24 | Yes
2026-11-07 | Daniel Wong Jun Hao | M2 | note_parser.dart | Gemini order-note parser wrapper | Google Gemini | Parse a free-text order note into item and quantity pairs; handle Malay and English | 90 | 62 |  | Priya Nair | Approved with changes | Yes | Pass | PR#25 | Yes
2026-11-16 | Priya Nair | M2 | invoice_view.dart | Invoice layout widget | GitHub Copilot | Lay out order lines, subtotal, tax and total in a printable column | 50 | 41 |  | Mei Ling Chong | Approved | Yes | Pass | PR#26 | Yes
2026-11-17 | Mei Ling Chong | M2 | write_queue.dart | Offline write-queue scaffolding | Claude | A queue that persists pending writes and drains them once when connectivity returns | 75 | 58 |  | Daniel Wong Jun Hao | Approved with changes | Yes | Pass | PR#27 | Yes
2026-11-18 | Mei Ling Chong | M2 | app_theme.dart | Material 3 theme from the brand colours | GitHub Copilot | Build a Material 3 ColorScheme from a seed colour and define text styles | 35 | 33 |  | Priya Nair | Approved | No | Not run | PR#28 | Yes
2026-11-19 | Harith Bin Ismail | M2 | invoice_number.dart | Device-safe invoice numbering | Claude | Generate invoice numbers unique across devices without a central server | 40 | 30 |  | Aisyah Binti Rahman | Approved with changes | Yes | Pass | PR#29 | Yes
2026-11-20 | Priya Nair | M2 | order_form.dart | Double-submit guard | GitHub Copilot | Prevent a second submit while the first is still in flight | 20 | 18 |  | Mei Ling Chong | Approved | Yes | Pass | PR#30 | Yes
2026-11-28 | Mei Ling Chong | M3 | sync_service.dart | Retry with exponential backoff | GitHub Copilot | Retry a failed sync with exponential backoff and a maximum attempt count | 45 | 36 |  | Daniel Wong Jun Hao | Approved | Yes | Pass | PR#31 | Yes
2026-11-30 | Daniel Wong Jun Hao | M3 | stock_rules.dart | Low-stock threshold rules | GitHub Copilot | Flag an item as low stock based on a per-item threshold | 25 | 22 |  | Harith Bin Ismail | Approved | Yes | Pass | PR#32 | Yes
2026-12-01 | Mei Ling Chong | M3 | order_form_test.dart | Widget tests for the order form | Claude | Widget tests covering empty cart, quantity validation and the disabled submit state | 80 | 64 |  | Priya Nair | Approved with changes | Yes | Pass | PR#33 | Yes
2026-12-02 | Aisyah Binti Rahman | M3 | .github/workflows/release.yml | Signed release build job | Claude | Build a signed release APK and attach it to a GitHub release | 50 | 38 |  | Harith Bin Ismail | Approved with changes | No | Pass | PR#34 | Yes
2026-12-10 | Harith Bin Ismail | M3 | docs/user_manual.md | First draft of the user manual | ChatGPT / GPT-4 | Draft a user manual for counter staff covering sign-in, ordering and finding past orders | 120 | 70 |  | Aisyah Binti Rahman | Changes requested | No | Not run | PR#35 | Yes
2026-12-11 | Priya Nair | M3 | catalogue_list.dart | Performance fix for long lists | GitHub Copilot | Reduce rebuilds in a long list by adding keys and a const item widget | 30 | 26 |  | Daniel Wong Jun Hao | Approved | Yes | Pass | PR#36 | Yes
Note on I6: How many of the generated lines survived review and ended up merged. A low keep rate is not a failure; it is useful evidence about where the tool helps and where it does not.
Note on K6: The reviewer must not be the person who prompted the generator. A row where member and reviewer are the same name is highlighted red - self-review does not satisfy the rule.

## LOGCLIENT
Form LOGCLIENT - Client Engagement Log
Proof of the client relationship. M1 needs 2 meetings, M2 needs 4, M3 needs 6 - cumulative.
Client |  |  |  |  | Meetings held |  | Face-to-face |  | Total hours
Date | Milestone | Mode | Hours | Team attendees | Client attendees | Purpose / agenda | Decisions made | Action items & owners | Evidence (minutes / photo link) | Client sign-off?
2026-10-10 | M1 | Face-to-face | 1.5 | All five | Encik Faizal, counter supervisor | First visit: watch how orders are taken on paper today | Scope limited to ordering and invoicing; stock control is out of scope for this semester | Harith to draft the user stories by Friday; Aisyah to send the project brief | Photos + notes in docs/meetings/m01.md | No
2026-10-24 | M1 | Face-to-face | 2 | Harith, Aisyah, Priya | Encik Faizal | Walk through the paper mock-ups of the order screen | Order lines must allow a free-text note; quantity is by box, not kg | Priya to redraw the order screen; Mei Ling to update the SRS | Signed mock-up sheets, photographed | Yes
2026-11-07 | M2 | Online (Zoom/Meet) | 1 | Harith, Daniel | Encik Faizal | Review the SRS section on pricing | Prices change weekly - the app must keep the price at order time | Daniel to change the data model to dated prices; raise a CCR | docs/meetings/m03.md | No
2026-11-21 | M2 | Face-to-face | 2 | All five | Encik Faizal, two counter staff | Demonstrate the prototype on a real device | Staff asked for a bigger font; confirmed the offline requirement is real, the shop loses signal daily | Priya to raise the font issue; Mei Ling to prioritise the offline queue | Video of the session | Yes
2026-12-05 | M3 | Face-to-face | 1.5 | Harith, Mei Ling, Daniel | Encik Faizal | Review invoice layout and the order history screen | Invoice must show the shop name and SSM number; history only needs 30 days | Harith to update the invoice template | docs/meetings/m05.md | No
2026-12-12 | M3 | Face-to-face | 2.5 | All five | Encik Faizal, two counter staff | Acceptance test: staff place real orders unaided | Accepted with one cosmetic change (font size at the till) | Priya to ship the font fix before handover | Signed acceptance sheet | Yes
2027-01-02 | M4 | Face-to-face | 2 | All five | Encik Faizal, two counter staff | Handover: install the release build, train two staff, leave the quick card | Client signed off; agreed to a follow-up call in two weeks | Aisyah to send the repository link and the manual | Signed handover form | Yes

## LOGGIT
Form LOGGIT - GitHub Activity Log
Recorded weekly from the repository's Insights tab. These are facts, not estimates.
Repository |  |  |  |  | Commits |  | PRs merged |  | Reviews
Week | Milestone | Member | Commits | PRs opened | PRs merged | Reviews given | Issues closed | Lines + | Lines - | CI green? | Notes
3 | M1 | Aisyah Binti Rahman | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
3 | M1 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
3 | M1 | Mei Ling Chong | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
3 | M1 | Harith Bin Ismail | 3 | 1 | 1 | 1 | 1 | 126 | 33 | Yes
3 | M1 | Priya Nair | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
4 | M1 | Aisyah Binti Rahman | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
4 | M1 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
4 | M1 | Mei Ling Chong | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
4 | M1 | Harith Bin Ismail | 4 | 1 | 1 | 1 | 1 | 168 | 44 | Yes
4 | M1 | Priya Nair | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
5 | M1 | Aisyah Binti Rahman | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
5 | M1 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
5 | M1 | Mei Ling Chong | 3 | 1 | 1 | 1 | 1 | 126 | 33 | Yes
5 | M1 | Harith Bin Ismail | 5 | 1 | 1 | 2 | 1 | 210 | 55 | Yes
5 | M1 | Priya Nair | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
6 | M2 | Aisyah Binti Rahman | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
6 | M2 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
6 | M2 | Mei Ling Chong | 3 | 1 | 1 | 1 | 1 | 126 | 33 | Yes
6 | M2 | Harith Bin Ismail | 5 | 1 | 1 | 2 | 1 | 210 | 55 | Yes
6 | M2 | Priya Nair | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
7 | M2 | Aisyah Binti Rahman | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
7 | M2 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
7 | M2 | Mei Ling Chong | 4 | 1 | 1 | 1 | 1 | 168 | 44 | Yes
7 | M2 | Harith Bin Ismail | 6 | 2 | 1 | 2 | 2 | 252 | 66 | Yes
7 | M2 | Priya Nair | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
9 | M2 | Aisyah Binti Rahman | 2 | 0 | 0 | 1 | 0 | 84 | 22 | No | CI red for two days - intl version conflict, fixed in PR#27
9 | M2 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | No
9 | M2 | Mei Ling Chong | 4 | 1 | 1 | 1 | 1 | 168 | 44 | No
9 | M2 | Harith Bin Ismail | 7 | 2 | 1 | 2 | 2 | 294 | 77 | No
9 | M2 | Priya Nair | 2 | 0 | 0 | 1 | 0 | 84 | 22 | No
10 | M3 | Aisyah Binti Rahman | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
10 | M3 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
10 | M3 | Mei Ling Chong | 4 | 1 | 1 | 1 | 1 | 168 | 44 | Yes
10 | M3 | Harith Bin Ismail | 7 | 2 | 1 | 2 | 2 | 294 | 77 | Yes
10 | M3 | Priya Nair | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
11 | M3 | Aisyah Binti Rahman | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
11 | M3 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
11 | M3 | Mei Ling Chong | 4 | 1 | 1 | 1 | 1 | 168 | 44 | Yes
11 | M3 | Harith Bin Ismail | 6 | 2 | 1 | 2 | 2 | 252 | 66 | Yes
11 | M3 | Priya Nair | 2 | 0 | 0 | 1 | 0 | 84 | 22 | Yes
12 | M3 | Aisyah Binti Rahman | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
12 | M3 | Daniel Wong Jun Hao | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes
12 | M3 | Mei Ling Chong | 3 | 1 | 1 | 1 | 1 | 126 | 33 | Yes
12 | M3 | Harith Bin Ismail | 5 | 1 | 1 | 2 | 1 | 210 | 55 | Yes
12 | M3 | Priya Nair | 1 | 0 | 0 | 0 | 0 | 42 | 11 | Yes

## WEEK
Form WEEK - Weekly Status Report
Filled in at the weekly team meeting. This is the record the instructor and demonstrator read.
Team |  |  |  |  | Meetings held
Week | Week starting | M/stone | Met? | Present | Plan hrs | Actual hrs | Act/Plan | Cum PV | Cum EV | EV variance | Status | Biggest risk or issue this week | Commitment for next week
3 | 2026-10-05 | M1 | Yes | 5 | [7 empty] | Client not yet confirmed - no signed approval form | Submit the client approval form and open the repo
4 | 2026-10-12 | M1 | Yes | 5 | [7 empty] | Requirements still vague on pricing | Finish the SRS draft and book the mock-up review
5 | 2026-10-19 | M1 | Yes | 5 | [7 empty] | M1 due Saturday; SRS inspection not scheduled yet | Submit M1: proposal, SRS, charter, repo
6 | 2026-10-26 | M2 | Yes | 4 | [7 empty] | Daniel missed two sessions - no commits this week | Daniel to pick up the price repository and report Wednesday
7 | 2026-11-02 | M2 | Yes | 5 | [7 empty] | Dated-price change may not fit before M2 | Finish the order screen and the catalogue service
8 | 2026-11-09 | M2 | No | 0 | [7 empty] | Mid-semester break - no work planned | Resume Wednesday of week 9
9 | 2026-11-16 | M2 | Yes | 5 | [7 empty] | CI red for two days; contribution is very uneven | Submit M2; Aisyah to fix CI; raise contribution at the meeting
10 | 2026-11-23 | M3 | Yes | 5 | [7 empty] | Harith is carrying far too much of the work | Redistribute the sync tasks; Mei Ling takes the widget tests
11 | 2026-11-30 | M3 | Yes | 5 | [7 empty] | Coverage at 58%, below the 60% floor | Add tests for the write queue and the price repository
12 | 2026-12-07 | M3 | Yes | 5 | [7 empty] | Acceptance test revealed a font size issue | Fix the font, finish system test, prepare M3
13 | 2026-12-14 | M3 | Yes | 5 | [7 empty] | None - M3 submitted on time | Start the final report and the demo video
14 | 2026-12-21 | M4 | Yes | 5 | [7 empty] | Demo video not started | Record the demo and rehearse the presentation
15 | 2026-12-28 | M4 | Yes | 5 | [7 empty] | None - handover complete | Submit M4 and close the repository at v1.0.0

## IRTL
Form IRTL - Issue & Risk Tracking Log
A risk might happen; an issue already has. Both need an owner and a date, or they are just worry.
Team |  |  |  | Open |  | High priority
ID | Date raised | Type | Scope | Description | Likelihood | Impact | Priority | Owner | Mitigation / action taken | Follow-up | Status | Date closed
R01 | 2026-10-07 | Risk | Client | SeaFresh may not sign the client approval form in time | Medium | High |  | Harith Bin Ismail | Visited the shop twice in week 3; form signed on 10 Oct | 2026-10-21 | Complete | 2026-10-23
R02 | 2026-10-14 | Risk | Technical | The shop loses signal daily; orders could be lost mid-entry | High | High |  | Mei Ling Chong | Offline-first write queue built in M2; integration test simulates loss of connection | 2026-12-02 | Complete | 2026-12-04
I01 | 2026-10-28 | Issue | Team | Daniel logged no hours and no commits in week 6 | High | Medium |  | Aisyah Binti Rahman | Raised at the week 6 meeting; Daniel took the price repository and reported weekly after | 2026-11-18 | Complete | 2026-11-20
I02 | 2026-11-04 | Issue | Client | Prices change weekly - the data model assumed they were static | High | High |  | Daniel Wong Jun Hao | CCR-02 raised and approved; model changed to dated price records | 2026-11-18 | Complete | 2026-11-20
R03 | 2026-11-18 | Risk | Technical | Gemini API cost and latency unknown at the shop's connection speed | Medium | Medium |  | Priya Nair | Measured over a week; parser made optional with a manual fallback | 2026-12-02 | Complete | 2026-12-04
I03 | 2026-11-18 | Issue | Team | Work is very unevenly shared - one member has logged 45% of all hours | High | High |  | Aisyah Binti Rahman | Tasks redistributed in week 10; still uneven at M3, reported honestly in the peer evaluation | 2026-12-16 | In progress
I04 | 2026-11-18 | Issue | Technical | CI red for two days after an intl version conflict | Medium | Medium |  | Aisyah Binti Rahman | Dependency pinned; a weekly dependency check added to the workflow | 2026-11-25 | Complete | 2026-11-27
R04 | 2026-12-02 | Risk | Project | Coverage below the 60% floor with two weeks to M3 | Medium | High |  | Mei Ling Chong | Mei Ling took the widget tests; coverage reached 64% by week 12 | 2026-12-09 | Complete | 2026-12-11
R05 | 2026-12-16 | Risk | Client | Counter staff may not adopt the app after handover | Medium | High |  | Harith Bin Ismail | Two staff trained in person at handover; one-page card left at the till | 2026-12-30 | Complete | 2027-01-01

## IRWEEK
Issue & Risk Week Summary
How the risk picture moved each week. Calculated from IRTL - the comment column is yours.
Week | Week starting | Raised | Closed | Open at end | High priority open | Risks open | Issues open | What the team did about it this week
3 | 2026-10-05
4 | 2026-10-12
5 | 2026-10-19
6 | 2026-10-26
7 | 2026-11-02
8 | 2026-11-09
9 | 2026-11-16
10 | 2026-11-23
11 | 2026-11-30
12 | 2026-12-07
13 | 2026-12-14
14 | 2026-12-21
15 | 2026-12-28
Reading this sheet
Watch the Open at end column across the weeks, not any single number. A count that climbs steadily means the team is raising risks faster than it resolves them - which is still better than a column of zeros, because a project with no recorded risks is a project where nobody is looking for them.

## RISK
Top Risk Register
The highest-priority open items from IRTL, ranked. Read this at every weekly meeting.
Open items |  | High priority (6 or more)
Rank | ID | Risk or issue | Likelihood | Impact | Priority | Owner | Follow-up | Status | Mitigation in hand
1
2
3
4
5
6
7
8
9
10
11
12
Priority is likelihood times impact
High = 3, Medium = 2, Low = 1, so priority runs from 1 to 9. Six or more needs an owner and a date this week. A risk with no owner is not being managed, it is being hoped about.
Note on A6: This sheet is calculated from IRTL and sorted by priority. To change anything here, change the row in IRTL - a completed item drops off this list automatically.

## CCR
Form CCR - Configuration Change Request
Once a baseline is agreed with the client, changes go through here - not through a quiet commit.
Team |  |  |  | Requests |  | Approved |  | Added hours
CCR ID | Date | Raised by | Change type | Component | What changes | Why - whose need does this serve | Est. hrs | M/stone | Reviewer | Decision | Decided on | Notes
CCR-01 | 2026-10-27 | Harith Bin Ismail | Requirement | Order entry | Add a free-text note to each order line | Counter staff already write notes on the paper book; without it they will not use the app | 6 | M2 | Aisyah Binti Rahman | Approved | 2026-10-29 | Absorbed into the M2 plan
CCR-02 | 2026-11-03 | Daniel Wong Jun Hao | Design | Order & catalogue service | Replace the single price field with dated price records | Supplier prices change weekly; an invoice must use the price at order time | 14 | M2 | Aisyah Binti Rahman | Approved | 2026-11-05 | Pushed the catalogue work one week; schedule updated
CCR-03 | 2026-11-17 | Priya Nair | Requirement | Order entry | Add a Gemini parser for free-text order notes | Staff type faster than they browse; raised after the week 9 demo | 18 | M3 | Aisyah Binti Rahman | Approved | 2026-11-19 | Made optional with a manual fallback after the latency test
CCR-04 | 2026-12-01 | Harith Bin Ismail | Requirement | Order history | Show all orders rather than the last 30 days | Requested by the client at the week 11 meeting | 10 | M3 | Aisyah Binti Rahman | Deferred | 2026-12-03 | Deferred to post-handover; the client agreed 30 days is enough for the pilot
CCR-05 | 2026-12-08 | Priya Nair | Code | UI / screens | Increase the base font size at the till | Counter staff could not read the catalogue at arm's length during the acceptance test | 2 | M4 | Aisyah Binti Rahman | Approved | 2026-12-10 | Shipped before handover
CCR-06 | 2026-12-15 | Mei Ling Chong | Build / CI | SYSTEM | Add a signed release job to the workflow | M4 requires a v1.0.0 release artefact | 4 | M4 | Aisyah Binti Rahman | Approved | 2026-12-17 | Done in week 14

## SUMS
Form SUMS - Size Summary
Screens, widgets, services and their size. Without size there is no density, no rate, no learning.
Team
[6 empty] | PLANNED SIZE | [6 empty] | ACTUAL SIZE
ID | Assembly / part name | Type | Parent assembly | Owner | Size measure | Base | Deleted | Modified | Added | Reused | New & changed | Total | Base | Deleted | Modified | Added | Reused | New & changed | Total
1 | UI / screens | Part | SYSTEM | Priya Nair | Dart LOC | 0 | 0 | 200 | 1800 | 300 |  |  | 0 | 0 | 260 | 1950 | 300
2 | Order & catalogue service | Part | SYSTEM | Daniel Wong Jun Hao | Dart LOC | 0 | 0 | 100 | 900 | 150 |  |  | 0 | 0 | 140 | 980 | 150
3 | Local store & sync | Part | SYSTEM | Mei Ling Chong | Dart LOC | 0 | 0 | 60 | 500 | 80 |  |  | 0 | 0 | 90 | 540 | 80
4 | Shared widgets & theme | Part | SYSTEM | Mei Ling Chong | Dart LOC | 0 | 0 | 0 | 350 | 0 |  |  | 0 | 0 | 30 | 410 | 0
5 | Order entry screen | Part | UI / screens | Priya Nair | Screens | 0 | 0 | 0 | 6 | 0 |  |  | 0 | 0 | 0 | 7 | 0
6 | Catalogue screen | Part | UI / screens | Priya Nair | Screens | 0 | 0 | 0 | 4 | 0 |  |  | 0 | 0 | 0 | 5 | 0
7 | Invoice & history | Part | UI / screens | Harith Bin Ismail | Screens | 0 | 0 | 0 | 4 | 0 |  |  | 0 | 0 | 0 | 4 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
TOTAL (Dart LOC rows only)
Document & Artefact Size
| Artefact |  |  |  | Measure | Plan | [5 empty] | Actual
| Software Requirements Specification (SRS) |  |  |  | SRS Pages | 60 | [5 empty] | 64
| Software Design Document (SDD) |  |  |  | SDD Pages | 50 | [5 empty] | 58
| User Manual |  |  |  | Documents | 1 | [5 empty] | 1
| Test Plan |  |  |  | Documents | 1 | [5 empty] | 1
| Final Report |  |  |  | Documents | 1 | [5 empty] | 1
| Screens delivered |  |  |  | Screens | 14 | [5 empty] | 16
| Reusable widgets built |  |  |  | Widgets | 20 | [5 empty] | 24
| API endpoints consumed |  |  |  | API Endpoints | 8 | [5 empty] | 9

## SUMP
Form SUMP - Plan Summary
Plan columns are yours to fill at the launch. Actual columns read themselves out of the logs.
Team |  |  | Cycle / milestone
Program Size
| Plan | Actual | Actual % |  | Source
Total requirements pages (SRS) |  |  |  |  | SUMS document block
Total design pages (SDD) |  |  |  |  | SUMS document block
New & changed Dart LOC (N) |  |  |  |  | SUMS component totals
Total Dart LOC (T) |  |  |  |  | SUMS component totals
Reused Dart LOC (R) |  |  |  |  | SUMS component totals
Screens delivered |  |  |  |  | SUMS document block
Reusable widgets built |  |  |  |  | SUMS document block
Time in Phase (hours)
Phase | Plan | Actual | Actual % | Plan % | Description
MGMT | 7 |  |  |  | Management & Miscellaneous
STRAT | 11 |  |  |  | Launch & Strategy
PLAN | 10.5 |  |  |  | Planning
REQ | 7 |  |  |  | Requirements / SRS
STP | 6 |  |  |  | System Test Plan
REQINSP | 11 |  |  |  | Requirements Inspection
HLD | 9.5 |  |  |  | High-Level Design / Architecture (SDD)
ITP | 6 |  |  |  | Integration Test Plan
HLDINSP | 6 |  |  |  | HLD Inspection
DLD | 27.5 |  |  |  | Detailed Design (screens, widgets, models)
DLDR | 40.5 |  |  |  | Detailed Design Review
TD | 37 |  |  |  | Test Development
DLDINSP | 25.5 |  |  |  | Detailed Design Inspection
CODE | 66 |  |  |  | Code - hand-written Dart/Flutter
AIGEN | 30 |  |  |  | Code - AI-assisted generation (Vibe)
CR | 37 |  |  |  | Code Review / Pull-Request Review
BUILD | 34.5 |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP | 36 |  |  |  | Code Inspection
UT | 35 |  |  |  | Unit Test
WT | 14 |  |  |  | Widget Test
IT | 17 |  |  |  | Build & Integration Test
CICD | 10 |  |  |  | CI/CD Pipeline (GitHub Actions)
ST | 20 |  |  |  | System Test
UAT | 8 |  |  |  | Client Acceptance Test
DOC | 16 |  |  |  | Documentation & User Manual
PM | 12 |  |  |  | Postmortem
TOTAL
Defects Injected
Phase | Plan | Actual | Actual % |  | Description
PLAN |  |  |  |  | Planning
REQ | 8 |  |  |  | Requirements / SRS
STP |  |  |  |  | System Test Plan
REQINSP |  |  |  |  | Requirements Inspection
HLD | 7 |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  |  | Integration Test Plan
HLDINSP |  |  |  |  | HLD Inspection
DLD | 12 |  |  |  | Detailed Design (screens, widgets, models)
DLDR | 2 |  |  |  | Detailed Design Review
TD |  |  |  |  | Test Development
DLDINSP |  |  |  |  | Detailed Design Inspection
CODE | 20 |  |  |  | Code - hand-written Dart/Flutter
AIGEN | 6 |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  |  | Code Inspection
UT |  |  |  |  | Unit Test
WT |  |  |  |  | Widget Test
IT |  |  |  |  | Build & Integration Test
CICD |  |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  |  | System Test
TOTAL DEVELOPMENT DEFECTS INJECTED
UAT - injected in client acceptance test
PL - injected after release
Defects Removed
Phase | Plan | Actual | Actual % |  | Description
PLAN |  |  |  |  | Planning
REQ |  |  |  |  | Requirements / SRS
STP |  |  |  |  | System Test Plan
REQINSP | 6 |  |  |  | Requirements Inspection
HLD |  |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  |  | Integration Test Plan
HLDINSP | 5 |  |  |  | HLD Inspection
DLD |  |  |  |  | Detailed Design (screens, widgets, models)
DLDR | 8 |  |  |  | Detailed Design Review
TD |  |  |  |  | Test Development
DLDINSP | 4 |  |  |  | Detailed Design Inspection
CODE |  |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  |  | Code - AI-assisted generation (Vibe)
CR | 11 |  |  |  | Code Review / Pull-Request Review
BUILD | 5 |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP | 4 |  |  |  | Code Inspection
UT | 5 |  |  |  | Unit Test
WT | 2 |  |  |  | Widget Test
IT | 1 |  |  |  | Build & Integration Test
CICD |  |  |  |  | CI/CD Pipeline (GitHub Actions)
ST | 1 |  |  |  | System Test
TOTAL DEVELOPMENT DEFECTS REMOVED
UAT - removed in client acceptance test
PL - removed after release
Summary Measures
| Plan | Actual |  |  | What it tells you
LOC per hour |  |  |  |  | Team productivity. Compare cycle to cycle, never team to team.
Cost performance index (CPI) |  |  |  |  | Planned hours over actual hours. Below 1.0 means the work cost more than planned.
Defects per KLOC (development) |  |  |  |  | Defect density in new and changed code.
Hours per defect removed |  |  |  |  | Rising cost per defect is the signal to review earlier, not test harder.
% of code that is AI-assisted |  |  |  |  | Lines kept from AI generation as a share of new and changed code.
Defects traced to AI-generated code |  |  |  |  | If this climbs, the review rule is not being applied.
Client acceptance defects |  |  |  |  | The number the client sees. The goal is zero critical.

## SUMQ
Form SUMQ - Quality Summary
Everything here is derived. If a number looks wrong, the log is wrong - fix the log, not this sheet.
Team |  |  | Cycle / milestone
Defect Density
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Defects / page - requirements inspection |  |  |  |  | Few defects per page usually means the inspection was too fast, not that the SRS was clean.
Defects / page - design inspection
Defects / KLOC - Detailed design review
Defects / KLOC - Detailed design inspection
Defects / KLOC - Code review / PR review
Defects / KLOC - Build & static analysis
Defects / KLOC - Code inspection
Defects / KLOC - Unit test
Defects / KLOC - Widget test
Defects / KLOC - Integration test
Defects / KLOC - System test
Defects / KLOC - total development
Defects / KLOC - client acceptance test |  |  | 0 |  | This is the one the client experiences. Everything upstream exists to drive it to zero.
Defect Ratios
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Design review defects / unit test defects |  |  | >= 2.0 |  | Finding design defects in test instead of review is the expensive way round.
Code review defects / build defects |  |  | >= 2.0
Development Time Ratios
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Requirements inspection / requirements |  |  | >= 0.20
Design inspection / high-level design |  |  | >= 0.20
Detailed design / code |  |  | >= 1.00
Design review / detailed design |  |  | >= 0.50
Code review / code |  |  | >= 0.50
AI generation / total coding |  |  | no target |  | Not a quality target - it tells the team how much of its coding effort is prompting rather than writing, which is worth knowing at the postmortem.
Review & Inspection Rates
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Requirements inspection (pages/hr) |  |  | <= 10 |  | Reviewing faster than the guideline reliably means defects were missed.
Design inspection (pages/hr) |  |  | <= 10 |  | Reviewing faster than the guideline reliably means defects were missed.
Detailed design review (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Detailed design inspection (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Code review (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Code inspection (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Appraisal / failure ratio (A/FR) |  |  | >= 2.0 |  | Time spent reviewing versus time spent fixing in test. Low A/FR predicts a painful system test.
Phase Yield - % of defects present that this phase caught
Measure | Plan | Actual | Guideline | Verdict | Interpretation
PLAN - Planning
REQ - Requirements / SRS
STP - System Test Plan
REQINSP - Requirements Inspection
HLD - High-Level Design / Architecture (SDD)
ITP - Integration Test Plan
HLDINSP - HLD Inspection
DLD - Detailed Design (screens, widgets, models)
DLDR - Detailed Design Review
TD - Test Development
DLDINSP - Detailed Design Inspection
CODE - Code - hand-written Dart/Flutter
AIGEN - Code - AI-assisted generation (Vibe)
CR - Code Review / Pull-Request Review
BUILD - Build & Static Analysis (flutter analyze)
CODEINSP - Code Inspection
UT - Unit Test
WT - Widget Test
IT - Build & Integration Test
CICD - CI/CD Pipeline (GitHub Actions)
ST - System Test
Process Yield - % of defects removed before entering this phase
Measure | Plan | Actual | Guideline | Verdict | Interpretation
% removed before build & static analysis |  |  | >= 70%
% removed before unit test |  |  | >= 70%
% removed before widget test |  |  | >= 85%
% removed before integration test |  |  | >= 85%
% removed before system test |  |  | >= 85%
% removed before client acceptance test |  |  | >= 95%
Test & Release Quality (feeds the Testing and Release rubric)
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Test cases recorded |  |  | >= 50 by M3
Test pass rate |  |  | >= 95%
Automated share of test cases |  |  | >= 70%
Unit tests |  |  | ~60% of cases
Widget tests |  |  | ~30% of cases
Integration tests |  |  | ~10% of cases
Code coverage reported by CI (enter manually) |  | 64% | >= 60% |  | Read from the coverage job in GitHub Actions, not estimated.
Open defects at this milestone |  |  | 0 critical |  | A defect with no fix reference is still open.

## CHARTS
Chart Gallery
Fourteen charts, redrawn from your own logs. They update themselves - there is nothing to press.
| Planned against earned, with a dashed projection at your current rate. The gap is the schedule story. | Value planned and value actually earned, week by week. Empty bars are weeks nothing finished.
| Effort against the plan. Below the line with earned value also low means the team is simply not working the hours it committed to. | The same comparison week by week. Look for the weeks that collapsed and ask what happened in them.
| Share of components that entered each phase with no defect found. Should climb towards acceptance test. | The total climbing through the process. A curve that stays flat until test is a team not reviewing.
| Where defects are actually being caught. The mass should sit left of unit test, not right of it. | The same picture normalised by code size, so cycles and components can be compared.
| Your rate against the 200 LOC/hour guideline. Above the guideline means defects were missed, whatever the review found. | Of the defects present when each phase began, the share that phase caught.
| Defects removed before reaching each test phase, against the guideline. The acceptance-test bar is the one the client experiences. | Five axes, each scored against its QPROFPARAM target. A shape that fills the pentagon is a team finding its own defects.
| Hours logged and commits made, side by side. Not an assessment - a prompt for a conversation. | Where the effort was meant to go against where it went. The phases you under-spent are usually the reviews.
Note on A3: Charts refresh when the workbook recalculates. If one looks empty, the log behind it is empty - check CHARTDATA to see which series has no numbers.

## PEER
Form PEER - Peer & Individual Evaluation
Each member rates every member including themselves, 1 to 5, against the 10 rubric categories. 50 marks.
Team |  |  |  |  | Milestone | M3
Summary - score received by each member (out of 50)
# | Member | Avg from peers | Self-rating | Peer vs self | Score /50 | Score /10 | Rank | Reading
1
2
3
4
5
6
Rating scale
| 1 Well below what the team required |  | 2 Below what the team required |  | 3 Met what the team required
| 4 Consistently met and sometimes exceeded |  | 5 Consistently exceeded
Ratings given by -> member 1
# | Category | [6 empty] | What you are judging
1 | Quantity of work | 4 | 2 | 4 | 5 | 4 |  | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | 4 | 2 | 5 | 5 | 4 |  | Meets the deadlines the team set, without being chased.
3 | Task support | 4 | 3 | 4 | 5 | 4 |  | Helps other members with their tasks when they need it.
4 | Interaction | 4 | 3 | 4 | 5 | 4 |  | Listens, accepts criticism, communicates respectfully.
5 | Attendance | 5 | 2 | 5 | 5 | 4 |  | Turns up to team and client meetings.
6 | Responsibility | 4 | 2 | 4 | 5 | 4 |  | Carries out assigned tasks and volunteers for others.
7 | Involvement | 4 | 2 | 4 | 5 | 4 |  | Takes part in discussion and brings relevant material to the team.
8 | Leadership | 4 | 3 | 4 | 5 | 3 |  | Steps up and leads when the situation calls for it.
9 | Role assignment | 4 | 2 | 4 | 5 | 4 |  | Performs the duties of the role they hold this cycle.
10 | Overall performance | 4 | 3 | 4 | 5 | 4 |  | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 2
# | Category | [6 empty] | What you are judging
1 | Quantity of work | 4 | 4 | 4 | 5 | 4 |  | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | 4 | 4 | 5 | 5 | 4 |  | Meets the deadlines the team set, without being chased.
3 | Task support | 4 | 3 | 4 | 5 | 4 |  | Helps other members with their tasks when they need it.
4 | Interaction | 4 | 4 | 4 | 5 | 4 |  | Listens, accepts criticism, communicates respectfully.
5 | Attendance | 5 | 4 | 5 | 5 | 4 |  | Turns up to team and client meetings.
6 | Responsibility | 4 | 4 | 4 | 5 | 4 |  | Carries out assigned tasks and volunteers for others.
7 | Involvement | 4 | 3 | 4 | 5 | 4 |  | Takes part in discussion and brings relevant material to the team.
8 | Leadership | 3 | 3 | 4 | 5 | 3 |  | Steps up and leads when the situation calls for it.
9 | Role assignment | 4 | 4 | 4 | 5 | 4 |  | Performs the duties of the role they hold this cycle.
10 | Overall performance | 4 | 4 | 4 | 5 | 4 |  | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 3
# | Category | [6 empty] | What you are judging
1 | Quantity of work | 4 | 2 | 4 | 5 | 4 |  | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | 4 | 2 | 5 | 5 | 4 |  | Meets the deadlines the team set, without being chased.
3 | Task support | 4 | 2 | 4 | 5 | 5 |  | Helps other members with their tasks when they need it.
4 | Interaction | 4 | 3 | 4 | 5 | 4 |  | Listens, accepts criticism, communicates respectfully.
5 | Attendance | 5 | 2 | 5 | 5 | 4 |  | Turns up to team and client meetings.
6 | Responsibility | 4 | 2 | 4 | 5 | 4 |  | Carries out assigned tasks and volunteers for others.
7 | Involvement | 4 | 2 | 4 | 5 | 4 |  | Takes part in discussion and brings relevant material to the team.
8 | Leadership | 3 | 2 | 4 | 5 | 4 |  | Steps up and leads when the situation calls for it.
9 | Role assignment | 4 | 2 | 4 | 5 | 4 |  | Performs the duties of the role they hold this cycle.
10 | Overall performance | 4 | 3 | 4 | 5 | 4 |  | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 4
# | Category | [6 empty] | What you are judging
1 | Quantity of work | 4 | 2 | 4 | 5 | 4 |  | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | 4 | 2 | 5 | 5 | 4 |  | Meets the deadlines the team set, without being chased.
3 | Task support | 4 | 2 | 4 | 5 | 4 |  | Helps other members with their tasks when they need it.
4 | Interaction | 4 | 3 | 4 | 5 | 4 |  | Listens, accepts criticism, communicates respectfully.
5 | Attendance | 5 | 2 | 5 | 5 | 4 |  | Turns up to team and client meetings.
6 | Responsibility | 4 | 2 | 4 | 4 | 4 |  | Carries out assigned tasks and volunteers for others.
7 | Involvement | 4 | 2 | 4 | 5 | 4 |  | Takes part in discussion and brings relevant material to the team.
8 | Leadership | 3 | 2 | 4 | 5 | 3 |  | Steps up and leads when the situation calls for it.
9 | Role assignment | 4 | 2 | 4 | 5 | 4 |  | Performs the duties of the role they hold this cycle.
10 | Overall performance | 4 | 3 | 4 | 5 | 4 |  | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 5
# | Category | [6 empty] | What you are judging
1 | Quantity of work | 4 | 2 | 4 | 5 | 4 |  | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | 4 | 2 | 5 | 5 | 4 |  | Meets the deadlines the team set, without being chased.
3 | Task support | 3 | 2 | 4 | 5 | 4 |  | Helps other members with their tasks when they need it.
4 | Interaction | 4 | 3 | 4 | 5 | 4 |  | Listens, accepts criticism, communicates respectfully.
5 | Attendance | 5 | 2 | 5 | 5 | 4 |  | Turns up to team and client meetings.
6 | Responsibility | 4 | 2 | 4 | 5 | 4 |  | Carries out assigned tasks and volunteers for others.
7 | Involvement | 4 | 2 | 4 | 5 | 4 |  | Takes part in discussion and brings relevant material to the team.
8 | Leadership | 2 | 2 | 4 | 5 | 4 |  | Steps up and leads when the situation calls for it.
9 | Role assignment | 4 | 2 | 4 | 5 | 4 |  | Performs the duties of the role they hold this cycle.
10 | Overall performance | 4 | 3 | 4 | 5 | 4 |  | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 6
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Note on C7: Average of the ratings this member received from the other members, out of 50. Self-rating is reported separately so it cannot inflate the score.

## TEAMEVAL
Form TEAMEVAL - Team Evaluation
Each member rates the team's dynamics 1 to 5, anonymously. Then discuss the spread, not just the mean.
Team |  |  |  |  | Milestone | M3
Team Dynamics
# | Variable | 1 <---------------------> 5 | R1 | R2 | R3 | R4 | R5 | R6 | Mean | Spread - talk about this
1 | Goals | Unclear and poorly understood ... Clear, understood, fully committed to | 4 | 4 | 4 | 5 | 4
2 | Openness | Members are guarded in discussion ... Members speak freely | 4 | 4 | 4 | 4 | 3
3 | Mutual trust | Members are suspicious of each other ... Members trust each other | 4 | 5 | 4 | 5 | 4
4 | Attitudes toward difference | Conflict is smoothed over or avoided ... Differences are voiced and worked through | 3 | 3 | 4 | 4 | 3
5 | Support | Reluctant to ask for or give help ... Comfortable giving and receiving help | 4 | 4 | 4 | 5 | 4
6 | Participation | A few members dominate ... Everyone is involved | 2 | 3 | 2 | 4 | 2
7 | Decision-making | Decided by a few ... Everyone is involved in deciding | 3 | 3 | 4 | 4 | 3
8 | Flexibility | Locked into rules that are hard to change ... Procedures change as situations change | 4 | 4 | 4 | 4 | 4
9 | Use of member resources | Abilities and knowledge are under-used ... Every member's ability is fully used | 2 | 5 | 3 | 4 | 2
10 | Overall team performance | Falls well short of requirements ... Consistently exceeds requirements | 4 | 3 | 4 | 4 | 3
TOTAL /50
Team score /10
Agreed actions from this evaluation
1 | Rebalance the work: no member above 30% or below 12% of logged hours by M4 | [7 empty] | Aisyah Binti Rahman | 2026-12-10
2 | Everyone logs time the same day; the Team Leader checks LOGT every Wednesday | [7 empty] | Mei Ling Chong | 2026-11-25
3 | Rotate who chairs the weekly meeting so the same two people stop deciding everything | [7 empty] | Aisyah Binti Rahman | 2026-12-03
4 | Ask Daniel what he actually wants to own - the current split was assumed, not agreed | [7 empty] | Harith Bin Ismail | 2026-11-25

## ASSESS
Assessment Tracker
The official weighting for TMA3084, with the forms that produce the evidence.
Team |  |  |  | Member (for the individual components) |  |  | Harith Bin Ismail
Components
Group | Component | Rubric | Weight | Raw | Out of | Weighted | Evidence lives in | Notes
Final Project (60%) | Proposal & Planning | 1_RUBRIC_Proposal (10%) | 10% | 8 | 10 |  | STRAT, TASK, SCHEDULE, LOGCLIENT | Strong objectives; pitch ran 30 s over
Final Project (60%) | Requirement Specification | 2_RUBRIC_RequirementSpec (15%) | 15% | 12 | 15 |  | SUMS (SRS pages), LOGCLIENT, CCR | AI element well justified; some requirements still vague on pricing
Final Project (60%) | Project Evaluation - Design & Implementation | 3_RUBRIC_ProjectEvaluation (25%) | 25% | 20 | 25 |  | SUMS, SUMP, LOGAI, LOGGIT | Architecture sound; alternatives thinly argued
Final Project (60%) | Testing and Release | 8_RUBRIC_Testing_and_Release (10%) | 10% | 8 | 10 |  | LOGTEST, SUMQ, LOGD, LOGGIT | Good coverage and CI; demo handled questions well
Oral Commitment (10%) | Presentation | 4_RUBRIC_Presentation (10%) | 10% | 16 | 20 |  | Slides, demo video | Clear slides, confident delivery, finished on time
Practical Exam (30%) | Peer / Individual Evaluation | 5_RUBRIC_Peer_IndividualEvaluation (10%) | 10% |  | 50 |  | PEER
Practical Exam (30%) | Project Evaluation | 6_RUBRIC_ProjectEvaluation (10%) | 10% | 42 | 50 |  | WEEK, IRTL, TASK | Consistent weekly tracking; contribution imbalance handled openly
Practical Exam (30%) | Team Evaluation | 7_RUBRIC_TeamEvaluation (10%) | 10% |  | 50 |  | TEAMEVAL
TOTAL
Note
Raw marks are entered by the instructor or demonstrator against the published rubrics. Peer/Individual and Team Evaluation read straight from the PEER and TEAMEVAL forms, so the team can see where it stands before the mark is finalised. This sheet is a tracker, not the official record of marks.

## DASHBOARD
Team Dashboard
Everything here is read from the logs. It is only as honest as the data the team puts in.
Team |  |  |  | Generated
Milestone Readiness (cumulative actual vs the threshold on SETUP)
Measure | M1 | M2 | M3 | M4 |  |  |  | Reading
Commits | [7 empty] | Green means the cumulative figure has reached the threshold for that milestone.
PRs merged
Client meetings
LOGAI entries
Test cases
Team hours
Effort & Schedule
Measure | Plan | Actual | Ratio | Verdict |  |  |  | Reading
Total hours
Tasks complete
Earned value to date
Cost performance index
Quality
Measure | Value | Target | Verdict |  |  |  |  | Reading
Defects recorded
Defects / KLOC (development)
% removed before unit test |  | 70% | [5 empty] | Defects caught before test cost a fraction of defects caught in test.
Test pass rate |  | 95%
Code coverage |  | 60%
Defects from AI-generated code | [7 empty] | Rising count means AI output is reaching the repository without real review.
AI entries without a reviewer |  | 0 | [5 empty] | Any row here breaks the review rule - fix before the milestone.
Open issues & risks
Contribution (the free-rider check)
Member | Hours | Share | Commits | PRs merged | Reviews | LOGAI | Peer /50 | Reading

## PHASES
Process Phase Standard
The phases you may enter in LOGT, LOGD and TASK. Use the code exactly as it appears here.
Code | Phase | Scope | Log time | Log injected | Log removed | Counts as development | Size basis | What belongs in this phase
MGMT | Management & Miscellaneous | S | Y | N | N | N | - | Team admin, lab attendance, instructor and demonstrator check-ins, anything not project work.
STRAT | Launch & Strategy | S | Y | N | N | N | - | The launch meeting, cycle strategy, build-versus-reuse and technology decisions.
PLAN | Planning | S | Y | Y | Y | Y | - | Producing TASK and SCHEDULE, estimating, re-planning after a change request.
REQ | Requirements / SRS | S | Y | Y | Y | Y | Pages | Interviews with the client, user stories, use cases, writing and revising the SRS.
STP | System Test Plan | S | Y | Y | Y | Y | - | Writing the system test plan against the requirements.
REQINSP | Requirements Inspection | S | Y | Y | Y | Y | Pages | Team inspection of the SRS. Log the time you spend inspecting, not preparing.
HLD | High-Level Design / Architecture (SDD) | S | Y | Y | Y | Y | Pages | Architecture, component breakdown, data model, writing the SDD.
ITP | Integration Test Plan | S | Y | Y | Y | Y | - | Writing the integration test plan.
HLDINSP | HLD Inspection | S | Y | Y | Y | Y | Pages | Team inspection of the SDD.
DLD | Detailed Design (screens, widgets, models) | P | Y | Y | Y | Y | LOC | Designing a specific screen, widget, service or model before writing it.
DLDR | Detailed Design Review | P | Y | Y | Y | Y | LOC | Your own review of your detailed design, before anyone else sees it.
TD | Test Development | P | Y | Y | Y | Y | - | Writing test cases - the writing, not the running.
DLDINSP | Detailed Design Inspection | P | Y | Y | Y | Y | LOC | Team inspection of a detailed design.
CODE | Code - hand-written Dart/Flutter | P | Y | Y | Y | Y | LOC | Dart and Flutter you wrote yourself, keyboard to screen.
AIGEN | Code - AI-assisted generation (Vibe) | P | Y | Y | Y | Y | LOC | Prompting a generator and shaping its output. Every AIGEN session needs a LOGAI row.
CR | Code Review / Pull-Request Review | P | Y | Y | Y | Y | LOC | Reviewing someone's pull request, or them reviewing yours. Log it as CR either way.
BUILD | Build & Static Analysis (flutter analyze) | P | Y | Y | Y | Y | LOC | flutter analyze, flutter build, fixing what they report, dependency and signing problems.
CODEINSP | Code Inspection | P | Y | Y | Y | Y | LOC | Team code inspection - several people reading the same code together.
UT | Unit Test | P | Y | Y | Y | Y | LOC | Running and fixing unit tests.
WT | Widget Test | P | Y | Y | Y | Y | LOC | Running and fixing Flutter widget tests.
IT | Build & Integration Test | S | Y | Y | Y | Y | LOC | Building the whole app and testing components together.
CICD | CI/CD Pipeline (GitHub Actions) | S | Y | Y | Y | Y | - | GitHub Actions workflows, the coverage job, release automation.
ST | System Test | S | Y | Y | Y | Y | LOC | Testing the finished app against the SRS, end to end.
UAT | Client Acceptance Test | S | Y | Y | Y | N | LOC | The client or their staff using the app and telling you what is wrong.
DOC | Documentation & User Manual | S | Y | N | N | N | Pages | User manual, final report, API documentation, deployment guide.
PM | Postmortem | S | Y | N | N | N | - | The postmortem: reading your own data and agreeing what changes next cycle.
PL | Product Life (post-release) | N | N | Y | Y | N | LOC | Anything after the release is handed over.
Reading the columns
Scope: S = the phase applies to the system as a whole. P = it applies to one component. N = neither.
Log time: Y means sessions in this phase belong in LOGT.
Log injected / removed: Y means LOGD may name this phase in the Injected in or Removed in column.
Counts as development: Y means the phase feeds the development defect totals on SUMP and the yields on SUMQ.
Size basis: what the phase's rate is measured against when SUMQ computes review rates.

## DEFECTTYPES
Defect Type Standard
The types you may choose in LOGD. Types 10-100 are the TSP standard; 110-150 were added for this course.
Type | Name | What it covers | A Flutter example
10 | Documentation | Comments, README, API docs, user manual | A widget's doc comment describes the old behaviour after a refactor.
20 | Syntax | Dart syntax, spelling, punctuation, typos | Missing semicolon, misspelled identifier, wrong bracket.
30 | Build / Package | pubspec, dependency conflict, Gradle, signing, build config | pubspec version conflict; Gradle or signing config breaks the release build.
40 | Assignment | Declaration, duplicate names, scope, null-safety misuse | A nullable field used without a null check; two widgets sharing a class name.
50 | Interface | Procedure calls, REST/API contract, parameters, serialization | A repository returns a List where the caller awaits a Stream; JSON key mismatch.
60 | Checking | Error messages, input validation, inadequate checks | No validation on a quantity field; an empty list shows a spinner forever.
70 | Data | Structure, content, persistence, local DB / Firestore schema | Dates stored local but compared as UTC; a schema missing a sync-status column.
80 | Function | Logic, pointers, loops, recursion, computation, business rules | A total recalculated on add but not on edit; discount applied before tax.
90 | System | Configuration, timing, memory, platform (iOS/Android) differences | Works on Android, fails on iOS; a timing problem only under slow network.
100 | Environment | Design, compile, test or other support system problems | The emulator, the CI runner or the toolchain itself is the problem.
110 | UI / Layout | Overflow, responsiveness, theming, accessibility, Material 3 misuse | RenderFlex overflow on a small screen; text unreadable at the counter's font setting.
120 | State Management | Provider/Riverpod/GetX misuse, rebuild storms, stale or lost state | setState after dispose; a filter that does not clear when a screen is reopened.
130 | Performance | Jank, frame drops, oversized images, unbounded list builds | A long list janks; an oversized image decoded on every rebuild.
140 | Security | Hard-coded API key, missing auth check, unsafe storage, leaked PII | An API key committed in source; a screen reachable without an auth check.
150 | AI-Generated | Defect traced to AI-generated code that passed review unverified | Generated code that passed review but was wrong - a validator accepting negatives.
Choosing a type
Pick the type that describes the mistake, not the symptom. A crash caused by a missing null check is Assignment, not System. If a defect genuinely spans two types, choose the earlier one in the list - that is where the fix belongs. Type 150 is for a defect that reached the repository inside generated code: use it alongside the From AI code column in LOGD, because together they show whether the review rule is working.

## PLANGUIDE
Planning Guidelines
Use these only until you have your own data. After the first cycle, your own numbers beat any guideline.
Before you have any data
| The first plan is a guess | Your first cycle has no history, so the estimates below are a starting point, not a standard. Record what actually happens and the second plan will be built on your own numbers instead of someone else's.
| Effort per member | Budget about 10 hours per member per week across a 13-week semester. For a five-person team that is roughly 600 team-hours for the whole project. If your plan totals far more than that, you are planning work the team cannot do.
| Task size | Break work into tasks of 2 to 10 hours. Anything larger hides its own progress - you cannot tell a 20-hour task that is half done from one that has barely started.
Splitting the effort across phases
| Rough shape of a cycle | Requirements and design together should be about a third of the effort, implementation about a third, and test, documentation and management the rest. A plan that spends 70% on coding is a plan that will spend its last three weeks in test.
| Phase group | Share of cycle effort | Guide
| Launch, strategy and planning | 8% | STRAT + PLAN + MGMT
| Requirements and inspection | 14% | REQ + REQINSP + STP
| Architecture and inspection | 12% | HLD + HLDINSP + ITP
| Detailed design and review | 16% | DLD + DLDR + DLDINSP
| Implementation | 22% | CODE + AIGEN
| Review and inspection of code | 10% | CR + CODEINSP
| Test development and testing | 13% | TD + BUILD + UT + WT + IT + ST
| CI/CD and release | 2% | CICD
| Documentation and postmortem | 3% | DOC + PM
Rates to plan against
| Activity | Planning rate | Why this number
| Writing requirements | 2 - 4 SRS pages per hour | Includes the thinking, not just the typing.
| Requirements inspection | no faster than 10 pages per hour | Faster than this and you stop finding defects.
| Writing a design | 3 - 5 SDD pages per hour | Diagrams take longer than prose.
| Design inspection | no faster than 10 pages per hour | Same reason as the SRS.
| Writing Dart by hand | 20 - 40 LOC per hour | New and changed lines, including the thinking.
| AI-assisted generation | 60 - 120 LOC per hour kept | Faster to produce, but the review is the real cost.
| Design or code review | no faster than 200 LOC per hour | The single most reliable number in TSP.
| Writing test cases | 4 - 8 cases per hour | A case is a scenario, not a line of code.
A warning about the AI rate
Generated code arrives faster than written code, and teams plan as though that speed carries through to delivery. It does not. The generator moves the work from writing to reviewing, and a team that plans for the first saving without planning for the second cost finds its defects in system test instead of in review. Plan AIGEN at a high rate and plan CR high to match it.

## QUALGUIDE
Quality Guidelines
What good looks like on each SUMQ measure, and what it means when yours is below it.
The idea behind all of it
A defect costs more the later you find it. One caught in a design review costs minutes; the same defect caught in system test costs hours; caught by the client it costs their trust. Every measure on SUMQ exists to answer one question: are you finding your defects early, or is the machine finding them for you late?
| Measure | Aim for | If yours is below it
| Review rate | <= 200 LOC/hour | You read too fast to find anything. The rate, not the hours, is what predicts how many defects a review catches - halve the rate before you add more reviewers.
| Inspection rate | <= 10 pages/hour | Same problem on documents. An SRS inspection at 30 pages an hour finds typos, not missing requirements.
| A/FR (appraisal / failure) | >= 2.0 | You are spending more time fixing in test than reviewing before it. This is the earliest reliable warning that system test will hurt.
| Design review / design time | >= 0.5 | Designs are going to code unreviewed. Defects injected in design are the expensive ones - they survive until integration.
| Code review / code time | >= 0.5 | Code is being merged on a glance. With AI-generated code in the repository this matters more, not less.
| Design time / code time | >= 1.0 | The team is typing before it is thinking. Expect rework.
| Yield before unit test | >= 70% | Most of your defects are reaching test. Each one there costs several times what it would have cost in review.
| Yield before system test | >= 85% | Integration will be slow and unpredictable, because you are still finding unit-level defects there.
| Yield before acceptance test | >= 95% | The client is about to become your tester. This is the number that decides whether handover goes well.
| Defects / KLOC in test | falling each cycle | The absolute number matters less than the direction. A team whose test density rises cycle over cycle is reviewing less, not writing better.
| Defects found in acceptance | 0 critical | Anything critical here was missed by every check you have. Work backwards and find which one.
| Code coverage | >= 60% on logic | Untested logic is not working logic, it is logic nobody has contradicted yet.
| Test pass rate | >= 95% | A suite that is often red stops being read. Fix or delete failing tests - never ignore them.
| AI entries without a reviewer | 0 | Every one of these is generated code merged on trust. This is the single rule most worth enforcing.
The order to fix things in
If several measures are red, fix them in this order: review rate first, because it is the cheapest change and it moves everything downstream; then design review time, because design defects are the costly ones; then coverage. Do not start by adding testers - testing finds defects later and more expensively than reviewing does, and a team that responds to poor quality by testing harder is paying the highest price available for the same information.

## QPROFPARAM
Quality Profile Parameters
The five targets behind the Quality Profile chart. Change them only if your instructor says so.
# | Parameter | Target | What it means | Direction
1 | Design / code time | 1 | Time in detailed design as a multiple of time spent coding. TSP says good work spends at least as long designing as typing. | higher is better
2 | Design review time | 0.5 | Time reviewing your own design as a fraction of design time. | higher is better
3 | Code review time | 0.5 | Time in code and pull-request review as a fraction of coding time. | higher is better
4 | Build defects / KLOC | 10 | Defects found by flutter analyze and the build, per thousand new and changed lines. | lower is better
5 | Unit test defects / KLOC | 5 | Defects found in unit test per thousand new and changed lines. | lower is better
How the profile is scored
Each axis is scored from 0 to 1, where 1 means the target was met. For the first three, the score is your value divided by the target, capped at 1. For the two defect densities it is the target divided by your value, capped at 1, because fewer defects is better. A profile that reaches the edge on all five axes is a team reviewing enough to find its own defects before the machine does.

## CHARTDATA
Chart Data
Every chart on PROJECT and CHARTS reads from here. Calculated - never type in this sheet.
Current week (last week with logged hours) |  |  |  | Weeks worked |  |  | EV earned to date |  |  | EV rate / week
A. Weekly series (earned value and hours)
Week | Plan hrs | Cum plan hrs | Actual hrs | Cum actual hrs | Plan value | Cum planned value | Earned value | Cum earned value | Cum predicted EV
3
4
5
6
7
8
9
10
11
12
13
14
15
B. By development phase (defects, density, yield, time)
Phase | Injected | Removed | Cum removed | Defects / KLOC | Phase yield | Plan hrs | Actual hrs
PLAN
REQ
STP
REQINSP
HLD
ITP
HLDINSP
DLD
DLDR
TD
DLDINSP
CODE
AIGEN
CR
BUILD
CODEINSP
UT
WT
IT
CICD
ST
C. Review and inspection rates (LOC per hour, guideline 200)
Review | Actual rate | Guideline
Design review
Design inspection
Code / PR review
Code inspection
D. Process yield (% of defects removed before entering the phase)
Before | Process yield | Guideline
Build
Unit test
Widget test
Integration test
System test
Acceptance test
E. Percent defect free (share of components with no defect found in that phase)
Component | Build | Unit test | Integration test | System test | Acceptance test
% defect free
E2. Percent defect free by phase (chart series)
Phase | % defect free
Build
Unit test
Integration test
System test
Acceptance test
F. Quality profile (five axes normalised against QPROFPARAM, 1.0 is the target)
Axis | Actual | Target
Design / code time
Design review time
Code review time
Build defect density
Unit test defect density
G. Contribution by member
Member | Hours | Commits | AI entries

## LISTS
Validation Lists
Source lists for every drop-down in this workbook. Edit only the Roles and Size Measure columns.
Phase Code | Phase Description | Defect Type | Milestone | Role | Size Measure | AI Tool | Team Member | Yes/No | Status | Week | Test Type | Severity | Issue or Risk | Priority | Meeting Mode | Task Status | Review Verdict | Change Type | Component Type
MGMT | Management & Miscellaneous | 10 - Documentation | M1 | Team Leader | Dart LOC | GitHub Copilot |  | Yes | Not started | 3 | Unit | Critical | Risk | High | Face-to-face | Planned | Approved | Requirement | Assembly
STRAT | Launch & Strategy | 20 - Syntax | M2 | Product Owner | Screens | Claude |  | No | In progress | 4 | Widget | Major | Issue | Medium | Online (Zoom/Meet) | In progress | Approved with changes | Design | Part
PLAN | Planning | 30 - Build / Package | M3 | Development Manager | Widgets | ChatGPT / GPT-4 |  |  | Blocked | 5 | Integration | Minor |  | Low | Phone | Complete | Changes requested | Code
REQ | Requirements / SRS | 40 - Assignment | M4 | Planning Manager | API Endpoints | Google Gemini |  |  | Complete | 6 | Manual | Cosmetic |  |  | Email / async | Carried over | Rejected | Test
STP | System Test Plan | 50 - Interface |  | Quality & Test Manager | Test Cases | Cursor |  |  | Dropped | 7 | Acceptance |  |  |  |  | Cancelled | Pending | Document
REQINSP | Requirements Inspection | 60 - Checking |  | Support Manager | SRS Pages | Other |  |  |  | 8 | Regression | [6 empty] | Build / CI
HLD | High-Level Design / Architecture (SDD) | 70 - Data |  |  | SDD Pages | None |  |  |  | 9 | Performance
ITP | Integration Test Plan | 80 - Function |  |  | Documents |  |  |  |  | 10 | Security
HLDINSP | HLD Inspection | 90 - System | [7 empty] | 11
DLD | Detailed Design (screens, widgets, models) | 100 - Environment | [7 empty] | 12
DLDR | Detailed Design Review | 110 - UI / Layout | [7 empty] | 13
TD | Test Development | 120 - State Management | [7 empty] | 14
DLDINSP | Detailed Design Inspection | 130 - Performance | [7 empty] | 15
CODE | Code - hand-written Dart/Flutter | 140 - Security
AIGEN | Code - AI-assisted generation (Vibe) | 150 - AI-Generated
CR | Code Review / Pull-Request Review
BUILD | Build & Static Analysis (flutter analyze)
CODEINSP | Code Inspection
UT | Unit Test
WT | Widget Test
IT | Build & Integration Test
CICD | CI/CD Pipeline (GitHub Actions)
ST | System Test
UAT | Client Acceptance Test
DOC | Documentation & User Manual
PM | Postmortem
PL | Product Life (post-release)