## README
TSPi Team Workbook - TMA3084 Software Engineering Laboratory
Faculty of Computer Science & Information Technology, UNIMAS ¦ Semester 1, Session 2026/2027 ¦ Workbook v3.0 (2026-10-29)
| What this is | A Team Software Process (TSP) team workbook rebuilt for TMA3084. It keeps the TSP measurement discipline - time, defects, size, earned value - and adds the forms this course actually assesses: AI-assisted coding, automated testing, GitHub workflow, client engagement and peer evaluation.
| Lineage | The process model follows the Team Software Process introduced by Watts S. Humphrey. The original TSPi support workbook (2002, Addison-Wesley) is the ancestor of this file; every sheet here has been rewritten for this course. Forms, phases, defect types and all guidance text are original to TMA3084.
| What changed from the 2002 workbook | NEW forms: LOGAI (AI-assisted development), LOGTEST (test cases), LOGCLIENT (client meetings), LOGGIT (GitHub activity), CCR (change requests), PEER, TEAMEVAL, ASSESS, DASHBOARD, FORM-SI. MODERNISED: phase set now covers AI generation, pull-request review, static analysis, widget test and CI/CD; defect types extended with UI/Layout, State Management, Performance, Security and AI-Generated; size measures cover screens, widgets and API endpoints alongside LOC. REMOVED: the single-week WEEK form is now a 13-week tracking table, and the PSP-style prediction intervals are dropped as the team has no historical data base.
| Colour convention | AMBER cells are yours to fill in. GREY cells are calculated - typing over one destroys the rollup. Every drop-down is fed by the LISTS sheet.
| How to run it | 1. Fill SETUP once, then FORM-SI with every member. 2. Agree roles in ROLES and goals in GOALS. 3. Plan each cycle in TASK and SCHEDULE. 4. Record daily in LOGT, LOGD, LOGTEST and LOGAI. 5. Hold the weekly meeting against WEEK and IRTL. 6. SUMP, SUMQ, SUMS and DASHBOARD fill themselves.
| One workbook per team | The team keeps one shared copy in the repository (docs/tspi/). Each member records their own rows in the logs and tags them with their name, so individual contribution is traceable without separate files.
| Honesty clause | These numbers are the evidence behind Peer/Individual and Team Evaluation. Logging work you did not do, or back-filling a term's worth of hours the night before a milestone, is academic dishonesty and the pattern is visible in DASHBOARD.
Milestones
| Milestone | Week / Due | Deliverables
| M1 Proposal & Planning (10%) | Week 5 - due 25 Oct 2026 ¦ Proposal, SRS draft, GitHub repo, Team Charter, client approval, >=2 client meetings
| M2 Requirements & Design (15%) | Week 9 - due 20 Nov 2026 ¦ Revised SRS, SDD, Flutter prototype (4-5 screens), >=10 LOGAI entries, test plan (>=20 cases), >=4 client meetings
| M3 Implementation & Testing (35%) | Week 13 - due 20 Dec 2026 ¦ Final SDD, >=50 tests at >=60% coverage, GitHub Actions green, APK/IPA build, >=6 client meetings
| M4 Release & Oral Commitment (40%) | Week 15 - due 02 Jan 2027 ¦ Final report, user manual, demo video 5-10 min, presentation, client sign-off, v1.0.0 release

## MANUAL
How to Use This Workbook
TMA3084 Software Engineering Laboratory - a step-by-step manual for the team. Read this once, together, at the launch meeting.
1. What this workbook is
| The short version | This is a Team Software Process (TSP) workbook. TSP is a way of running a software project where the team plans its own work, measures what actually happens, and uses those measurements to plan better next time. The workbook is where the measuring happens.
| Why bother | Three questions decide most student projects: are we going to finish on time, is the thing we are building any good, and is everyone actually contributing. Opinions on all three are usually wrong. This workbook answers them with data the team collected itself.
| The four things you record | TIME - how long work actually took, not how long it felt. SIZE - how much you built. DEFECTS - every mistake found, and the phase where it was made. STATUS - which tasks are finished. Everything else on the summary sheets is arithmetic on those four.
| What it is not | It is not a surveillance tool and it is not graded on neatness. Nobody is marked down for a high defect count - a team recording 40 defects is doing better engineering than an identical team recording 3, because the second team is not looking. What does get noticed is a log that is empty, or one filled in all at once the night before a milestone.
2. Before you start - conventions
| Convention | What it means
| Amber cells | You type here. Everything the team knows goes into an amber cell.
| Grey cells | Calculated. Typing over one breaks the rollups that depend on it - if a grey number looks wrong, the log feeding it is wrong, so fix the log.
| Drop-downs | Fed by the LISTS sheet. Member names come from FORM-SI, so fill FORM-SI first or every name drop-down in the workbook will be empty.
| Red / amber / green | Applied automatically. Red is not a punishment, it is a prompt to talk about something at the next meeting.
| Hover for help | Cells with a small red corner marker carry a note explaining what goes in them.
| Reference sheets | PHASES and DEFECTTYPES are the standards you code against - read them in Week 1. PLANGUIDE and QUALGUIDE tell you what to aim for. None of the four should ever be edited.
| Charts | PROJECT and CHARTS draw themselves from the logs. There is no Draw button and nothing to refresh - if a chart is empty, the log behind it is empty.
3. Stage one - the launch (do this in Week 1, and again at the start of every cycle)
# | Step | What to do | Form | Who / when
1 | Fill in SETUP | Course details, team name, project title, client, repository URL and team size. Then check the milestone dates against the course outline and set the thresholds. Every other sheet reads its header from here, so this is the one place you type the team name. | SETUP | Team Leader, Week 1
2 | Enter every member | One row per member in FORM-SI: matric number, full name, UNIMAS email, GitHub handle. The name you type here is the name that appears in every drop-down, so agree on a spelling and do not change it later. | FORM-SI | All members, Week 1
3 | Write the team charter | The lower half of FORM-SI. Six short answers: vision, communication norms, definition of done, conflict resolution, quality standards, expected hours. Write these before you disagree about them, not after. | FORM-SI | Team, Week 1
4 | Assign roles | There are six roles and five of you, so one member holds two this cycle and nobody holds more than two. The double rotates, and nobody keeps the same role for more than two milestones running. The Role Load Check at the bottom of the sheet adds this up for you. A role is real work, not a title. | ROLES | Team Leader, each launch
5 | Set measurable goals | A goal needs a number and an owner or it is a wish. Seven starter goals are listed at the bottom of the sheet; replace them with your own. | GOALS | Team, each launch
6 | Agree the strategy | What each cycle actually delivers, what you build versus reuse, the main technical risk and who owns it. Then record the stack decisions and why - the Design rubric asks you to justify alternatives considered. | STRAT | Dev Manager, each launch
7 | Size what you are building | List the screens, modules and documents in SUMS with a planned size. Estimates will be wrong early on. Record them anyway - a wrong estimate you measured against is worth more than no estimate. | SUMS | Planning Manager
8 | Break the work into tasks | Tasks of roughly 2 to 10 hours, each with one owner, a phase, planned hours and a planned week. A task bigger than 10 hours is hiding something. | TASK | Planning Manager
9 | Spread it across the weeks | Put the hours each week in SCHEDULE. Check the Difference cell at the top: schedule hours must match task hours. If they do not, one of the two plans is fiction. | SCHEDULE | Planning Manager
4. Stage two - daily discipline (the habit that makes everything else work)
# | Step | What to do | Form | Who / when
10 | Log time as you work | Start a LOGT row when you sit down, fill in the stop time when you get up. Subtract interruptions honestly. Reconstructing a week of hours from memory produces numbers that are worse than useless, because they look real. | LOGT | Every member, daily
11 | Tag the task | Put the Task ID from TASK in the Task ID column. That is what makes hours roll up against the plan. Unplanned work with no ID is fine - add the task to TASK afterwards so the plan stays honest. | LOGT | Every member, daily
12 | Log every defect | Anything wrong that you had to fix, including the ones you found yourself within a minute. The hard column is Injected in: the phase where the mistake was MADE, not where you noticed it. Getting that right is the whole point. | LOGD | Every member, daily
13 | Log every test | One row per test case with its type and status. Automated tests get a row too - LOGTEST is the evidence behind the Testing and Release rubric, not a duplicate of your test files. | LOGTEST | Quality & Test Manager, daily
14 | Log every AI-assisted change | Any time Copilot, Claude or another generator wrote code that reached the repository: what you asked for, how many lines it gave you, how many survived review, who reviewed it, and whether tests were written. The reviewer must not be you - the sheet turns that row red. | LOGAI | Every member, each change
15 | Record client meetings | Date, mode, who attended, what was decided, what actions came out and who owns them. Keep the minutes or a photo as evidence. The milestones require 2, 4 and 6 cumulative meetings - this is how you prove it. | LOGCLIENT | Product Owner
5. Stage three - the weekly meeting (about 30 minutes, same time every week)
# | Step | What to do | Form | Who / when
16 | Pull the GitHub numbers | Commits, pull requests, reviews and issues closed per member, read from the repository Insights tab. These are facts - do not estimate them. | LOGGIT | Support Manager, weekly
17 | Update task status | Mark finished tasks Complete. Earned value is only credited for completed tasks; a task that is 90% done earns nothing. That is deliberate - it is what stops a plan from slipping quietly. | TASK | Planning Manager, weekly
18 | Read the week's numbers | WEEK fills itself from SCHEDULE. Look at EV variance: negative means the team has delivered less than it planned by this week, however many hours it has burned. Hours are effort; earned value is progress. | WEEK | Team Leader, weekly
19 | Raise risks and issues | A risk might happen, an issue already has. Both need a likelihood, an impact, an owner and a follow-up date. Priority is calculated; anything scoring 6 or more goes red and gets discussed. | IRTL | Team Leader, weekly
20 | Handle change requests | Once the client has agreed a baseline, changes go through CCR with an estimate and a decision - not through a quiet commit. This is also how scope creep becomes visible instead of mysterious. | CCR | Support Manager, as needed
21 | Check the dashboard | Milestone readiness, effort, quality and contribution on one screen. Anything red is the agenda for the next ten minutes. | DASHBOARD | Team, weekly
22 | Talk about contribution | The contribution panel compares each member's hours, commits, reviews and AI entries against an even share. A flag is a prompt for a conversation, not an accusation - someone may be carrying work the logs do not capture, and if so, that is worth knowing too. | DASHBOARD | Team, weekly
23 | Write next week's commitment | One line in WEEK saying what the team will have finished by the next meeting. Then check it at that meeting. This single habit does more for delivery than any tool. | WEEK | Team Leader, weekly
6. Stage four - closing a milestone (the postmortem)
# | Step | What to do | Form | Who / when
24 | Record actual sizes | Go back to SUMS and fill the actual columns, plus actual SRS and SDD pages. Without actual size there is no defect density and no productivity figure. | SUMS | Planning Manager
25 | Check the plan summary | SUMP now shows where the time went, where defects were injected and where they were removed. Compare the Actual % column against your plan. The gap between them is the lesson. | SUMP | Planning Manager
26 | Read the quality summary | SUMQ is where the uncomfortable truths live: review rates that were too fast, A/FR below 2.0, process yield under 70%. Each one predicts a specific kind of pain in the next cycle. | SUMQ | Quality & Test Manager
27 | Enter the coverage figure | One manual cell on SUMQ, read from the coverage job in GitHub Actions. Do not estimate it. | SUMQ | Quality & Test Manager
28 | Run the peer evaluation | Each member rates every member including themselves, 1 to 5, across the 10 rubric categories. Self-ratings are reported separately so they cannot inflate anyone's score. Rate what people did, not whether you like them. | PEER | All members, each milestone
29 | Run the team evaluation | Ten statements about how the team works, rated 1 to 5. Then look at the spread, not just the mean - where members disagree sharply is the thing worth discussing. Agree actions at the bottom of the sheet. | TEAMEVAL | All members, each milestone
30 | Update the assessment tracker | ASSESS maps every rubric to the forms that produce its evidence. Peer and Team Evaluation fill themselves; the rest are entered by the instructor. | ASSESS | Team Leader
31 | Look at the charts together | Open CHARTS and read them as a team. The four that matter most are Cumulative Earned Value (did we deliver what we planned), Defects Removed by Phase (are we catching them early), Review Rates (did we read fast enough to miss things) and Process Yield (what reached test). A number on a sheet is arguable; a line going the wrong way for six weeks is not. | CHARTS | Team, each milestone
32 | Agree three changes | Not twenty. Pick three things the team will do differently next cycle, write them into GOALS with an owner, and check them at the next postmortem. A postmortem that changes nothing was just a meeting. | GOALS | Team, each milestone
7. Every form, and what it is for
| Form | What it holds | Who owns it | Feeds into
| SETUP | Course, team, client, repository, milestone plan and the thresholds that drive the dashboard traffic lights. | Team Leader | Every sheet header, DASHBOARD
| FORM-SI | Member details, the team charter, and each member's planned versus actual hours with a contribution flag. | All members | Every name drop-down, DASHBOARD
| ROLES | Which of the six TSP roles each member holds in each milestone, what that role owns, and a check that nobody is carrying more than two. | Team Leader | -
| GOALS | Measurable team goals with a target, an owner and a review date. | Team | -
| STRAT | What each cycle delivers, build-versus-reuse decisions, technical risks, and the technology stack with justification. | Dev Manager | Design rubric evidence
| TASK | Every task with owner, phase, estimate, planned week, status and earned value. Actual hours arrive automatically from LOGT. | Planning Manager | SCHEDULE, WEEK, FORM-SI, DASHBOARD
| SCHEDULE | Planned hours per week from Week 3 to Week 15, against actual hours and earned value. | Planning Manager | WEEK, DASHBOARD
| LOGT | One row per working session: date, member, phase, task, start, stop and interruptions. The single most important sheet in the workbook. | Every member | TASK, SCHEDULE, SUMP, SUMQ, FORM-SI, DASHBOARD
| LOGD | Every defect found: type, component, the phase it was injected in, the phase it was removed in, fix time, severity, and whether it came from AI-generated code. | Every member | SUMP, SUMQ, DASHBOARD
| LOGTEST | Every test case with type, expected and actual result, status, tester and whether it is automated. | Quality & Test Manager | SUMQ, DASHBOARD
| LOGAI | Every AI-assisted change: tool, prompt, lines generated, lines kept, reviewer, verdict and test status. Self-review is flagged red. | Every member | SUMP, DASHBOARD
| LOGCLIENT | Client meetings with mode, attendees, decisions, actions and sign-off evidence. | Product Owner | DASHBOARD milestone readiness
| LOGGIT | Weekly commits, pull requests, reviews and issues per member, read from GitHub Insights. | Support Manager | DASHBOARD contribution panel
| WEEK | The weekly status record: hours, earned value, variance, risk and next week's commitment. | Team Leader | -
| IRTL | Risks and issues with likelihood, impact, calculated priority, owner and follow-up date. | Team Leader | DASHBOARD
| CCR | Change requests against an agreed baseline, with estimated impact and a recorded decision. | Support Manager | -
| SUMS | Planned and actual size of every component and document - LOC, screens, widgets, pages. | Planning Manager | SUMP, SUMQ
| SUMP | Size, time in each phase, and defects injected and removed by phase. Plan columns are typed; actual columns read themselves out of the logs. | Planning Manager | SUMQ, DASHBOARD
| SUMQ | Defect density, defect ratios, development time ratios, review rates, A/FR, phase yield, process yield and test quality - each against a guideline with a verdict. | Quality & Test Manager | DASHBOARD
| PEER | Peer and individual evaluation: every member rates every member on 10 categories out of 50, with self-ratings reported separately. | All members | ASSESS, DASHBOARD
| TEAMEVAL | Team dynamics across 10 variables rated 1 to 5, with the spread highlighted and agreed actions recorded. | All members | ASSESS
| ASSESS | The official assessment weighting mapped to the rubrics and to the forms that supply the evidence. | Team Leader | -
| DASHBOARD | Milestone readiness, effort and schedule, quality, and the contribution check - all read from the logs. | Automatic | -
| PROJECT | The one-page project summary: headline numbers, the earned-value and effort charts, and a plain sentence saying whether the team is on track. | Automatic | -
| CHARTS | Fourteen charts drawn from your logs - earned value, hours, defects by phase, review rates, yields, the quality profile and contribution. | Automatic | -
| IRWEEK | How the risk picture moved each week: raised, closed, still open, and how many are high priority. | Team Leader | -
| RISK | The top open risks and issues from IRTL, ranked by priority. Completed items drop off by themselves. | Automatic | -
| PHASES | The process phase standard: every phase code, what belongs in it, and whether it counts towards development defects. | Reference | LOGT, LOGD, TASK
| DEFECTTYPES | The defect type standard, each with a Flutter example. Types 110 to 150 were added for this course. | Reference | LOGD
| PLANGUIDE | Planning guidelines: how to split effort across phases and what rates to plan against before you have your own data. | Reference | TASK, SCHEDULE
| QUALGUIDE | Quality guidelines: what to aim for on each SUMQ measure, what it means when you are below it, and the order to fix things in. | Reference | SUMQ
| QPROFPARAM | The five targets behind the Quality Profile chart. | Quality & Test Mgr | CHARTS
| CHARTDATA | The calculated series every chart reads from. Look here only to find out why a chart is empty. | - | PROJECT, CHARTS
| LISTS | The source lists behind every drop-down. Leave it alone unless you are adding a role or a size measure. | - | -
8. Worked examples
| Situation | What you record
| You spend the morning writing the SRS, with a 15-minute phone call in the middle | LOGT: date 20-Oct-26, member your name, milestone M1, phase REQ, task ID T01, start 09:00, stop 12:00, interrupt 15. Delta calculates as 165 minutes. Week fills in by itself.
| During the code review of a login screen, you find a null check that was never written | LOGD: type 60 - Checking, component auth_module, injected in CODE (the mistake was made while coding), removed in CR (you found it in review), fix time 8 minutes, severity Major, from AI code No.
| Copilot generates a form validator; you keep about three quarters of it after review | LOGAI: tool GitHub Copilot, lines generated 60, lines kept 45, reviewer a teammate's name - not yours - verdict Approved with changes, tests written Yes, commit reference PR#7, approved Yes.
| A test that passed last week now fails after a refactor | LOGTEST: update that test's row to Fail with today's date. Then raise the defect in LOGD with injected phase CODE and removed phase UT, and link the two with the defect reference.
| The client asks for an extra screen three weeks before release | CCR: change type Requirement, what changes and why, estimated hours, affected milestone, reviewer and decision. If approved, add the tasks to TASK so the plan reflects reality.
9. Things that go wrong
| Symptom | Cause and fix
| The name drop-downs are empty | FORM-SI has no names in it yet. Every member drop-down in the workbook reads column C of FORM-SI rows 9 to 14. Fill those first.
| A summary number has not changed after I logged work | Press F9, or close and reopen the file. If it still looks wrong, check the phase or task ID you typed in the log - a typo means the row matches nothing and is silently excluded.
| Hours are logged but TASK shows zero actual hours | The Task ID column in LOGT is blank or does not match an ID in TASK. The match is exact, so T1 and T01 are different tasks.
| Defect density and review rates are blank | SUMS has no actual size recorded, so there is nothing to divide by. Fill the actual columns in SUMS at the end of each milestone.
| Someone's peer score looks far too low | Check that every member filled in their own rating block. An empty block is ignored rather than counted as zero, but a block filled in for only some members will skew the average.
| A grey cell shows a wrong number and I want to correct it | Do not type over it. Find the log row that is wrong and fix that. Overwriting a calculated cell breaks the formula permanently and every number downstream of it.
| We forgot to log for two weeks | Reconstruct what you honestly can, mark those rows in the comments column, and say so at the weekly meeting. Inventing plausible numbers is worse than admitting a gap - the gap is recoverable, fabricated data quietly corrupts every conclusion the team draws for the rest of the project.
10. One last thing
The workbook cannot make the team work well. What it can do is make it obvious, early and to everyone, when the team is not - while there is still time to do something about it. A team that logs honestly and looks at the numbers every week will finish; a team that fills this in the weekend before submission will have a very tidy record of a project that went wrong.

## INDEX
Index of Forms
Click a form name to jump to it.
Start here
| Form | What it is for | Owner | When
| MANUAL | Step-by-step manual: what to do, when, and on which form | Read at launch | Week 1
| PROJECT | Project summary: headline numbers and the two charts that matter most | Automatic | Always
Launch - do these once, at the start of each cycle
| Form | What it is for | Owner | When
| SETUP | Course, team, client, repository and the milestone plan | Team Leader | Week 1
| FORM-SI | Member details, contribution rollup and the team charter | All members | Week 1
| ROLES | Who holds which of the six TSP roles in each milestone | Team Leader | Each launch
| GOALS | Measurable team goals with owners and review dates | Team | Each launch
| STRAT | What each cycle delivers, and the stack decisions behind it | Dev Manager | Each launch
Plan - the commitment the team makes
| Form | What it is for | Owner | When
| TASK | Task plan, estimates, ownership and earned value | Planning Manager | Each launch
| SCHEDULE | Hours per week, planned against earned value | Planning Manager | Each launch
Record - fill these as the work happens, not afterwards
| Form | What it is for | Owner | When
| LOGT | Time recording log - one row per working session | All members | Daily
| LOGD | Defect recording log - every defect, wherever found | All members | Daily
| LOGTEST | Test case log with status, type and coverage evidence | Quality & Test Mgr | Daily
| LOGAI | AI-assisted development log with reviewer and verdict | All members | Every AI change
| LOGCLIENT | Client meetings, decisions, actions and sign-off | Product Owner | Each meeting
| LOGGIT | Weekly GitHub activity read from repository Insights | Support Manager | Weekly
Track - the weekly rhythm
| Form | What it is for | Owner | When
| WEEK | Weekly status: hours, earned value, risk and commitment | Team Leader | Weekly
| IRTL | Issue and risk tracking with likelihood, impact and owner | Team Leader | Weekly
| IRWEEK | How the risk picture moved week by week - raised, closed, still open | Team Leader | Weekly
| RISK | The top open risks from IRTL, ranked by priority | Automatic | Weekly
| CCR | Change requests against an agreed baseline | Support Manager | As needed
Summarise - these calculate themselves
| Form | What it is for | Owner | When
| SUMS | Size summary for components and documents | Planning Manager | Each milestone
| SUMP | Plan summary: size, time in phase, defects injected and removed | Planning Manager | Each milestone
| SUMQ | Quality summary: density, yield, review rates, test quality | Quality & Test Mgr | Each milestone
| CHARTS | The fourteen TSP charts, drawn from your own logs | Automatic | Always
Evaluate - the assessed forms
| Form | What it is for | Owner | When
| PEER | Peer and individual evaluation, 10 categories out of 50 | All members | Each milestone
| TEAMEVAL | Team dynamics evaluation, 10 variables out of 50 | All members | Each milestone
| ASSESS | Assessment tracker mapped to the published rubrics | Team Leader | Each milestone
| DASHBOARD | Readiness, effort, quality and contribution at a glance | Automatic | Always
Standards and guidance - read these, do not edit them
| Form | What it is for | Owner | When
| PHASES | Process phase standard: every phase code, what belongs in it | - | Read in Week 1
| DEFECTTYPES | Defect type standard with a Flutter example of each | - | Read in Week 1
| PLANGUIDE | Planning guidelines: effort split and the rates to plan against | - | Each launch
| QUALGUIDE | Quality guidelines: what good looks like on each SUMQ measure | - | Each milestone
| QPROFPARAM | The five targets behind the Quality Profile chart | Quality & Test Mgr | Set once
Machinery - calculated, leave alone
| Form | What it is for | Owner | When
| CHARTDATA | The series every chart reads from | - | -
| LISTS | Source lists behind every drop-down in the workbook | - | -

## PROJECT
Project Summary
The one page to open first. Everything here is calculated from the logs.
| Project |  |  | Report date
| Team |  |  | Current week
| Client |  |  | Team size
| Instructor |  |  | Repository
Headline Measures
| Planned hours | Actual hours | Planned value to date | Earned value to date | New & changed LOC | Defects removed | Defects / KLOC | Test cases | Test pass rate
Earned Value and Effort
Where the team stands

## SETUP
Project Setup
Fill this sheet once at team launch. Every other form reads from here.
Team & Project Identification
| Course | TMA3084 Software Engineering Laboratory
| Semester | Semester 1, Session 2026/2027
| Instructor | Ts. Nurfauza Jali
Lab Demonstrator
Lab Group (1 or 2)
Team Name / Number
Project Title
Client Organisation
Client Contact & Email
GitHub Repository URL
Project Board URL
| Team Size | 5
Milestone Plan
ID | Milestone | Week | Start | Due | Weight | Status | Key Deliverables
M1 | Proposal & Planning | 5 | 2026-10-19 | 2026-10-25 | 10% |  | Proposal, SRS draft, GitHub repo, Team Charter, client approval, >=2 client meetings
M2 | Requirements & Design | 9 | 2026-11-16 | 2026-11-20 | 15% |  | Revised SRS, SDD, Flutter prototype (4-5 screens), >=10 LOGAI entries, test plan (>=20 cases), >=4 client meetings
M3 | Implementation & Testing | 13 | 2026-12-14 | 2026-12-20 | 35% |  | Final SDD, >=50 tests at >=60% coverage, GitHub Actions green, APK/IPA build, >=6 client meetings
M4 | Release & Oral Commitment | 15 | 2026-12-28 | 2027-01-02 | 40% |  | Final report, user manual, demo video 5-10 min, presentation, client sign-off, v1.0.0 release
Course Thresholds (used by DASHBOARD to flag a team that is behind)
Threshold | M1 | M2 | M3 | M4 |  |  | Notes
Minimum commits (cumulative) | 15 | 30 | 50 | 70 |  |  | Git history, all branches merged to develop
Minimum pull requests merged | 3 | 8 | 15 | 20 |  |  | Every PR needs at least one reviewer approval
Minimum client meetings (cumulative) | 2 | 4 | 6 | 7 |  |  | Logged in LOGCLIENT with client sign-off
Minimum LOGAI entries (cumulative) | 2 | 10 | 15 | 18 |  |  | Every AI-assisted change reviewed and logged
Minimum test cases (cumulative) | 0 | 20 | 50 | 60 |  |  | LOGTEST; unit + widget + integration
Minimum code coverage | 0% | 30% | 60% | 60% |  |  | Critical business logic; from coverage report
Minimum hours per member (cumulative) | 15 | 40 | 80 | 100 |  |  | LOGT; flags under-contribution

## FORM-SI
Form SI - Student & Team Information
One row per member. Names entered here feed every drop-down in the workbook.
| Team |  |  | Project
| Repository |  |  | Client
Team Members
# | Matric No. | Full Name | UNIMAS Email | Phone | GitHub Handle | Primary Role | Secondary Role | Plan Hrs | Actual Hrs | Share of Team Hrs | Flag
1
2
3
4
5
6
TEAM TOTAL
Team Charter (agree in Week 1, revisit at every launch)
Team vision
Communication norms
Definition of done
Conflict resolution
Quality standards
Commitment
Note on H8: Only the member who doubles up this cycle has a secondary role - leave it blank for everyone else. ROLES is where the full rotation lives.
Note on L8: LOW = this member has logged well under an even share of team hours. HIGH = carrying a disproportionate load. Both are conversations to have at the weekly meeting, not automatic verdicts.
Note on B18: What this product is for, in one sentence the client would recognise.
Note on B19: Channel, response time, meeting cadence, language.
Note on B20: Code reviewed, tests written and passing, CI green, documented.
Note on B21: How disagreements are escalated and settled.
Note on B22: Coverage floor, lint rules, review turnaround, AI-code review rule.
Note on B23: Expected hours per member per week and how absence is handled.

## ROLES
Role Assignment Matrix
Six roles, five of you. One member doubles up each cycle and the double rotates, so everyone leads something.
Team
Roles by Milestone
Role | What this role owns in TMA3084 | M1 | M2 | M3 | M4
Team Leader | Runs the launch and the weekly meeting, keeps the team to its plan, owns the relationship with the instructor and demonstrator, reports status.
Product Owner | Owns the client relationship and the backlog. Books and chairs client meetings, turns client needs into prioritised user stories, obtains sign-off.
Development Manager | Owns the Flutter codebase and the architecture. Allocates implementation work, enforces the branching model and the pull-request review rule.
Planning Manager | Owns TASK and SCHEDULE. Produces the plan, tracks earned value weekly, raises the alarm when the team drifts off plan.
Quality & Test Manager | Owns SUMQ, LOGD and LOGTEST - the review, inspection and test discipline. Tracks defect density, yield and coverage, chairs inspections, owns the AI-code review rule, and reports release readiness.
Support Manager | Owns the repository, CI/CD, environments, builds and configuration control. Maintains LOGGIT and the CCR log.
Role Load Check - calculated from the matrix above, do not type here
Member | Reading | M1 | M2 | M3 | M4
Members holding two roles
Roles filled
Role Rotation Rule
There are six roles and five of you, so in every cycle exactly one member holds two roles and nobody holds more than two. The double role rotates - the same member does not carry it twice in a row - and every member holds a role in every cycle. No member may hold the same role for more than two consecutive milestones. Agree the rotation at the launch meeting and record it above; a change mid-cycle goes through the CCR log with the reason stated. If your team has four members, two of you will double up; the check above works that out from the team size.
Note on C7: Six roles, and nobody may hold more than two of them in one cycle. With five members that means exactly one member doubles up; with four it means two do. The check below works this out from the team size on SETUP.

## GOALS
Team & Role Goals
A goal that cannot be measured is a wish. Every goal needs a number and an owner.
Team
Goals
# | Stakeholder | Goal | Measure | Target | Actual | Owner | Review By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
Suggested starting goals (replace with your own)
| Stakeholder | Goal | Measure | Target
| Client | Client accepts the delivered app | Client sign-off obtained | Yes by M4
| Team | Finish within the planned effort | Actual hours / planned hours | 0.9 - 1.1
| Quality | Catch defects before test | % defects removed before unit test | >= 70%
| Quality | Keep the released build clean | Defects found in acceptance test | 0 critical
| Process | Every AI-generated change is reviewed | LOGAI entries approved / total | 100%
| Process | Keep the main branch releasable | GitHub Actions pass rate on develop | >= 95%
| Individual | Contribution is evenly shared | Each member's share of team hours | within +/-40% of even

## STRAT
Development Strategy
What gets built in each cycle, what is reused, and what could go wrong.
Cycle Strategy
# | Milestone | Scope delivered this cycle | Build / buy / reuse decision | Main technical risk | Mitigation | Owner
1 | M1
2 | M2
3 | M3
4 | M4
Technology Stack Decisions
# | Area | Decision | Why | Alternative considered | Decided | Owner
1 | Mobile framework
2 | State management
3 | Backend / data
4 | AI capability & API
5 | Authentication
6 | Testing framework
7 | CI/CD
8 | Release channel

## TASK
Form TASK - Task Plan & Earned Value
Break the cycle into tasks of roughly 2-10 hours. A task is done or it is not - no part marks.
Team |  |  |  | Tasks |  | Plan hrs |  | Actual hrs |  |  | Complete |  |  | Earned value
Task ID | M/stone | Phase | Component | Task | Owner | Est. size | Size measure | Rate /hr | Est. hrs | Plan hrs | Plan wk | Actual hrs | Act. wk | Status | Plan value | Earned value | Cum PV | Cum EV
Note on J7: Estimated hours from size and rate. If you have no rate data yet, leave size and rate blank and put your judgement straight into Plan hrs.
Note on Q7: Earned value is only credited when the task is marked Complete. Half-finished work earns nothing - that is what stops a plan from quietly slipping.

## SCHEDULE
Form SCHEDULE - Weekly Schedule & Earned Value
Planned hours are what the team commits to. Earned value is what it actually delivered.
Team |  |  |  | Task plan hrs |  | Schedule plan hrs |  | Difference
Week | Week starting | Plan hrs | Cum plan | Actual hrs | Cum actual | Plan value | Cum PV | Earned value | Cum EV | EV vs PV | Comment
3 | 2026-10-05
4 | 2026-10-12
5 | 2026-10-19
6 | 2026-10-26
7 | 2026-11-02
8 | 2026-11-09 | [9 empty] | Mid-semester break
9 | 2026-11-16
10 | 2026-11-23
11 | 2026-11-30
12 | 2026-12-07
13 | 2026-12-14
14 | 2026-12-21
15 | 2026-12-28
TOTAL
Note on K7: Negative means the team has earned less value than it planned to by this week - it is behind, regardless of how many hours it has burned.

## LOGT
Form LOGT - Time Recording Log
One row per working session. Delta is calculated; never type over it.
Team |  |  |  | Total hours logged |  |  | Sessions
Date | Member | Milestone | Week | Phase | Task ID | Component / what you worked on | Start | Stop | Interrupt (min) | Delta (min) | AI used? | Comments
Note on F6: Must match an ID on the TASK sheet so the hours roll up against the plan. Leave blank only for unplanned work, and then add the task to TASK afterwards.
Note on J6: Minutes of interruption to subtract: a phone call, a break, switching to something else. Be honest - interrupt time is what makes the rate data usable.

## LOGD
Form LOGD - Defect Recording Log
Every defect found, wherever it was found. A defect caught in review still counts.
Team |  |  |  | Defects recorded |  |  | Total fix time (hrs)
Date | Defect ID | Found by | Milestone | Type | Component | Injected in | Removed in | Fix time (min) | Fix reference | Severity | From AI code? | Description & root cause
Note on G6: The phase where the mistake was MADE, not where you noticed it. Being honest here is the whole point - it is what tells you which review to strengthen.
Note on L6: Mark Yes if the faulty line came from Copilot, Claude or any other generator. This is how the team learns where unreviewed AI output costs it time.

## LOGTEST
Form LOGTEST - Test Case Log
The evidence behind the Testing & Release rubric. Automated tests still get a row.
Team |  |  |  | Cases |  | Passed |  | Pass rate |  | Automated
Date run | Test ID | Module / Screen | What is being tested | Type | Expected result | Actual result | Status | Milestone | Tester | Defect ref (LOGD) | Automated?

## LOGAI
Form LOGAI - AI-Assisted Development Log
Every change where a generator wrote code that reached the repository. No entry, no merge.
Team |  |  | Entries |  | Approved |  | Lines generated |  |  | Lines kept after review |  |  | Keep rate
Date | Member | Milestone | File / module | Feature or behaviour | AI tool | Prompt (summarised) | Lines gen. | Lines kept | Keep % | Reviewer | Review verdict | Tests written? | Test status | Commit / PR ref | Approved?
Note on I6: How many of the generated lines survived review and ended up merged. A low keep rate is not a failure; it is useful evidence about where the tool helps and where it does not.
Note on K6: The reviewer must not be the person who prompted the generator. A row where member and reviewer are the same name is highlighted red - self-review does not satisfy the rule.

## LOGCLIENT
Form LOGCLIENT - Client Engagement Log
Proof of the client relationship. M1 needs 2 meetings, M2 needs 4, M3 needs 6 - cumulative.
Client |  |  |  |  | Meetings held |  | Face-to-face |  | Total hours
Date | Milestone | Mode | Hours | Team attendees | Client attendees | Purpose / agenda | Decisions made | Action items & owners | Evidence (minutes / photo link) | Client sign-off?

## LOGGIT
Form LOGGIT - GitHub Activity Log
Recorded weekly from the repository's Insights tab. These are facts, not estimates.
Repository |  |  |  |  | Commits |  | PRs merged |  | Reviews
Week | Milestone | Member | Commits | PRs opened | PRs merged | Reviews given | Issues closed | Lines + | Lines - | CI green? | Notes

## WEEK
Form WEEK - Weekly Status Report
Filled in at the weekly team meeting. This is the record the instructor and demonstrator read.
Team |  |  |  |  | Meetings held
Week | Week starting | M/stone | Met? | Present | Plan hrs | Actual hrs | Act/Plan | Cum PV | Cum EV | EV variance | Status | Biggest risk or issue this week | Commitment for next week
3 | 2026-10-05
4 | 2026-10-12
5 | 2026-10-19
6 | 2026-10-26
7 | 2026-11-02
8 | 2026-11-09
9 | 2026-11-16
10 | 2026-11-23
11 | 2026-11-30
12 | 2026-12-07
13 | 2026-12-14
14 | 2026-12-21
15 | 2026-12-28

## IRTL
Form IRTL - Issue & Risk Tracking Log
A risk might happen; an issue already has. Both need an owner and a date, or they are just worry.
Team |  |  |  | Open |  | High priority
ID | Date raised | Type | Scope | Description | Likelihood | Impact | Priority | Owner | Mitigation / action taken | Follow-up | Status | Date closed

## IRWEEK
Issue & Risk Week Summary
How the risk picture moved each week. Calculated from IRTL - the comment column is yours.
Week | Week starting | Raised | Closed | Open at end | High priority open | Risks open | Issues open | What the team did about it this week
3 | 2026-10-05
4 | 2026-10-12
5 | 2026-10-19
6 | 2026-10-26
7 | 2026-11-02
8 | 2026-11-09
9 | 2026-11-16
10 | 2026-11-23
11 | 2026-11-30
12 | 2026-12-07
13 | 2026-12-14
14 | 2026-12-21
15 | 2026-12-28
Reading this sheet
Watch the Open at end column across the weeks, not any single number. A count that climbs steadily means the team is raising risks faster than it resolves them - which is still better than a column of zeros, because a project with no recorded risks is a project where nobody is looking for them.

## RISK
Top Risk Register
The highest-priority open items from IRTL, ranked. Read this at every weekly meeting.
Open items |  | High priority (6 or more)
Rank | ID | Risk or issue | Likelihood | Impact | Priority | Owner | Follow-up | Status | Mitigation in hand
1
2
3
4
5
6
7
8
9
10
11
12
Priority is likelihood times impact
High = 3, Medium = 2, Low = 1, so priority runs from 1 to 9. Six or more needs an owner and a date this week. A risk with no owner is not being managed, it is being hoped about.
Note on A6: This sheet is calculated from IRTL and sorted by priority. To change anything here, change the row in IRTL - a completed item drops off this list automatically.

## CCR
Form CCR - Configuration Change Request
Once a baseline is agreed with the client, changes go through here - not through a quiet commit.
Team |  |  |  | Requests |  | Approved |  | Added hours
CCR ID | Date | Raised by | Change type | Component | What changes | Why - whose need does this serve | Est. hrs | M/stone | Reviewer | Decision | Decided on | Notes

## SUMS
Form SUMS - Size Summary
Screens, widgets, services and their size. Without size there is no density, no rate, no learning.
Team
[6 empty] | PLANNED SIZE | [6 empty] | ACTUAL SIZE
ID | Assembly / part name | Type | Parent assembly | Owner | Size measure | Base | Deleted | Modified | Added | Reused | New & changed | Total | Base | Deleted | Modified | Added | Reused | New & changed | Total
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
TOTAL (Dart LOC rows only)
Document & Artefact Size
| Artefact |  |  |  | Measure | Plan | [5 empty] | Actual
| Software Requirements Specification (SRS) |  |  |  | SRS Pages
| Software Design Document (SDD) |  |  |  | SDD Pages
| User Manual |  |  |  | Documents
| Test Plan |  |  |  | Documents
| Final Report |  |  |  | Documents
| Screens delivered |  |  |  | Screens
| Reusable widgets built |  |  |  | Widgets
| API endpoints consumed |  |  |  | API Endpoints

## SUMP
Form SUMP - Plan Summary
Plan columns are yours to fill at the launch. Actual columns read themselves out of the logs.
Team |  |  | Cycle / milestone
Program Size
| Plan | Actual | Actual % |  | Source
Total requirements pages (SRS) |  |  |  |  | SUMS document block
Total design pages (SDD) |  |  |  |  | SUMS document block
New & changed Dart LOC (N) |  |  |  |  | SUMS component totals
Total Dart LOC (T) |  |  |  |  | SUMS component totals
Reused Dart LOC (R) |  |  |  |  | SUMS component totals
Screens delivered |  |  |  |  | SUMS document block
Reusable widgets built |  |  |  |  | SUMS document block
Time in Phase (hours)
Phase | Plan | Actual | Actual % | Plan % | Description
MGMT |  |  |  |  | Management & Miscellaneous
STRAT |  |  |  |  | Launch & Strategy
PLAN |  |  |  |  | Planning
REQ |  |  |  |  | Requirements / SRS
STP |  |  |  |  | System Test Plan
REQINSP |  |  |  |  | Requirements Inspection
HLD |  |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  |  | Integration Test Plan
HLDINSP |  |  |  |  | HLD Inspection
DLD |  |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  |  | Detailed Design Review
TD |  |  |  |  | Test Development
DLDINSP |  |  |  |  | Detailed Design Inspection
CODE |  |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  |  | Code Inspection
UT |  |  |  |  | Unit Test
WT |  |  |  |  | Widget Test
IT |  |  |  |  | Build & Integration Test
CICD |  |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  |  | System Test
UAT |  |  |  |  | Client Acceptance Test
DOC |  |  |  |  | Documentation & User Manual
PM |  |  |  |  | Postmortem
TOTAL
Defects Injected
Phase | Plan | Actual | Actual % |  | Description
PLAN |  |  |  |  | Planning
REQ |  |  |  |  | Requirements / SRS
STP |  |  |  |  | System Test Plan
REQINSP |  |  |  |  | Requirements Inspection
HLD |  |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  |  | Integration Test Plan
HLDINSP |  |  |  |  | HLD Inspection
DLD |  |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  |  | Detailed Design Review
TD |  |  |  |  | Test Development
DLDINSP |  |  |  |  | Detailed Design Inspection
CODE |  |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  |  | Code Inspection
UT |  |  |  |  | Unit Test
WT |  |  |  |  | Widget Test
IT |  |  |  |  | Build & Integration Test
CICD |  |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  |  | System Test
TOTAL DEVELOPMENT DEFECTS INJECTED
UAT - injected in client acceptance test
PL - injected after release
Defects Removed
Phase | Plan | Actual | Actual % |  | Description
PLAN |  |  |  |  | Planning
REQ |  |  |  |  | Requirements / SRS
STP |  |  |  |  | System Test Plan
REQINSP |  |  |  |  | Requirements Inspection
HLD |  |  |  |  | High-Level Design / Architecture (SDD)
ITP |  |  |  |  | Integration Test Plan
HLDINSP |  |  |  |  | HLD Inspection
DLD |  |  |  |  | Detailed Design (screens, widgets, models)
DLDR |  |  |  |  | Detailed Design Review
TD |  |  |  |  | Test Development
DLDINSP |  |  |  |  | Detailed Design Inspection
CODE |  |  |  |  | Code - hand-written Dart/Flutter
AIGEN |  |  |  |  | Code - AI-assisted generation (Vibe)
CR |  |  |  |  | Code Review / Pull-Request Review
BUILD |  |  |  |  | Build & Static Analysis (flutter analyze)
CODEINSP |  |  |  |  | Code Inspection
UT |  |  |  |  | Unit Test
WT |  |  |  |  | Widget Test
IT |  |  |  |  | Build & Integration Test
CICD |  |  |  |  | CI/CD Pipeline (GitHub Actions)
ST |  |  |  |  | System Test
TOTAL DEVELOPMENT DEFECTS REMOVED
UAT - removed in client acceptance test
PL - removed after release
Summary Measures
| Plan | Actual |  |  | What it tells you
LOC per hour |  |  |  |  | Team productivity. Compare cycle to cycle, never team to team.
Cost performance index (CPI) |  |  |  |  | Planned hours over actual hours. Below 1.0 means the work cost more than planned.
Defects per KLOC (development) |  |  |  |  | Defect density in new and changed code.
Hours per defect removed |  |  |  |  | Rising cost per defect is the signal to review earlier, not test harder.
% of code that is AI-assisted |  |  |  |  | Lines kept from AI generation as a share of new and changed code.
Defects traced to AI-generated code |  |  |  |  | If this climbs, the review rule is not being applied.
Client acceptance defects |  |  |  |  | The number the client sees. The goal is zero critical.

## SUMQ
Form SUMQ - Quality Summary
Everything here is derived. If a number looks wrong, the log is wrong - fix the log, not this sheet.
Team |  |  | Cycle / milestone
Defect Density
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Defects / page - requirements inspection |  |  |  |  | Few defects per page usually means the inspection was too fast, not that the SRS was clean.
Defects / page - design inspection
Defects / KLOC - Detailed design review
Defects / KLOC - Detailed design inspection
Defects / KLOC - Code review / PR review
Defects / KLOC - Build & static analysis
Defects / KLOC - Code inspection
Defects / KLOC - Unit test
Defects / KLOC - Widget test
Defects / KLOC - Integration test
Defects / KLOC - System test
Defects / KLOC - total development
Defects / KLOC - client acceptance test |  |  | 0 |  | This is the one the client experiences. Everything upstream exists to drive it to zero.
Defect Ratios
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Design review defects / unit test defects |  |  | >= 2.0 |  | Finding design defects in test instead of review is the expensive way round.
Code review defects / build defects |  |  | >= 2.0
Development Time Ratios
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Requirements inspection / requirements |  |  | >= 0.20
Design inspection / high-level design |  |  | >= 0.20
Detailed design / code |  |  | >= 1.00
Design review / detailed design |  |  | >= 0.50
Code review / code |  |  | >= 0.50
AI generation / total coding |  |  | no target |  | Not a quality target - it tells the team how much of its coding effort is prompting rather than writing, which is worth knowing at the postmortem.
Review & Inspection Rates
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Requirements inspection (pages/hr) |  |  | <= 10 |  | Reviewing faster than the guideline reliably means defects were missed.
Design inspection (pages/hr) |  |  | <= 10 |  | Reviewing faster than the guideline reliably means defects were missed.
Detailed design review (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Detailed design inspection (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Code review (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Code inspection (LOC/hr) |  |  | <= 200 |  | Reviewing faster than the guideline reliably means defects were missed.
Appraisal / failure ratio (A/FR) |  |  | >= 2.0 |  | Time spent reviewing versus time spent fixing in test. Low A/FR predicts a painful system test.
Phase Yield - % of defects present that this phase caught
Measure | Plan | Actual | Guideline | Verdict | Interpretation
PLAN - Planning
REQ - Requirements / SRS
STP - System Test Plan
REQINSP - Requirements Inspection
HLD - High-Level Design / Architecture (SDD)
ITP - Integration Test Plan
HLDINSP - HLD Inspection
DLD - Detailed Design (screens, widgets, models)
DLDR - Detailed Design Review
TD - Test Development
DLDINSP - Detailed Design Inspection
CODE - Code - hand-written Dart/Flutter
AIGEN - Code - AI-assisted generation (Vibe)
CR - Code Review / Pull-Request Review
BUILD - Build & Static Analysis (flutter analyze)
CODEINSP - Code Inspection
UT - Unit Test
WT - Widget Test
IT - Build & Integration Test
CICD - CI/CD Pipeline (GitHub Actions)
ST - System Test
Process Yield - % of defects removed before entering this phase
Measure | Plan | Actual | Guideline | Verdict | Interpretation
% removed before build & static analysis |  |  | >= 70%
% removed before unit test |  |  | >= 70%
% removed before widget test |  |  | >= 85%
% removed before integration test |  |  | >= 85%
% removed before system test |  |  | >= 85%
% removed before client acceptance test |  |  | >= 95%
Test & Release Quality (feeds the Testing and Release rubric)
Measure | Plan | Actual | Guideline | Verdict | Interpretation
Test cases recorded |  |  | >= 50 by M3
Test pass rate |  |  | >= 95%
Automated share of test cases |  |  | >= 70%
Unit tests |  |  | ~60% of cases
Widget tests |  |  | ~30% of cases
Integration tests |  |  | ~10% of cases
Code coverage reported by CI (enter manually) |  |  | >= 60% |  | Read from the coverage job in GitHub Actions, not estimated.
Open defects at this milestone |  |  | 0 critical |  | A defect with no fix reference is still open.

## CHARTS
Chart Gallery
Fourteen charts, redrawn from your own logs. They update themselves - there is nothing to press.
| Planned against earned, with a dashed projection at your current rate. The gap is the schedule story. | Value planned and value actually earned, week by week. Empty bars are weeks nothing finished.
| Effort against the plan. Below the line with earned value also low means the team is simply not working the hours it committed to. | The same comparison week by week. Look for the weeks that collapsed and ask what happened in them.
| Share of components that entered each phase with no defect found. Should climb towards acceptance test. | The total climbing through the process. A curve that stays flat until test is a team not reviewing.
| Where defects are actually being caught. The mass should sit left of unit test, not right of it. | The same picture normalised by code size, so cycles and components can be compared.
| Your rate against the 200 LOC/hour guideline. Above the guideline means defects were missed, whatever the review found. | Of the defects present when each phase began, the share that phase caught.
| Defects removed before reaching each test phase, against the guideline. The acceptance-test bar is the one the client experiences. | Five axes, each scored against its QPROFPARAM target. A shape that fills the pentagon is a team finding its own defects.
| Hours logged and commits made, side by side. Not an assessment - a prompt for a conversation. | Where the effort was meant to go against where it went. The phases you under-spent are usually the reviews.
Note on A3: Charts refresh when the workbook recalculates. If one looks empty, the log behind it is empty - check CHARTDATA to see which series has no numbers.

## PEER
Form PEER - Peer & Individual Evaluation
Each member rates every member including themselves, 1 to 5, against the 10 rubric categories. 50 marks.
Team |  |  |  |  | Milestone
Summary - score received by each member (out of 50)
# | Member | Avg from peers | Self-rating | Peer vs self | Score /50 | Score /10 | Rank | Reading
1
2
3
4
5
6
Rating scale
| 1 Well below what the team required |  | 2 Below what the team required |  | 3 Met what the team required
| 4 Consistently met and sometimes exceeded |  | 5 Consistently exceeded
Ratings given by -> member 1
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 2
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 3
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 4
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 5
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Ratings given by -> member 6
# | Category | [6 empty] | What you are judging
1 | Quantity of work | [6 empty] | Produces accurate, complete work that meets or exceeds what the team agreed.
2 | Timeliness of work | [6 empty] | Meets the deadlines the team set, without being chased.
3 | Task support | [6 empty] | Helps other members with their tasks when they need it.
4 | Interaction | [6 empty] | Listens, accepts criticism, communicates respectfully.
5 | Attendance | [6 empty] | Turns up to team and client meetings.
6 | Responsibility | [6 empty] | Carries out assigned tasks and volunteers for others.
7 | Involvement | [6 empty] | Takes part in discussion and brings relevant material to the team.
8 | Leadership | [6 empty] | Steps up and leads when the situation calls for it.
9 | Role assignment | [6 empty] | Performs the duties of the role they hold this cycle.
10 | Overall performance | [6 empty] | Overall contribution against what the team required.
TOTAL /50
Note on C7: Average of the ratings this member received from the other members, out of 50. Self-rating is reported separately so it cannot inflate the score.

## TEAMEVAL
Form TEAMEVAL - Team Evaluation
Each member rates the team's dynamics 1 to 5, anonymously. Then discuss the spread, not just the mean.
Team |  |  |  |  | Milestone
Team Dynamics
# | Variable | 1 <---------------------> 5 | R1 | R2 | R3 | R4 | R5 | R6 | Mean | Spread - talk about this
1 | Goals | Unclear and poorly understood ... Clear, understood, fully committed to
2 | Openness | Members are guarded in discussion ... Members speak freely
3 | Mutual trust | Members are suspicious of each other ... Members trust each other
4 | Attitudes toward difference | Conflict is smoothed over or avoided ... Differences are voiced and worked through
5 | Support | Reluctant to ask for or give help ... Comfortable giving and receiving help
6 | Participation | A few members dominate ... Everyone is involved
7 | Decision-making | Decided by a few ... Everyone is involved in deciding
8 | Flexibility | Locked into rules that are hard to change ... Procedures change as situations change
9 | Use of member resources | Abilities and knowledge are under-used ... Every member's ability is fully used
10 | Overall team performance | Falls well short of requirements ... Consistently exceeds requirements
TOTAL /50
Team score /10
Agreed actions from this evaluation
1
2
3
4

## ASSESS
Assessment Tracker
The official weighting for TMA3084, with the forms that produce the evidence.
Team |  |  |  | Member (for the individual components)
Components
Group | Component | Rubric | Weight | Raw | Out of | Weighted | Evidence lives in | Notes
Final Project (60%) | Proposal & Planning | 1_RUBRIC_Proposal (10%) | 10% |  | 10 |  | STRAT, TASK, SCHEDULE, LOGCLIENT
Final Project (60%) | Requirement Specification | 2_RUBRIC_RequirementSpec (15%) | 15% |  | 15 |  | SUMS (SRS pages), LOGCLIENT, CCR
Final Project (60%) | Project Evaluation - Design & Implementation | 3_RUBRIC_ProjectEvaluation (25%) | 25% |  | 25 |  | SUMS, SUMP, LOGAI, LOGGIT
Final Project (60%) | Testing and Release | 8_RUBRIC_Testing_and_Release (10%) | 10% |  | 10 |  | LOGTEST, SUMQ, LOGD, LOGGIT
Oral Commitment (10%) | Presentation | 4_RUBRIC_Presentation (10%) | 10% |  | 20 |  | Slides, demo video
Practical Exam (30%) | Peer / Individual Evaluation | 5_RUBRIC_Peer_IndividualEvaluation (10%) | 10% |  | 50 |  | PEER
Practical Exam (30%) | Project Evaluation | 6_RUBRIC_ProjectEvaluation (10%) | 10% |  | 50 |  | WEEK, IRTL, TASK
Practical Exam (30%) | Team Evaluation | 7_RUBRIC_TeamEvaluation (10%) | 10% |  | 50 |  | TEAMEVAL
TOTAL
Note
Raw marks are entered by the instructor or demonstrator against the published rubrics. Peer/Individual and Team Evaluation read straight from the PEER and TEAMEVAL forms, so the team can see where it stands before the mark is finalised. This sheet is a tracker, not the official record of marks.

## DASHBOARD
Team Dashboard
Everything here is read from the logs. It is only as honest as the data the team puts in.
Team |  |  |  | Generated
Milestone Readiness (cumulative actual vs the threshold on SETUP)
Measure | M1 | M2 | M3 | M4 |  |  |  | Reading
Commits | [7 empty] | Green means the cumulative figure has reached the threshold for that milestone.
PRs merged
Client meetings
LOGAI entries
Test cases
Team hours
Effort & Schedule
Measure | Plan | Actual | Ratio | Verdict |  |  |  | Reading
Total hours
Tasks complete
Earned value to date
Cost performance index
Quality
Measure | Value | Target | Verdict |  |  |  |  | Reading
Defects recorded
Defects / KLOC (development)
% removed before unit test |  | 70% | [5 empty] | Defects caught before test cost a fraction of defects caught in test.
Test pass rate |  | 95%
Code coverage |  | 60%
Defects from AI-generated code | [7 empty] | Rising count means AI output is reaching the repository without real review.
AI entries without a reviewer |  | 0 | [5 empty] | Any row here breaks the review rule - fix before the milestone.
Open issues & risks
Contribution (the free-rider check)
Member | Hours | Share | Commits | PRs merged | Reviews | LOGAI | Peer /50 | Reading

## PHASES
Process Phase Standard
The phases you may enter in LOGT, LOGD and TASK. Use the code exactly as it appears here.
Code | Phase | Scope | Log time | Log injected | Log removed | Counts as development | Size basis | What belongs in this phase
MGMT | Management & Miscellaneous | S | Y | N | N | N | - | Team admin, lab attendance, instructor and demonstrator check-ins, anything not project work.
STRAT | Launch & Strategy | S | Y | N | N | N | - | The launch meeting, cycle strategy, build-versus-reuse and technology decisions.
PLAN | Planning | S | Y | Y | Y | Y | - | Producing TASK and SCHEDULE, estimating, re-planning after a change request.
REQ | Requirements / SRS | S | Y | Y | Y | Y | Pages | Interviews with the client, user stories, use cases, writing and revising the SRS.
STP | System Test Plan | S | Y | Y | Y | Y | - | Writing the system test plan against the requirements.
REQINSP | Requirements Inspection | S | Y | Y | Y | Y | Pages | Team inspection of the SRS. Log the time you spend inspecting, not preparing.
HLD | High-Level Design / Architecture (SDD) | S | Y | Y | Y | Y | Pages | Architecture, component breakdown, data model, writing the SDD.
ITP | Integration Test Plan | S | Y | Y | Y | Y | - | Writing the integration test plan.
HLDINSP | HLD Inspection | S | Y | Y | Y | Y | Pages | Team inspection of the SDD.
DLD | Detailed Design (screens, widgets, models) | P | Y | Y | Y | Y | LOC | Designing a specific screen, widget, service or model before writing it.
DLDR | Detailed Design Review | P | Y | Y | Y | Y | LOC | Your own review of your detailed design, before anyone else sees it.
TD | Test Development | P | Y | Y | Y | Y | - | Writing test cases - the writing, not the running.
DLDINSP | Detailed Design Inspection | P | Y | Y | Y | Y | LOC | Team inspection of a detailed design.
CODE | Code - hand-written Dart/Flutter | P | Y | Y | Y | Y | LOC | Dart and Flutter you wrote yourself, keyboard to screen.
AIGEN | Code - AI-assisted generation (Vibe) | P | Y | Y | Y | Y | LOC | Prompting a generator and shaping its output. Every AIGEN session needs a LOGAI row.
CR | Code Review / Pull-Request Review | P | Y | Y | Y | Y | LOC | Reviewing someone's pull request, or them reviewing yours. Log it as CR either way.
BUILD | Build & Static Analysis (flutter analyze) | P | Y | Y | Y | Y | LOC | flutter analyze, flutter build, fixing what they report, dependency and signing problems.
CODEINSP | Code Inspection | P | Y | Y | Y | Y | LOC | Team code inspection - several people reading the same code together.
UT | Unit Test | P | Y | Y | Y | Y | LOC | Running and fixing unit tests.
WT | Widget Test | P | Y | Y | Y | Y | LOC | Running and fixing Flutter widget tests.
IT | Build & Integration Test | S | Y | Y | Y | Y | LOC | Building the whole app and testing components together.
CICD | CI/CD Pipeline (GitHub Actions) | S | Y | Y | Y | Y | - | GitHub Actions workflows, the coverage job, release automation.
ST | System Test | S | Y | Y | Y | Y | LOC | Testing the finished app against the SRS, end to end.
UAT | Client Acceptance Test | S | Y | Y | Y | N | LOC | The client or their staff using the app and telling you what is wrong.
DOC | Documentation & User Manual | S | Y | N | N | N | Pages | User manual, final report, API documentation, deployment guide.
PM | Postmortem | S | Y | N | N | N | - | The postmortem: reading your own data and agreeing what changes next cycle.
PL | Product Life (post-release) | N | N | Y | Y | N | LOC | Anything after the release is handed over.
Reading the columns
Scope: S = the phase applies to the system as a whole. P = it applies to one component. N = neither.
Log time: Y means sessions in this phase belong in LOGT.
Log injected / removed: Y means LOGD may name this phase in the Injected in or Removed in column.
Counts as development: Y means the phase feeds the development defect totals on SUMP and the yields on SUMQ.
Size basis: what the phase's rate is measured against when SUMQ computes review rates.

## DEFECTTYPES
Defect Type Standard
The types you may choose in LOGD. Types 10-100 are the TSP standard; 110-150 were added for this course.
Type | Name | What it covers | A Flutter example
10 | Documentation | Comments, README, API docs, user manual | A widget's doc comment describes the old behaviour after a refactor.
20 | Syntax | Dart syntax, spelling, punctuation, typos | Missing semicolon, misspelled identifier, wrong bracket.
30 | Build / Package | pubspec, dependency conflict, Gradle, signing, build config | pubspec version conflict; Gradle or signing config breaks the release build.
40 | Assignment | Declaration, duplicate names, scope, null-safety misuse | A nullable field used without a null check; two widgets sharing a class name.
50 | Interface | Procedure calls, REST/API contract, parameters, serialization | A repository returns a List where the caller awaits a Stream; JSON key mismatch.
60 | Checking | Error messages, input validation, inadequate checks | No validation on a quantity field; an empty list shows a spinner forever.
70 | Data | Structure, content, persistence, local DB / Firestore schema | Dates stored local but compared as UTC; a schema missing a sync-status column.
80 | Function | Logic, pointers, loops, recursion, computation, business rules | A total recalculated on add but not on edit; discount applied before tax.
90 | System | Configuration, timing, memory, platform (iOS/Android) differences | Works on Android, fails on iOS; a timing problem only under slow network.
100 | Environment | Design, compile, test or other support system problems | The emulator, the CI runner or the toolchain itself is the problem.
110 | UI / Layout | Overflow, responsiveness, theming, accessibility, Material 3 misuse | RenderFlex overflow on a small screen; text unreadable at the counter's font setting.
120 | State Management | Provider/Riverpod/GetX misuse, rebuild storms, stale or lost state | setState after dispose; a filter that does not clear when a screen is reopened.
130 | Performance | Jank, frame drops, oversized images, unbounded list builds | A long list janks; an oversized image decoded on every rebuild.
140 | Security | Hard-coded API key, missing auth check, unsafe storage, leaked PII | An API key committed in source; a screen reachable without an auth check.
150 | AI-Generated | Defect traced to AI-generated code that passed review unverified | Generated code that passed review but was wrong - a validator accepting negatives.
Choosing a type
Pick the type that describes the mistake, not the symptom. A crash caused by a missing null check is Assignment, not System. If a defect genuinely spans two types, choose the earlier one in the list - that is where the fix belongs. Type 150 is for a defect that reached the repository inside generated code: use it alongside the From AI code column in LOGD, because together they show whether the review rule is working.

## PLANGUIDE
Planning Guidelines
Use these only until you have your own data. After the first cycle, your own numbers beat any guideline.
Before you have any data
| The first plan is a guess | Your first cycle has no history, so the estimates below are a starting point, not a standard. Record what actually happens and the second plan will be built on your own numbers instead of someone else's.
| Effort per member | Budget about 10 hours per member per week across a 13-week semester. For a five-person team that is roughly 600 team-hours for the whole project. If your plan totals far more than that, you are planning work the team cannot do.
| Task size | Break work into tasks of 2 to 10 hours. Anything larger hides its own progress - you cannot tell a 20-hour task that is half done from one that has barely started.
Splitting the effort across phases
| Rough shape of a cycle | Requirements and design together should be about a third of the effort, implementation about a third, and test, documentation and management the rest. A plan that spends 70% on coding is a plan that will spend its last three weeks in test.
| Phase group | Share of cycle effort | Guide
| Launch, strategy and planning | 8% | STRAT + PLAN + MGMT
| Requirements and inspection | 14% | REQ + REQINSP + STP
| Architecture and inspection | 12% | HLD + HLDINSP + ITP
| Detailed design and review | 16% | DLD + DLDR + DLDINSP
| Implementation | 22% | CODE + AIGEN
| Review and inspection of code | 10% | CR + CODEINSP
| Test development and testing | 13% | TD + BUILD + UT + WT + IT + ST
| CI/CD and release | 2% | CICD
| Documentation and postmortem | 3% | DOC + PM
Rates to plan against
| Activity | Planning rate | Why this number
| Writing requirements | 2 - 4 SRS pages per hour | Includes the thinking, not just the typing.
| Requirements inspection | no faster than 10 pages per hour | Faster than this and you stop finding defects.
| Writing a design | 3 - 5 SDD pages per hour | Diagrams take longer than prose.
| Design inspection | no faster than 10 pages per hour | Same reason as the SRS.
| Writing Dart by hand | 20 - 40 LOC per hour | New and changed lines, including the thinking.
| AI-assisted generation | 60 - 120 LOC per hour kept | Faster to produce, but the review is the real cost.
| Design or code review | no faster than 200 LOC per hour | The single most reliable number in TSP.
| Writing test cases | 4 - 8 cases per hour | A case is a scenario, not a line of code.
A warning about the AI rate
Generated code arrives faster than written code, and teams plan as though that speed carries through to delivery. It does not. The generator moves the work from writing to reviewing, and a team that plans for the first saving without planning for the second cost finds its defects in system test instead of in review. Plan AIGEN at a high rate and plan CR high to match it.

## QUALGUIDE
Quality Guidelines
What good looks like on each SUMQ measure, and what it means when yours is below it.
The idea behind all of it
A defect costs more the later you find it. One caught in a design review costs minutes; the same defect caught in system test costs hours; caught by the client it costs their trust. Every measure on SUMQ exists to answer one question: are you finding your defects early, or is the machine finding them for you late?
| Measure | Aim for | If yours is below it
| Review rate | <= 200 LOC/hour | You read too fast to find anything. The rate, not the hours, is what predicts how many defects a review catches - halve the rate before you add more reviewers.
| Inspection rate | <= 10 pages/hour | Same problem on documents. An SRS inspection at 30 pages an hour finds typos, not missing requirements.
| A/FR (appraisal / failure) | >= 2.0 | You are spending more time fixing in test than reviewing before it. This is the earliest reliable warning that system test will hurt.
| Design review / design time | >= 0.5 | Designs are going to code unreviewed. Defects injected in design are the expensive ones - they survive until integration.
| Code review / code time | >= 0.5 | Code is being merged on a glance. With AI-generated code in the repository this matters more, not less.
| Design time / code time | >= 1.0 | The team is typing before it is thinking. Expect rework.
| Yield before unit test | >= 70% | Most of your defects are reaching test. Each one there costs several times what it would have cost in review.
| Yield before system test | >= 85% | Integration will be slow and unpredictable, because you are still finding unit-level defects there.
| Yield before acceptance test | >= 95% | The client is about to become your tester. This is the number that decides whether handover goes well.
| Defects / KLOC in test | falling each cycle | The absolute number matters less than the direction. A team whose test density rises cycle over cycle is reviewing less, not writing better.
| Defects found in acceptance | 0 critical | Anything critical here was missed by every check you have. Work backwards and find which one.
| Code coverage | >= 60% on logic | Untested logic is not working logic, it is logic nobody has contradicted yet.
| Test pass rate | >= 95% | A suite that is often red stops being read. Fix or delete failing tests - never ignore them.
| AI entries without a reviewer | 0 | Every one of these is generated code merged on trust. This is the single rule most worth enforcing.
The order to fix things in
If several measures are red, fix them in this order: review rate first, because it is the cheapest change and it moves everything downstream; then design review time, because design defects are the costly ones; then coverage. Do not start by adding testers - testing finds defects later and more expensively than reviewing does, and a team that responds to poor quality by testing harder is paying the highest price available for the same information.

## QPROFPARAM
Quality Profile Parameters
The five targets behind the Quality Profile chart. Change them only if your instructor says so.
# | Parameter | Target | What it means | Direction
1 | Design / code time | 1 | Time in detailed design as a multiple of time spent coding. TSP says good work spends at least as long designing as typing. | higher is better
2 | Design review time | 0.5 | Time reviewing your own design as a fraction of design time. | higher is better
3 | Code review time | 0.5 | Time in code and pull-request review as a fraction of coding time. | higher is better
4 | Build defects / KLOC | 10 | Defects found by flutter analyze and the build, per thousand new and changed lines. | lower is better
5 | Unit test defects / KLOC | 5 | Defects found in unit test per thousand new and changed lines. | lower is better
How the profile is scored
Each axis is scored from 0 to 1, where 1 means the target was met. For the first three, the score is your value divided by the target, capped at 1. For the two defect densities it is the target divided by your value, capped at 1, because fewer defects is better. A profile that reaches the edge on all five axes is a team reviewing enough to find its own defects before the machine does.

## CHARTDATA
Chart Data
Every chart on PROJECT and CHARTS reads from here. Calculated - never type in this sheet.
Current week (last week with logged hours) |  |  |  | Weeks worked |  |  | EV earned to date |  |  | EV rate / week
A. Weekly series (earned value and hours)
Week | Plan hrs | Cum plan hrs | Actual hrs | Cum actual hrs | Plan value | Cum planned value | Earned value | Cum earned value | Cum predicted EV
3
4
5
6
7
8
9
10
11
12
13
14
15
B. By development phase (defects, density, yield, time)
Phase | Injected | Removed | Cum removed | Defects / KLOC | Phase yield | Plan hrs | Actual hrs
PLAN
REQ
STP
REQINSP
HLD
ITP
HLDINSP
DLD
DLDR
TD
DLDINSP
CODE
AIGEN
CR
BUILD
CODEINSP
UT
WT
IT
CICD
ST
C. Review and inspection rates (LOC per hour, guideline 200)
Review | Actual rate | Guideline
Design review
Design inspection
Code / PR review
Code inspection
D. Process yield (% of defects removed before entering the phase)
Before | Process yield | Guideline
Build
Unit test
Widget test
Integration test
System test
Acceptance test
E. Percent defect free (share of components with no defect found in that phase)
Component | Build | Unit test | Integration test | System test | Acceptance test
% defect free
E2. Percent defect free by phase (chart series)
Phase | % defect free
Build
Unit test
Integration test
System test
Acceptance test
F. Quality profile (five axes normalised against QPROFPARAM, 1.0 is the target)
Axis | Actual | Target
Design / code time
Design review time
Code review time
Build defect density
Unit test defect density
G. Contribution by member
Member | Hours | Commits | AI entries

## LISTS
Validation Lists
Source lists for every drop-down in this workbook. Edit only the Roles and Size Measure columns.
Phase Code | Phase Description | Defect Type | Milestone | Role | Size Measure | AI Tool | Team Member | Yes/No | Status | Week | Test Type | Severity | Issue or Risk | Priority | Meeting Mode | Task Status | Review Verdict | Change Type | Component Type
MGMT | Management & Miscellaneous | 10 - Documentation | M1 | Team Leader | Dart LOC | GitHub Copilot |  | Yes | Not started | 3 | Unit | Critical | Risk | High | Face-to-face | Planned | Approved | Requirement | Assembly
STRAT | Launch & Strategy | 20 - Syntax | M2 | Product Owner | Screens | Claude |  | No | In progress | 4 | Widget | Major | Issue | Medium | Online (Zoom/Meet) | In progress | Approved with changes | Design | Part
PLAN | Planning | 30 - Build / Package | M3 | Development Manager | Widgets | ChatGPT / GPT-4 |  |  | Blocked | 5 | Integration | Minor |  | Low | Phone | Complete | Changes requested | Code
REQ | Requirements / SRS | 40 - Assignment | M4 | Planning Manager | API Endpoints | Google Gemini |  |  | Complete | 6 | Manual | Cosmetic |  |  | Email / async | Carried over | Rejected | Test
STP | System Test Plan | 50 - Interface |  | Quality & Test Manager | Test Cases | Cursor |  |  | Dropped | 7 | Acceptance |  |  |  |  | Cancelled | Pending | Document
REQINSP | Requirements Inspection | 60 - Checking |  | Support Manager | SRS Pages | Other |  |  |  | 8 | Regression | [6 empty] | Build / CI
HLD | High-Level Design / Architecture (SDD) | 70 - Data |  |  | SDD Pages | None |  |  |  | 9 | Performance
ITP | Integration Test Plan | 80 - Function |  |  | Documents |  |  |  |  | 10 | Security
HLDINSP | HLD Inspection | 90 - System | [7 empty] | 11
DLD | Detailed Design (screens, widgets, models) | 100 - Environment | [7 empty] | 12
DLDR | Detailed Design Review | 110 - UI / Layout | [7 empty] | 13
TD | Test Development | 120 - State Management | [7 empty] | 14
DLDINSP | Detailed Design Inspection | 130 - Performance | [7 empty] | 15
CODE | Code - hand-written Dart/Flutter | 140 - Security
AIGEN | Code - AI-assisted generation (Vibe) | 150 - AI-Generated
CR | Code Review / Pull-Request Review
BUILD | Build & Static Analysis (flutter analyze)
CODEINSP | Code Inspection
UT | Unit Test
WT | Widget Test
IT | Build & Integration Test
CICD | CI/CD Pipeline (GitHub Actions)
ST | System Test
UAT | Client Acceptance Test
DOC | Documentation & User Manual
PM | Postmortem
PL | Product Life (post-release)